## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 13/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-12
Name of the builder |  |  |  |  | Mr. Bhagwanji Dharamshi Mina
Name of the builder company |  |  |  |  | M/s. Kasturi Developers
Name of the Project |  |  |  |  | Regius
Contact Details ( Name & Contact No.) |  |  |  |  | 9819076588
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  |  | Ms. Riddhi
Name / No of the Building |  |  |  |  | 01 Building
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | P52000023791
Project location details |  | Regius, Plot No.F-94 & F-95, Sector.12, Raghunath Road, Kharghar, Panvel, Raigad - 410210.
Plot No |  | F-94 & F-95 |  |  | Sector |  | 12
Road |  | Raghunath Road |  |  | Locality/Village |  | Kharghar
City |  | Kharghar |  |  | District |  | Raigad
Taluka |  | Panvel |  |  | Pin Code |  | 410210
Near by Landmark |  | HP Petrol Pump |  |  | Distance from city centre: |  | About 2.90Km from Kharghar Railway station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | As per Plan |  |  |  | At site
East |  | 24M Wide Road |  |  |  | Raghunath Road
West |  | Other Plot |  |  |  | HP Petrol Pump/Avenue Hills
North |  | 15M Wide Road |  |  |  | Internal Road
South |  | 24M Wide Road |  |  |  | Gharkul Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.0420627,73.0720209
Location Link |  | https://goo.gl/maps/gzU7Zq5iyh6sc353A
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 3434.63
Permissible FSI |  |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1.5
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 10577.28 |  |  |  |  | 5151.95
Total number of Buildings |  |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | CIDCO/BP-17189/TPO(NM & K)/2019/13245 |  |  |  | Dated | 2024-11-27 |  |  | CIDCO/BP-17189/TPO(NM & K)/2019/6267 |  |  |  | 16/12/2019.
Approved Floor plan No. |  | CIDCO/BP-17189/TPO(NM & K)/2019/13245 |  |  |  | Dated | 2024-11-27
Commencement Certificate No. |  | CIDCO/BP-17189/TPO(NM & K)/2019/6267 Valid Up to: G + 1st To 3rd Podium + 4th To 19th Floors |  |  |  | Dated | 16/12/2019.
Commencement Certificate No. Valid Up to: |  | CIDCO/BP-17189/TPO(NM & K)/2019/13245 |  |  |  | Dated | 2024-11-27
1Ground Floor + 2Parking + 19Floor (Total Builup Area = 10577.3 Sqm) Residential Units = 67 Nos, Commercial Units = 22Nos
O. Certificate No.: Approved upto : |  | CIDCO/BP-17189/TPO(NM & K)/2019/13839 Gr + 1st to 21st Floor Residential Units = 67 & Commercial Units = 22 |  |  | Date of approval: | Dated | 2025-03-29 | NA
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 10577.28 |  |  |  | Flats = 67 & Shop = 22
Approved no of units |  |  | Flats = 67, Shop = 22 |  | Approved no of units
Approved no of Floors |  |  | Gr + 1st to 3rd Podium + 4th to 21st Floor
Proposed no of Floors |  |  | Gr + 1st to 3rd Podium + 4th to 21st Floor
Expected Completion |  |  | Completed
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc. | Swimming Pool, Multipurpose Hall, Indoor Games, Yoga Area, Landscape Garden, Decorative Entrance Lobby, Etc.
Quality of construction: |  |  | Good
Projected life of the structure: |  |  | 60 Years
Material laying at Site: |  |  | Nothing
Violations Observed if any : |  |  | NA
Wheather the construction is as per approved Building plan : |  |  | Yes
Construction details: G + 1st To 3rd Podium + 4th to 21st Floor | [8 empty] | Excavation work completed, Plinth work completed, RCC upto 22 Slab completed, Brickwork upto 21 Floor completed, Internal Plaster upto 21 Floor completed, External Plaster upto 21 Floor completed, Flooring upto 21 Floor completed, Painting upto 21 Floor completed, Finishing upto 21 Floor completed
Ground |  | 1 | Podium |  | 0 |  | Floors | 21 | All work Completed. Wait For OC.
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. Provide OC.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Excavation |  | 21 | 100% |  | 100% |  | 100%
Plinth |  | 21 | 100%
RCC |  | 22 | 100% | [5 empty] | Excavation in process |  | 10.5
Brickwork | Brickwork & Internal Plaster | 21 | 100% | [5 empty] | Excavation Completed |  | 21
Internal Plaster | Brickwork & Internal Plaster | 21 | 100%
Ext. Plaster & Plumbing | External Plaster & Plumbing | 21 | 100% | [5 empty] | Footing in Process |  | 5.25
Flooring & Fitting | Flooring & Fitting | 21 | 100% | [5 empty] | Footing Completed |  | 10.5
Painting & Wooden |  | 21 | 100% | [5 empty] | Plinth in process |  | 15.75
Building Common Amenities | Building Common Amenities | 21 | 100% | [5 empty] | Plinth completed |  | 21
Possession |  | 21 | 100%
Recommended Rates of the Property : | [8 empty] | 11000
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 14600 |  |  | Smith verbal on higher side
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 20000
Club House Charges | [5 empty] | 450000
Society formation charges | [5 empty] | 100000
Development charges | [5 empty] | 550000 |  |  |  | 1447.5835 | 506654.221
Recommended rate of Parking | [5 empty] | 800000 |  |  |  | 1214.4689 | 546511.0043
Distressed valuation of the Property | [5 empty] | 11680
Commercial Area Details :
Building & Wing |  | No. of Shops | Total Carpet Area |  |  | Total Saleable Area
Building |  | 22 | 15716.6563 |  |  | 26718.3158 |  |  |  |  | 134976.9142 | 85331.9544
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
Building |  | 67 | 69615.2981 |  |  | 108258.5985
Total |  | 89 | 85331.9544 |  |  | 134976.9142
Building details Floor Wise
Details of Commercial & Residential in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | Floor
70%
Ground Floor is For Commercial Entrance Lobby, Metre Room & Parking
1 |  | Shop | 465.0156 |  | 0 | 790.5265 | Ground Floor is For Commercial Entrance Lobby, Metre Room & Parking |  |  | 43.101 | 1.7
2 |  | Shop | 444.7792 |  | 0 | 756.1247 |  |  |  |  | 1.7
3 |  | Shop | 688.4547 |  | 0 | 1170.3729 |  |  |  |  | 1.7
4 |  | Shop | 939.934 |  | 0 | 1597.8878 |  |  |  |  | 1.7
5 |  | Shop | 757.1505 |  | 0 | 1287.1559 |  |  |  | 70.1066 | 1.7
6 |  | Shop | 728.8197 |  | 0 | 1238.9934 |  |  |  |  | 1.7 | 67.4738
7 |  | Shop | 733.0392 |  | 0 | 1246.1666 |  |  |  |  | 1.7
8 |  | Shop | 516.4137 |  | 0 | 877.9032 |  |  |  |  | 1.7
9 |  | Shop | 1111.0601 |  | 0 | 1888.8021 |  |  |  |  | 1.7 | 109.2734
10 |  | Shop | 730.9725 |  | 0 | 1242.6532 |  |  |  |  | 1.7 | 64.3449
11 |  | Shop | 526.3165 |  | 0 | 894.7381 |  |  |  |  | 1.7
12 |  | Shop | 526.3165 |  | 0 | 894.7381 |  |  |  |  | 1.7
13 |  | Shop | 777.8066 |  | 0 | 1322.2713 |  |  |  |  | 1.7
14 |  | Shop | 675.9792 |  | 0 | 1149.1646 |  |  |  |  | 1.7
15 |  | Shop | 675.9792 |  | 0 | 1149.1646 |  |  |  |  | 1.7
16 |  | Shop | 675.9792 |  | 0 | 1149.1646 |  |  |  |  | 1.7
17 |  | Shop | 675.9792 |  | 0 | 1149.1646 |  |  |  |  | 1.7
18 |  | Shop | 675.9792 |  | 0 | 1149.1646 |  |  |  |  | 1.7
19 |  | Shop | 607.7893 |  | 0 | 1033.2417 |  |  |  |  | 1.7
20 |  | Shop | 741.7257 |  | 0 | 1260.9337 |  |  |  |  | 1.7
21 |  | Shop | 675.9792 |  | 0 | 1149.1646 |  |  |  |  | 1.7
22 |  | Shop | 1365.1874 |  | 0 | 2320.8185 |  |  |  | 126.9382 | 1.7
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | Floor |  |  | 67
55%
1st & 2nd Podium Floor
3rd Podium Floor for Gym, Swimming Pool, Banquet Hall, SPA, Garden, Yoga room, & Indoor Games
4th Floor For Residential
1 |  | 3BHK | 961.6773 |  | 531.311 | 1623.4276 | 4th Floor For Residential |  |  |  | 48.755
2 |  | 2BHK | 755.1484 |  | 16.5766 | 1187.0566 |  |  |  | 62.1775
3 |  | 2BHK | 755.1484 |  | 16.5766 | 1187.0566
4 |  | 3BHK | 979.6962 |  | 755.622 | 1707.4347 |  |  |  |  | 30.135
5th, 7th, 9th, 11th, 13th, 15th Floor
1 |  | 3BHK | 1090.0703 |  | 0 | 1689.6089 | 5th, 7th, 9th, 11th, 13th, 15th Floor |  |  | 86.172 | 5.208 | 8.26
2 |  | 2BHK | 774.7389 |  | 0 | 1200.8453
3 |  | 2BHK | 774.7389 |  | 0 | 1200.8453
4 |  | 3BHK | 1123.6863 |  | 0 | 1741.7137
6th, 8th, 10th, 12th, 14th & 16th Floor (Refuge Area at Midlanding of Staircase)
1 |  | 3BHK | 1090.0703 |  | 0 | 1689.6089 | 6th, 8th, 10th, 12th, 14th, 16th & 18th Floor |  |  |  |  | 1.55
2 |  | 2BHK | 774.7389 |  | 0 | 1200.8453 | [5 empty] | 1.55
3 |  | 2BHK | 774.7389 |  | 0 | 1200.8453 | [5 empty] | 1.55
4 |  | 3BHK | 1123.6863 |  | 0 | 1741.7137 | [5 empty] | 1.55
17th & 19th Floor
1 |  | 3BHK | 1115.032 |  | 0 | 1728.2996 | 17th & 19th Floor |  |  |  | 1.55 | 9431.2352 | 11572.0678
2 |  | 4BHK | 1960.1782 |  | 0 | 3038.2762 |  |  |  |  | 1.55 | 3982.5214 | 4943.5926 | 35834435.3353
3 |  | 3BHK | 1125.7529 |  | 0 | 1744.9171 |  |  |  |  | 1.55
18th & 20th Floor (Refuge Area at Midlanding Of staircase)
1 |  | 3BHK | 1115.032 |  | 0 | 1728.2996 | 18th & 20th Floor (Refuge Area at Midlanding Of staircase) |  |  |  | 1.55 | 9431.2352 | 11572.0678
2 |  | 4BHK | 1960.1782 |  | 0 | 3038.2762 |  |  |  |  | 1.55 | 3982.5214 | 4943.5926 | 35834435.3353
3 |  | 3BHK | 1125.7529 |  | 0 | 1744.9171 |  |  |  |  | 1.55
21st Floor
1 |  | 3BHK | 1115.032 |  | 0 | 1728.2996 | 21st Floor
2 |  | 4BHK | 1960.1782 |  | 0 | 3038.2762
3 |  | 3BHK | 1125.7529 |  | 0 | 1744.9171
Remarks:
1. All work completed. OC received. 2. We considered Saleable area as per our Calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony Area + Chajja Area. 5. We have considered rate by verifying it from market inquire. 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. We have considered proposed No. of Floor for Stage Calculation. 9. As per RERA revised approved CC dated 17/08/2023 permission granted for 11 Floor. But previously approved CC granted for G + 1st To 3rd Podium + 4th To 19th Floors 10. We have updated revised approved CC from CIDCO site on 19/12/2024. 11. We have updated revised Approved Plans (On 27/02/2025). 12. Please check for Airport NOC. 13. Recommended Rates / Other charges of the Property have been revised on 05/03/2025. 14. We have updated approved OC on 30/05/2025.
Undertaking : | [9 empty] | We have consider Terrace area as per the sale plan for Flat No. 404.
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report Prepared By : |  |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Regius
Google Map :
Google Map :
Formulas:
Kharghar = [Kharghar, row above]
N

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 19
Particulars | total floor | 19
plinth | 10 | 3 | 30%
slab | 20 | 0 | 0% |  | Parking |  | Rate
Bricks | 19 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 19 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 19 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 19 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 19 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 3 | 23 |  | Progress |  | 3 | 0 | 0 | 0 | 0 | 0 | 0
RCC | 0 | 0 |  | Recommended |  | 23 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 3% | 23% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0