## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 12/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-12
Name of the builder |  |  |  |  | Mr.Sanjay Yadav
Name of the builder company |  |  |  |  | M/s. S. S. Realty
Name of the Project |  |  |  |  | S. S. Park
Contect Details ( Name & Contect No.) |  |  |  |  | 2506058585/7776948955
Name / no of the Building |  |  |  |  | S. S. Park (Building no.3 - Type C1a - Wing B) /01 Building (01 wing)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, NA Order
RERA Number |  |  |  |  | P99000017470
Project location details |  | S. S. Park, Building no.3 (Type C1a) - Wing B, Gut. no. 193, Village Zhanzhroli, Kelve (E), Palghar 401401.
Gut. no. |  | 193 |  |  | Locality |  | Kelve East
Road |  | Kelve East Road |  |  | District |  | Palghar
City |  | Kelve |  |  | Pin Code |  | 401401
Near by Landmark |  | Kelve Road Station |  |  | Distance from city centre: |  | About 500M from Kelve Road Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 3 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Land |  | Balaji Apt. |  | Open Land |  | Open Land
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 19.623657,72.796870
Location Link |  | https://goo.gl/maps/WQV1Vn89xBh9iic28
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any) : No
Total land area of the project in Sq. Mt. |  |  |  |  | 6299.03
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.9
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 5669.127
Total number of Buildings |  |  |  |  | 01 Building (01 Wing)
Approval Detail : Plan approval
Layout Approval No |  | BS/BP/ZANZROLI/PALGHAR/G.NO.193/NR/337 |  |  |  | Dated | 16/03/2017.
Building plan approval No |  | BS/BP/ZANZROLI/PALGHAR/G.NO.193/NR/337 |  |  |  | Dated | 16/03/2017. | Expiry date:NA
Date of Commencement of Construction |  | NA |  |  |  | Dated | NA | Expiry date: One year from date of issue
NA Order |  | MHSUL/KS.NO.1/T.1A/NAP/SR-191/2016 (Type C1a) = G + 1st to 4th Floor |  |  |  | Dated | 05/08/2017.
O. Certificate No.: |  | NA |  |  | Date of approval: | Dated | NA | Expiry date: NA
Commencement date of construction |  |  | NA |  | Expected Completion |  | 2024-12-31
P
Approved area of the building in Sq.Mt |  |  | 5669.127 |  | Approved no of units residential |  |  | Shops = 06 Flats = 26
Approved no of Floors |  | Building no.3 (Type C1a) = G + 1st to 4th Floor
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | Building no.3 (Type C1a) = G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, External Plaster upto 2.5 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, External Plaster upto 2.5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1 | 1
Excavation |  | 4 | 100% |  | 63.75% |  | 83.12% |  | Excavation in process | 2 | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4 | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1 | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2 | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2.5 | 62.5% | [5 empty] | Basement 2 | 0 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3 | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4 | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the Flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3400 |  |  |  | 3000 to 3400 |  | Gaurav | Cost Sheet | 2022-07-11
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 6000
Maintenance charges | [5 empty] | 18900/-
Society formation charges | [5 empty] | 35000/-
Recommended rate of Parking | [5 empty] | 50000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 2720
Building details Floor Wise
Details of Flats in Building
Flat No. | Description | Gross Carpet area | Built-up Area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building no.3 (Type C1a) - B Wing
Ground Floor For Parking
1 | Shop | 124.3242 | 149.189 |  | 0 | 217 | NA | Ground Floor
2 | Shop | 124.3242 | 149.189 |  | 0 | 217 | NA
3 | Shop | 127.3381 | 152.8057 |  | 0 | 221 | NA
4 | Shop | 162.8593 | 195.4312 |  | 0 | 284 | NA
5 | Shop | 172.8698 | 207.4438 |  | 0 | 301 | NA
6 | Shop | 245.0963 | 294.1155 |  | 0 | 431 | NA
1 | 1 RK | 220.0162 | 264.0194 |  | 0 | 370 | NA
2 | 1 BHK | 312.6942 | 375.233 |  | 0 | 526 | NA
1st to 4th Floors
1 | 1 BHK | 318.2915 | 381.9498 |  | 0 | 535 | NA | 1st to 4th Floors
2 | 1 BHK | 318.2915 | 381.9498 |  | 0 | 535 | NA
3 | 1 BHK | 308.7115 | 370.4538 |  | 0 | 519 | NA
4 | 1 BHK | 308.7115 | 370.4538 |  | 0 | 519 | NA
5 | 1 BHK | 312.6942 | 375.233 |  | 0 | 526 | NA
6 | 1 BHK | 312.6942 | 375.233 |  | 0 | 526 | NA
Remarks: 1. Construction work was stopped. work is same as last visit dtd.11/08/2024 2. We have considered rate by verifying it from market inquire. 3. We have considered Other charges from cost sheet. 4. Car parking is subjected to authentic documentation. 5. We adopted Carpet Area as per Approved Plan. 6 The Built-up is as per Our Calculation. 7. We considered Saleable Area as per builder area sheet. 8. As building have received CC on 05/08/2017, still building work is not completed. 9. As per RERA, completion period of project is expired on 31/12/2024 but still project is under construction. 10. As checked on RERA portal on dated 12/08/2025, we have observed that above project "S. S. Park" is kept under abeyance. 8. On site we meet Mr. Sanjay Yadav(Builder) - 7776948955 & Mr.Rajesh - 7559412038.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | S. S. Park
Google Map :

## Construction % (2)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 3 | 60 | Progress | 10 | 24 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 30 | 18 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 4 | 0 | 0 |  | RCC | 24 | 18
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 4 | 0 | 0 |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 34 | 48

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing | Riddhi Siddhi Apartment | 1Rk | 232 | 336.4 | 2419.7384 | 814000
housing | Riddhi Siddhi Apartment | 1BHK | 299 | 433.55 | 2419.5595 | 1049000
housing | Riddhi Siddhi Apartment | 3BHK | 300 | 435 | 2420.6897 | 1053000
99Acers | Riddhi Siddhi Apartment | 3BHK | 311 | 450.95 | 2421.5545 | 1092000
Average |  |  | 0 | 0 | 2420.3855
Valuation Adopted |  |  |  |  | 2500

## Note
2020-11-07 | Pratiksha
21/11/2020. | Dhanashree | OLD APF
1. Rate has not Changed.

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Construction % (hidden)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 1 | 20 | Progress | 10 | 8 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 30 | 6 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 4 | 0 | 0 |  | RCC | 8 | 6
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 4 | 0 | 0 |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 18 | 36

## Construction % (3) (hidden)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 2 | 40 | Progress | 10 | 16 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 30 | 12 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 4 | 0 | 0 |  | RCC | 16 | 12
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 4 | 0 | 0 |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 26 | 42