## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-13
Name of the builder group |  |  |  |  | M/s.Shree Construction
Name of the builder company |  |  |  |  | M/s.Shree Construction
Name of the Project |  |  |  |  | Shree Enclave
Contect Details ( Name & Contect No.) |  |  |  |  | 7709545078
Name / No of the Building |  |  |  |  | 1 Building
Docouments Provided |  |  |  |  | Approved Plans, NA order cum CC & Cost Sheet.
RERA No. |  |  |  |  | P99000020704
Project location details |  | Shree Enclave, Survey no.55/1/A, Near little Rock English School, Boisar East, Palghar.
S No. | 55/1/A |  |  | Plot No. |  | NA | Locality | Boisar.
Road | Boisar Road |  |  |  | District | Thane
City | Palghar. |  |  |  | Pin Code | 401501
Near by Landmark |  | Near little Rock English School. |  |  | Distance from city centre: |  | About 1.6 Km from Boisar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Internal road |  | U.C Building |  | little Rock English School |  | Open
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.806916,72.768557
Location Link |  | https://goo.gl/maps/BnFHyiXwQKWPtz9y6?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 1500
Permissible FSI |  |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.75
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 1125
Total number of Buildings |  |  |  |  | 02 Wings
Approval Detail : Plan approval
Layout Approval No |  | MHSUL/KS-1/T-1/NAP/SR/221/18 |  |  |  | Dated | 21/09/2018.
Approved Floor plan No. |  | MHSUL/KS-1/T-1/NAP/SR/221/18 |  |  |  | Dated | 21/09/2018.
NA order cum Commencement Certificate No. |  | MHSUL/KS-1/T-1/NAP/SR-(221/2012)221/18 Valid Upto : Type A = G + 3rd Floor |  |  |  | Dated | 21/09/2018. | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA |  |  | Date of approval: |  | Dated | NA
Commencement date of construction |  |  | 21/09/2018. |  | Expected Completion |  | 30/03/2024.
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 1125 |  | Approved no of units |  |  | 30
Approved no of Floors |  | G + 1st to 3rd Floor |  |  | No of floors at site : See construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | A Wing = G + 1st to 3rd Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 90% |  | 95% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC |  | 4 | 100% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Construction details: |  | B Wing = G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 3 Floor, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor, Flooring upto 3 Floor, Painting upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork upto 3 Floor, Internal Plaster upto 3 Floor, External Plaster upto 3 Floor, Flooring upto 3 Floor, Painting upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 80% |  | 90% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 3 | 75% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 75% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 75% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3600
Society formation charges | [5 empty] | NA
Rate of Parking (Subjected to Authentic Documentation) | [5 empty] | 100000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 2880
Building details Floor Wise
Details of Flats in Building
Flat No. (Sale Plan) | Flat Type | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
A Wing
Ground Floor For Parking.
1st, 2nd & Raised 2nd Floor.
1 | Type B | 1BHK | 369.6896 |  | 0 | 680 | N | 1st, 2nd & Raised 2nd Floor. |  | 2552.9412
2 | Type A | 1BHK | 432.6052 |  | 0 | 750 | N
3 | Type C | 1RK | 224.9676 |  | 0 | 510 | N
4 | Type D | 1BHK | 403.3271 |  | 0 | 725 | N
5 | Type E | 1BHK | 375.7174 |  | 0 | 680 | N
B Wing
Ground Floor For Parking.
1st, 2nd & Raised 2nd Floor.
1 | Type E | 1BHK | 375.7174 |  | 0 | 680 | N | 1st, 2nd & Raised 2nd Floor.
2 | Type D | 1BHK | 403.3271 |  | 0 | 725 | N
3 | Type C | 1RK | 224.9676 |  | 0 | 510 | N |  |  | 3239.2157 | 2196.0784
4 | Type B | 1BHK | 369.6896 |  | 0 | 680 | N
5 | Type A | 1BHK | 432.6052 |  | 0 | 750 | N
Remarks: 1. Work is same as last visit (18/08/2023). Some tenants have occupied the flats. 2. We considered Saleable area as per Builder saleable area. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. Car parking is subjected to authentic documentation. 6. Flat numbering as per Sale Plan. 7. As per RERA, completion period of project Shree Enclave is expired on 30/03/2024 but still project work is pending 8. Since the project has received first CC on 21/09/2018, but still project is under construction. Please provide revised approved CC 9. As checked on RERA portal on dated 19/08/2025, we have observed that above project is kept under abeyance. 10. Construction progress % reduced of wing B because the proposed structure is changed. 11. Please provide revised approved plans and CC. 7. On site, we meet Mr.Amit Singh - 7709545078.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Shree Enclave
Google Map :

## G - C %
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 4 | 100 | Progress |  |  | 10 | 40 | 15 | 6.6667 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 66.6667 | Recommended |  |  | 30 | 30 | 15 | 6.6667 | 0 | 0 | 0
| 3 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 2 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 0 |  | Plaster | 6.6667 | 6.6667
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 71.6667 | 81.6667

## G - C % (2)
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 4 | 66.6667 | Progress |  |  | 10 | 40 | 10 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 10 | 0 | 0 | 0 | 0
| 3 | 2 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 10 | 10
| 3 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 60 | 70

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 4.1 | 11.275 | CB | 2.75 | 0.45 | 1.2375 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.1 | 2.75 | 5.775 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 2.75 | 7.5625 | CB | 0.9 | 2.45 | 2.205 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.85 | 1.2 | 2.22 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.65 | 1.2 | 1.98 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.4 | 1.2 | 1.68 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 328.2213 | 30.4925 |  |  | 37.0551 | 3.4425 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing. | Shree Enclave | 1RK | 0 | 400 | 2800 | 1120000
housing. | Shree Enclave | 1BHK | 0 | 590 | 2800 | 1652000
housing. | Shree Enclave | 1BHK | 0 | 620 | 2800 | 1736000
Average |  |  |  |  | 2800
Valuation Adopted |  |  |  |  | 2800