## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 12/08/2025
CPC Name: |  |  |  |  | Axis Goregoan
Date Of Property Visit |  |  |  |  | 2025-08-12
Name of the builder group |  |  |  |  | M/s.Shree Shiv Shakti Enterprises
Name of the builder company |  |  |  |  | M/s.Shree Shiv Shakti Enterprises
Name of the Project |  |  |  |  | Shiv Shakti Apartment
Name of the Project as per RERA |  |  |  |  | Ideal View
Contact Details ( Name & Contact No.) |  |  |  |  | 2506058585
Name / no of the Building |  |  |  |  | Ideal View - Building No.1 (Wing A & B)
Docouments Provided |  |  |  |  | Approved Layout & NA Order cum CC
RERA No. |  |  |  |  | P99000004618
Project location details |  | Shiv Shakti Apartment, S.No. 198, Umroli, Palghar, Thane 401209.
S No |  | 198 |  |  | Locality |  | Umroli
Road |  | Kolgoan Road |  |  | District |  | Thane
City |  | Palghar |  |  | Pin Code |  | 401209
Near by Landmark |  | City Fire Services |  |  | Distance from city centre: |  | 0.65 Km from Umroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Under construction building |  | Open Plot |  | Building |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.7564828,72.7603612
Location Link |  | https://goo.gl/maps/U53xEPkqgxoCjBhz8?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential + Commercial. (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 5260
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.9
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 4734
Total number of Buildings |  |  |  |  | Wing 02
Approval Detail : Plan approval
Layout Approval No |  | MHSUL/K.1/T.1A/NAP/SR/211/17 |  |  |  | Dated | 18/07/2019.
Building plan approval No |  | MHSUL/K.1/T.1A/NAP/SR/211/17 |  |  |  | Dated | 18/07/2019.
NA Order cum Commencement of Construction |  | MHSUL/K.1/T.1A/NAP/SR/211/17 Valid upto : Buillding No.1 = Type A & Type B = G + 3rd Floor |  |  |  | Dated | 18/07/2019. | Expiry date: One year from date of issue
O. Certificate No.: NA |  |  |  |  | Date of approval: NA | Dated |  | Expiry date: NA
Commencement date of construction |  |  | 18/07/2019. |  | Expected Completion |  | 2024-12-30
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 4734 |  | Approved no of units |  | Shops = 07 & Flats = 27
Approved no of Floors |  | Wing A & B = G + 1st to 3rd Floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Wing A & B = G + 1st to 3rd Floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 93.33% |  | 95% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 4 | 100% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 3 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 66.67% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3300
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 6000
Other charges | [5 empty] | 100000/-
Recommended rate of Parking | [5 empty] | 100000/-
Distressed valuation of the Property | [5 empty] | 2640
Commercial Area Details :
Building & Wing |  | No. of Shop | Total Gross Carpet Area |  |  | Total Saleable Area
A Wing |  | 7 | 848.849 |  |  | 1640
Residential Area Details :
Building & Wing |  | No. of Flats | Total Gross Carpet Area |  |  | Total Saleable Area
A Wing |  | 13 | 5344.1107 |  |  | 8670
B Wing |  | 14 | 5637.4297 |  |  | 9270
Total |  | 27 | 10981.5404 |  |  | 17940 |  |  |  | 11830.3895
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No.1
Wing A (Type A)
Ground Floor
1 |  | Shop | 78.3619 |  | 0 | 150 | N | Ground Floor
2 |  | Shop | 144.7758 |  | 0 | 280 | N
3 |  | Shop | 153.0641 |  | 0 | 300 | N
4 |  | Shop | 96.4454 |  | 0 | 180 | N |  |  | 1.8663
5 |  | Shop | 153.0641 |  | 0 | 300 | N
6 |  | Shop | 144.7758 |  | 0 | 280 | N
7 |  | Shop | 78.3619 |  | 0 | 150 | N
1 |  | 1BHK | 334.0069 |  | 0 | 630 | N
1st, 2nd & 3rd Floor
1 |  | 1BHK | 390.6256 |  | 0 | 630 | N | 1st & 2nd Floor | 1.6128
2 |  | 2BHK | 495.0364 |  | 0 | 820 | N
3 |  | 1BHK | 393.7471 |  | 0 | 600 | N
4 |  | 1BHK | 390.6256 |  | 0 | 630 | N
Wing B (Type B)
Ground Floor For Parking
1 |  | 1BHK | 334.0069 |  | 0 | 630 | N | Ground Floor
2 |  | 1BHK | 325.611 |  | 0 | 600 | N
1st, 2nd & 3rd Floor
1 |  | 1BHK | 390.6256 |  | 0 | 630 | N | 1st,2nd & 3rd Floor
2 |  | 1BHK | 382.9831 |  | 0 | 600 | N
3 |  | 2BHK | 495.0364 |  | 0 | 820 | N
4 |  | 1BHK | 390.6256 |  | 0 | 630 | N
Remarks: 1. Construction work was stopped from visit 13/01/2021. No one found on site. (Lift Installation work is pending). 2. Occupancy of flats is between 70 to 80 percent. Flats in A Wing are occupied by tenents. 3. We considered Saleable area as per Builder area sheet. 4. We considered Carpet area as per Approved Plan. 5. We have considered rate by verifying it from market inquire. 6. We have considered Other charges from cost sheet. 7. We update revised Approved Plan provided to us. (on 22/08/2019) 8. Car parking is subjected to authentic documentation. 9. The project has received CC on 18/07/2019, But construction work is not yet completed. 10. As per RERA, completion period of project is expired on 30/12/2024 but still project is under construction. 11. The project name has been changed from "Shiv Shakti Apartment Ideal City Building No. 1" to "Ideal View" on the RERA portal. Please check before any disbursement 12. As checked on RERA portal on dated 12/08/2025, we have observed that above project "Shiv Shakti Apartment" is kept under abeyance.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  | Shiv Shakti Apartment
Google Map :
Wing B
Wing B
Wing A

## Note
20/10/2020. | Dhanashree | OLD APF
Rate has not Changed

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
housing | Soham Gardens - 290m | 1BHK | 0 | 555 | 2900.9009 | 1610000
housing | Soham Gardens - 290m | 2BHK | 0 | 770 | 2900 | 2233000
Average |  |  | 0 | 0 | 2900.4505
Valuation Adopted |  |  |  |  | 3000

## Construction %
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 4 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 5 | 3.3333
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 5 | 3.3333
| 3 | 3 | 100
plaster | Total Floor | completed Floor | 100
| 3 | 3 | 66.6667
Flooring | Total Floor | completed Floor
| 3 | 3 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 3 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 3 | 2 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 5 | 5
|  |  |  | Finishing | 3.3333 | 3.3333
|  |  |  | total | 93.3333 | 98.3333

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 0 | 3.68 | 0 | CB | 2.7 | 0.9 | 2.43 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.24 | 2.1 | 4.704 | CB |  |  | 0 |  |  | 0
|  | 1.2 | 0.6 | 0.72 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.98 | 2.7 | 8.046 | CB | 2.98 | 0.9 | 2.682 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  | 0 | 0 | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.18 | 2.33 | 5.0794 | DB |  |  | 0 |  |  | 0
| toilet2 | 0 | 0 | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 0 | 0 | 0 |  |  |  | 0 |  |  | 0
| passage2 | 2.5 | 0.9 | 2.25 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 223.8847 | 20.7994 |  |  | 55.0256 | 5.112 |  | 0 | 0
25.9114

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.7 | 3.68 | 9.936 | CB | 2.7 | 0.9 | 2.43 |  |  | 0
|  |  |  | 0 | FB | 2.7 | 0.9 | 2.43 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.84 | 2.7 | 7.668 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.76 | 2.7 | 7.452 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.18 | 2.32 | 5.0576 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 324.1428 | 30.1136 |  |  | 52.313 | 4.86 |  | 0 | 0
34.9736

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0