## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 19/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-13
Name of the builder |  |  |  |  | Mr. Pawan Singh
Name of the builder company |  |  |  |  | M/s.Thakur Housing Development Corporation
Name of the Project (As per Builder) |  |  |  |  | Thakur Nagari Type C
Name of the Project (As per RERA) |  |  |  |  | Thakur Nagari Building No.6
Contact Details ( Name & Contact No.) |  |  |  |  | 7798416508
Name / No of the Building |  |  |  |  | Building No.6 (Type C)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC, Builder Salable Area
RERA No. |  |  |  |  | P99000026873
Project location details |  | Thakur Nagari Type C, Survey No.61/1/4/2, Tarapur-Boisar Road, Pasthal, Boisar, Palghar.
Survey No |  | 61/1/4/2
Road |  | Tarapur-Boisar Road |  |  | Locality/Village |  | Pasthal
City |  | Boisar |  |  | District |  | Palghar
Taluka |  | Palghar |  |  | Pin Code |  | 401501
Near by Landmark |  | Lotus Residency |  |  | Distance from city centre: |  | About 4.3 Km from Boisar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Building |  | Building |  | North |  | Open
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.812128, 72.728778
Location Link |  | https://goo.gl/maps/f67ucPHoHov9QmNd9 |  |  |  | Longitude
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 10100
Permissible FSI |  |  |  |  | 0.9
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.9
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 9090
Total number of Buildings |  |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | G.No.PJP/G.M./PDKRN/568 |  |  |  | Dated | 19/01/2019.
Approved Floor plan No. |  | G.No.PJP/G.M./PDKRN/568 |  |  |  | Dated | 19/01/2019.
Commencement Certificate No. |  | G.No.PJP/G.M./PDKRN/568 Valid Up to: Ground(Pt)+Stilt(Pt)+4th Floor |  |  |  | Dated | 19/01/2019. | Valid upto date: One year from date of issue
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Commencement date of construction |  |  | 19/01/2019. |  | Expected Completion |  | As per RERA=30/06/2027
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 1749.07 |  | Approved no of units |  | Flats = 58
Approved no of Floors |  |  | Ground(Pt)+Stilt(Pt)+4th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Ground(Pt)+ Stilt(Pt) + 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 2 Floor, External Plaster upto 3 Floor, Painting upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 2 Floor, External Plaster upto 3 Floor, Painting upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 70% |  | 86.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 2 | 50% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 1 | 25% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3500
Society Formation Charges | [5 empty] | 150000/-
Development Charges | [5 empty] | 110000/-
Water & Electrician | [5 empty] | 40000/-
One Year Maintenance | [5 empty] | 20000/-
Recommended rate of Parking | [5 empty] | 100000/-
Distressed valuation of the Property | [5 empty] | 2800
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
01 Building |  | 58 | 16563.105 |  |  | 25751
Building details Floor Wise
Details of Flats in Building
Flat No. | Description (As per Builder area sheet) | Description (As per Approved Plan) | Gross Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building No.6 (Type - C)
Ground Floor for Residential & Parking
1 | 1 BHK | 1 RK | 276.4195 |  | 0 | 432 | N | Ground Floor for Residential & Parking |  | 1832000 | 1512000 | 320000
2 | 1 BHK | 1 RK | 274.8049 |  | 0 | 432 | N |  |  | 1832000 | 1512000 | 320000
3 | 2 BHK | 1 BHK | 361.778 |  | 0 | 571 | N |  |  | 2318500 | 1998500 | 320000
4 | 1 BHK | 1 RK | 276.4195 |  | 0 | 432 | N |  |  | 1832000
5 | 1 BHK | 1 RK | 274.8049 |  | 0 | 432 | N |  |  | 1832000
6 | 1 BHK | 1 RK | 276.4195 |  | 0 | 432 | N |  |  | 1832000
1st to 4th Floor
1 | 1 BHK | 1 RK | 274.8049 |  | 0 | 432 | N | 1st to 4th Floor |  | 3472.2222 | 2000000
2 | 1 BHK | 1 RK | 274.8049 |  | 0 | 432 | N |  |  | 3240.7407
3 | 1 BHK | 1 RK | 274.8049 |  | 0 | 432 | N
4 | 1 BHK | 1 RK | 286.5915 |  | 0 | 432 | N |  |  | 3587.963
5 | 1 BHK | 1 RK | 286.5915 |  | 0 | 432 | N
6 | 1 BHK | 1 RK | 274.8049 |  | 0 | 432 | N |  |  |  | 1.572
7 | 2 BHK | 1 BHK | 361.778 |  | 0 | 571 | N |  |  | 2539.4046 | 1.5783 |  | 3152.3643
8 | 1 BHK | 1 RK | 276.4195 |  | 0 | 432 | N
9 | 1 BHK | 1 RK | 274.8049 |  | 0 | 432 | N
10 | 1 BHK | 1 RK | 284.4925 |  | 0 | 432 | N |  |  | 3356.4815
11 | 1 BHK | 1 RK | 284.4925 |  | 0 | 432 | N
12 | 1 BHK | 1 RK | 274.8049 |  | 0 | 432 | N
13 | 1 BHK | 1 RK | 276.4195 |  | 0 | 432 | N |  |  | 3356.4815
Remarks: | [8 empty] | Construction work has just resumed.(Labour Found)
1. Work is same as last visit (08/08/2024). 2. We considered Saleable area as per Builder area sheet. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. In Sale Plan few flats are 1BHK But in Approved Floor Plans those flats are 1RK. Flat are internally converted from 1RK to 1BHK, although area will remain same. 8. The project has received first CC on 19/01/2019, But construction work is not yet completed. 9. As per RERA, completion period of project Thakur Nagari Building No.6 is expired on 30/06/2024 but still project is under construction. | [8 empty] | On site, we meet Mr.Ajit(sales) - 7798416508. |  |  |  |  | Construction work is in process at the time of Visit (labour found) Construction work was not active at the time of Visit. (labour Not found) All work completed. Wait for OC / OC received. Work not yet Started.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnyesh Patil |  | Report Prepared By : |  |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Thakur Nagari Type C
Google Map :
Type C
Type C
Type C

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 0 | 0 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 50% | 60% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
10/10/2020. | Dhanashree | OLD APF
1. Rate has changed
Befor it was = 4250-sq.ft
2021-01-29 | Pratiksha

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
nobroker | Thakur Nagari Type D | 1BHK | 0 | 425 | 3647.0588 | 1550000
proptiger. | Symphony | 1BHK | 314 | 418 | 2892.3445 | 1209000
proptiger. | Symphony | 1BHK | 320 | 464 | 2655.1724 | 1232000
proptiger. | Symphony | 1BHK | 327 | 474.15 | 2655.2779 | 1259000
housing | Symphony | 1BHK | 314 | 455.3 | 2655.392 | 1209000
housing | Symphony | 1BHK | 320 | 464 | 2655.1724 | 1232000
housing | Symphony | 1BHK | 327 | 474.15 | 2655.2779 | 1259000
housing | Symphony | 1BHK | 331 | 479.95 | 2654.4432 | 1274000
housing | Symphony | 1BHK | 333 | 482.85 | 2655.0689 | 1282000
Average |  |  | 0 |  | 2791.6898
Valuation Adopted |  |  |  |  | 2800

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0