## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 20/08/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-13
Name of the builder group |  |  |  | Elite Associates
Name of the builder company |  |  |  | Elite Associates
Name of the Project |  |  |  | The Crown
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Lucas Mascarenhas 8850676929
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Aslam |  |  |  | Mr. Lokesh Shah
Name / No of the Building |  |  |  | Wing A & B
Name / No of the Existing Building |  |  |  | Building No. 113 Tilak Nagar Manivishwa CHS Ltd. | [10 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans & Cost Sheet. | [10 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800048225 |  |  |  | #N/A | [6 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | The Crown, CTS No.36 (Pt), Redevlopement of "Building No. 113 Tilak Nagar Manivishwa CHS Ltd.", near Five Star Housing Society, Shanta Jog Marg, Sarvodaya Maha Buddha Vihar, Chembur, Tilaknagar West, Kurla, Mumbai - 400089. | [12 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 36 (Pt), Redevlopement of "Building No. 113 Tilak Nagar Manivishwa CHS Ltd." | [12 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Sarvodaya Maha Buddha Vihar | [12 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Shanta Jog Marg |  | Locality/Village |  | Chembur | [8 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Tilaknagar West |  | District |  | Mumbai | [8 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kurla |  | Pin Code |  | 400089 | [11 empty] | Mahad | Daund
Nearby Landmark |  | Five Star Housing Society |  | Distance from city centre: |  | 750M from Tilaknagar Railway Station | [11 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [13 empty] | Mangaon | Ambegaon
[18 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [13 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [13 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [13 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Road |  |  | Shanta Jog Marg
West | NA | Other Plot |  |  | Geet Govind CHS
North | NA | Other Plot |  |  | Tilak Nagar Education Society
South | NA | 12.20 M. Wide Road |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.066111,72.894801
Location Link |  | https://maps.app.goo.gl/guYto1gktmzKvPbh6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1256.66
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 3.2485
Total FSI availaible for the project |  |  |  | 6.2485
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7852.23
Total number of Buildings |  |  |  | 02 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority (MHADA)
Layout Approval No |  | Mhada-25/1073/2022 |  |  | Dated | 2022-03-10
Approved Floor plan No. |  | Mhada-25/1073/2022 |  |  | Dated | 2022-03-10
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-25/1073/2025/FCC/2/Amend |  |  | Dated | 2025-05-07
|  | This C.C. Re-endorsed upto top of 15th floor of Wing A & Wing B & further extended upto top of 16th (pt.) floor of wing B (Including LMR/OHT) along with parking tower as per approved Amended plans dtd. 01.04.2025. |  |  | Valid Upto Date | 2025-08-29
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 7852.23
Approved no of units |  |  | Flats - 113, Shops - 11, Offices - 02
Approved no of Floors |  |  | A Wing = Gr + 1st to 15th Floor B Wing = Gr + 1st to 15th Floor
Proposed no of Floors |  |  | A Wing = Gr + 1st to 15th Floor
B Wing = Gr + 1st to 16th Floor
Expected Completion |  |  | As per RERA - 28/04/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gym, Roof top sit out area, Decorative Entrance Lobby, Vitrified Flooring, Granite kitchen platform, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing = Gr + 1st to 15th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 14 Floor, Painting upto 13 Floor, Finishing upto 8 Floor Completed | , Flooring upto 14 Floor, Painting upto 13 Floor, Finishing upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 15 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 14 Floor, Painting upto 13 Floor, Finishing upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.75
Excavation |  | 15 | 100% | 91.33% |  | 94.67% |  | Excavation in process | 7.5
Plinth |  | 15 | 100% |  |  |  |  | Excavation Completed | 15
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3.75
Brickwork | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Footing Completed | 7.5
Internal Plaster | Brickwork & Internal Plaster | 15 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 14 | 93.33% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 13 | 86.67% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 8 | 53.33% |  |  |  |  | Plinth in process | 11.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 15
Construction details: |  | B Wing = Gr + 1st to 16th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 15 Floor, Painting upto 13 Floor, Finishing upto 6 Floor Completed | , Flooring upto 15 Floor, Painting upto 13 Floor, Finishing upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 15 Floor, Painting upto 13 Floor, Finishing upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 90.31% |  | 94.69% |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 17 | 100% |  |  |  |  | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 15 | 93.75% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 13 | 81.25% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 6 | 37.5% |  |  |  |  | Plinth in process | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 16
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 15500
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 28000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 21000
Floor Rise Rate from Floor
Development Charges
Club Charges
Grill Charges |  |  |  |  | 60000
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 30000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 600000
Distressed valuation of the Property |  |  |  |  | 12400
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | Shop | 5 |  | 1321.0657 |  | 2047.6519
Wing B | Shop | 6 |  | 1697.9134 |  | 2631.7657
| Office | 2 |  | 1052.8268 |  | 1631.8816
Total |  | 13 |  | 4071.8059 |  | 6311.2992
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 44 |  | 32043.9544 |  | 48065.9316
Wing B |  | 69 |  | 39010.2634 |  | 58515.3951
Total |  | 113 |  | 71054.2178 |  | 106581.3267
Grand Total |  | 126 |  | 75126.0237 |  | 112892.6259
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
[7 empty] | 55% | 10.764
Wing A
Ground Floor For Commercial, Entrance Lobby, Meter Room, Substation Area & Parking Tower
1 |  | Shop | 302.0378 | 0 | 302.0378 | 0 | 468.1587 | 27.9286
2 |  | Shop | 274.0514 | 0 | 274.0514 | 0 | 424.7797
3 |  | Shop | 182.988 | 0 | 182.988 | 0 | 283.6314
4 |  | Shop | 254.0304 | 0 | 254.0304 | 0 | 393.7471
5 |  | Shop | 307.958 | 0 | 307.958 | 0 | 477.335 | 27.6549
Wing B
Ground Floor For Commercial, Entrance Lobby, Meter Room, Pump Room & Parking Tower
6 |  | Shop | 176.9602 | 0 | 176.9602 | 0 | 274.2882
7 |  | Shop | 176.9602 | 0 | 176.9602 | 0 | 274.2882
8 |  | Shop | 210.9744 | 0 | 210.9744 | 0 | 327.0103
9 |  | Shop | 141.9772 | 0 | 141.9772 | 0 | 220.0646
10 |  | Shop | 371.0351 | 0 | 371.0351 | 0 | 575.1044 | 31.865
11 |  | Shop | 620.0064 | 0 | 620.0064 | 0 | 961.0099 | 55.616
1st Floor For Fitness Centre, Society Office & Commercial
- |  | Society Office & Fitness Centre | [5 empty] | 53.2625
- | [7 empty] | 53.2625
- | [7 empty] | 53.2625
1 |  | Office | 607.6278 | 0 | 607.6278 | 0 | 941.8231 | 53.2625
2 |  | Office | 445.199 | 0 | 445.199 | 0 | 690.0585 | 41.3625
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
[7 empty] | 50% | 10.764
Wing A
1st Floor For Residential | [9 empty] | Given
1 |  | 1BHK | 506.5022 | 59.6207 | 566.1229 | 0 | 849.1843 | 47.0552 | 5.5389 | 54.2 | 52.5941 |  | 746.56 | 1.3187
2 |  | 3BHK | 893.7123 | 70.8594 | 964.5717 | 0 | 1446.8576 | 83.0279 | 6.583 | 92.85 | 89.6109 |  | 1374.95 | 1.4255
3 |  | 2BHK | 513.3492 | 0 | 513.3492 | 0 | 770.0237 | 47.6913 |  | 49.03 |  | 15324.2031 | 793.75 | 1.5462
2nd to 7th & 9th to 15th Floor
1 |  | 2BHK | 656.4576 | 59.6207 | 716.0783 | 0 | 1074.1175 | 60.9864 | 5.5389 | 68.8 |  |  | 900.22
2 |  | 3BHK | 893.7123 | 70.8594 | 964.5717 | 0 | 1446.8576 |  |  | 92.85 |  |  | 1374.95
3 |  | 2BHK | 513.3492 | 0 | 513.3492 | 0 | 770.0237 |  |  | 49.03 |  |  | 793.75
8th Floor (Part Refuge Area)
1 |  | Refuge Area
2 |  | 3BHK | 893.7123 | 70.8594 | 964.5717 | 0 | 1446.8576 |  |  | 92.85 |  | 13823.0605 | 1374.95 | 1.4255
3 |  | 2BHK | 513.3492 | 0 | 513.3492 | 0 | 770.0237 |  |  | 49.03 |  |  | 746.56
Wing B
1st Floor For Fitness Centre, Society Office & Commercial
2nd to 7th & 9th to 15th Floor
1 |  | 2BHK | 564.0863 | 34.6859 | 598.7723 | 0 | 898.1584 | 52.4049 | 3.2224 | 58.2 |  |  | 900.22
2 |  | 1BHK | 416.5948 | 0 | 416.5948 | 0 | 624.8922 | 38.7026 |  | 40.2 |  |  | 603.4
3 |  | 1BHK | 414.5496 | 0 | 414.5496 | 0 | 621.8244 | 38.5126 |  | 40.09 |  |  | 597.82
4 |  | 2BHK | 622.5252 | 42.9807 | 665.5058 | 0 | 998.2587 | 57.834 | 3.993 | 73.62 |  |  | 933.66
5 |  | 3BHK | 712.2883 | 40.9549 | 753.2432 | 0 | 1129.8648 | 66.1732 | 3.8048 | 64.54 |  |  | 966.36
8th Floor (Part Refuge Area)
1 |  | Refuge Area
2 |  | 1BHK | 416.5948 | 0 | 416.5948 | 0 | 624.8922 |  |  | 40.2 |  |  | 433
3 |  | 1BHK | 414.5496 | 0 | 414.5496 | 0 | 621.8244 |  |  | 40.09 |  | 154384.4112 | 429
4 |  | 2BHK | 622.5252 | 42.9807 | 665.5058 | 0 | 998.2587 |  |  | 73.62 |  | 18432.095
5 |  | 1BHK | 440.0043 | 40.9549 | 480.9592 | 0 | 721.4388 | 40.8774 | 3.8048 | 46.77 |  | 14970.0848 | 480
Remarks:
* | Construction work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | The validity of provided C.C. is expired on 29/08/2023. Please provide revised aprroved C.C.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned on approved layout plan & floor plan.
* | We have updated latest CC (On 15/05/2025).
* | Please provide revised approved floor plans.
Undertaking : | [7 empty] | Since Project's Builtup Area is above 20000 Sq.M. Please check for Environment Clearance Certificate.
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | The Crown
Layout :
Google Map :
Formulas:
Chembur = [Chembur, row above]
Wing B
A
Wing A
Wing A
Wing B
Wing B
B
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC