## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 14/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-12
Name of the builder |  |  |  |  | Mr.Kush Ramsingar Vishwakarma
Name of the builder company |  |  |  |  | M/s.Yash Enterprises
Name of the Project |  |  |  |  | Yash Apartment
Contect Details ( Name & Contect No.) |  |  |  |  | 9930621882
Name / no of the Building |  |  |  |  | Yash Apartment/1 Buildings (3 Wings)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, NA Order cum CC
Rera No. |  |  |  |  | P99000017533
Project location details |  | Yash Apartment, G.no. 140 & 156 at Village-Padghe, Palghar.
Plot No | NA |  |  | Gut . No. |  | 140 & 156 | Locality | Padghe
Road | Station Road |  |  |  | District | Palghar
City | Palghar |  |  |  | Pin Code | 401501
Near by Landmark |  | Sarpada Genesis MIDC |  |  | Distance from city centre: |  | About 180 m from Umroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 3 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Plot |  | Main Road |  | Building |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC
Latitude & Longitude |  | 19.757378,72.759201
Locatin Link |  | https://goo.gl/maps/vDbNS3ossxTDgseA9?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential + Commercial (Restrictive Covenants in regard to Land Use, if any) : No
Total land area of the project in Sq. Mt. |  |  |  |  | 10960
Permissible FSI |  |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.75
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 8220
Total number of Buildings |  |  |  |  | 3 Wings
Approval Detail : Plan approval
Layout Approval No |  | BS/SD/BP/PADAGHE/PALGHAR/G.NO.740&156/NR/592 |  |  |  | Dated | 06/06/2014.
Building plan approval No |  | BS/SD/BP/PADAGHE/PALGHAR/G.NO.740&156/NR/592 |  |  |  | Dated | 06/06/2014.
NA Order cum Commencement of Construction |  | MHSUL/KS.1/T.1/NAP/SR-113/2014 Valid Up to: G + 1st to 3rd Floor (All Wings) |  |  |  | Dated | 30/07/2014.
O. Certificate No.: NA |  |  |  |  | Date of approval: NA |  |  | Expiry date: NA
Commencement date of construction |  |  | 30/07/2014. |  | Expected Completion |  | 2025-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 8220 |  | Approved no of units |  | Shops = 14 Flats = 50
Approved no of Floors |  | G + 1st to 3rd Floor (All Wings)
Quality of construction: Good |  |  |  |  | Projected life : 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | Wing A = G + 1st to 3rd Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 2 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 30% |  | 60% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 2 | 50% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Construction details: |  | Wing B = G + 1st to 3rd Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 3 Slab, Brickwork upto 1 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab, Brickwork upto 1 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 42.5% |  | 69.17% |  | Excavation in process | 1.5
Plinth |  | 3 | 100% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 3 | 75% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 1 | 33.33% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Construction details: |  | Wing C = G + 1st to 3rd Floor | [6 empty] | Excavation work Completed. Footing work Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 3
Stage of construction: |  | Excavation work Completed. Footing work Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 0.75
Excavation |  | 3 | 100% |  | 5% |  | 32.5% |  | Excavation in process | 1.5
Plinth |  | 1.5 | 50% | [5 empty] | Excavation Completed | 3
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 0.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 1.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 2.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 3
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleble area) | [5 empty] | 3300
Recommended rate of the Shop Per Sq. Ft. ( on Saleble area) | [5 empty] | 6000
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Any Other amenities | [5 empty] | NA
Society formation charges | [5 empty] | 65000/-
Recommended rate of Parking | [5 empty] | NA
Development charges Per Sq. Ft. | [5 empty] | NA
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 2640
Building details Floor Wise
Details of Flats in Building
Wings | Flat No. | Description | Carpet area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Ground Floor For Parking & Commercial
A | 1 | Shop | 121.5 |  | 0 | 240 | NA | Ground
A | 2 | Shop | 161.88 |  | 0 | 301 | NA | Ground
A | 3 | Shop | 122.5 |  | 0 | 230 | NA | Ground
A | 4 | Shop | 179.38 |  | 0 | 333 | NA | Ground
A | 5 | Shop | 153.13 |  | 0 | 285 | NA | Ground
A | 6 | Shop | 122.5 |  | 0 | 230 | NA | Ground
A | 7 | Shop | 148.75 |  | 0 | 280 | NA | Ground
B | 8 | Shop | 148.75 |  | 0 | 280 | NA | Ground
B | 9 | Shop | 122.5 |  | 0 | 230 | NA | Ground
B | 10 | Shop | 153.13 |  | 0 | 285 | NA | Ground
B | 11 | Shop | 179.38 |  | 0 | 333 | NA | Ground
B | 12 | Shop | 122.5 |  | 0 | 230 | NA | Ground
B | 13 | Shop | 161.88 |  | 0 | 301 | NA | Ground
B | 14 | Shop | 121.5 |  | 0 | 240 | NA | Ground
1st Floor
A | 1 | 1 BHK | 323.03 |  | 0 | 560 | NA | 1st
A | 2 | 1 BHK | 261.24 |  | 0 | 460 | NA | 1st
A | 3 | 1 BHK | 261.24 |  | 0 | 460 | NA | 1st
A | 4 | 1 BHK | 295.47 |  | 0 | 596 | NA | 1st
A | 5 | 1 BHK | 295.47 |  | 0 | 690 | NA | 1st
A | 6 | 1 BHK | 312.8 |  | 0 | 710 | NA | 1st
2nd Floor
A | 1 | 1 BHK | 323.03 |  | 0 | 560 | NA | 2nd
A | 2 | 1 BHK | 261.24 |  | 0 | 460 | NA | 2nd
A | 3 | 1 BHK | 261.24 |  | 0 | 460 | NA | 2nd
A | 4 | 1 BHK | 295.47 |  | 0 | 520 | NA | 2nd
A | 5 | 1 BHK | 295.47 |  | 0 | 596 | NA | 2nd
A | 6 | 1 BHK | 312.8 |  | 0 | 550 | NA | 2nd
3rd Floor
A | 1 | 1 BHK | 323.03 |  | 0 | 560 | NA | 3rd
A | 2 | 1 BHK | 261.24 |  | 0 | 490 | NA | 3rd
A | 3 | 1 BHK | 261.24 |  | 0 | 490 | NA | 3rd
A | 4 | 1 BHK | 295.47 |  | 0 | 520 | NA | 3rd
1st Floor
B | 1 | 1 BHK | 312.8 |  | 0 | 525 | NA | 1st
B | 2 | 1 BHK | 295.47 |  | 0 | 596 | NA | 1st
B | 3 | 1 BHK | 295.47 |  | 0 | 596 | NA | 1st
B | 4 | 1 BHK | 261.24 |  | 0 | 438 | NA | 1st
B | 5 | 1 BHK | 261.24 |  | 0 | 460 | NA | 1st
B | 6 | 1 BHK | 323.03 |  | 0 | 560 | NA | 1st
2nd Floor
B | 1 | 1 BHK | 312.8 |  | 0 | 525 | NA | 2nd
B | 2 | 1 BHK | 295.47 |  | 0 | 596 | NA | 2nd
B | 3 | 1 BHK | 295.47 |  | 0 | 520 | NA | 2nd
B | 4 | 1 BHK | 261.24 |  | 0 | 460 | NA | 2nd
B | 5 | 1 BHK | 261.24 |  | 0 | 460 | NA | 2nd
B | 6 | 1 BHK | 323.03 |  | 0 | 542 | NA | 2nd
3rd Floor
B | 3 | 1 BHK | 295.47 |  | 0 | 596 | NA | 3rd
B | 4 | 1 BHK | 261.24 |  | 0 | 438 | NA | 3rd
B | 5 | 1 BHK | 261.24 |  | 0 | 438 | NA | 3rd
B | 6 | 1 BHK | 323.03 |  | 0 | 542 | NA | 3rd
1st Floor
C | 1 | 1 BHK | 312.8 |  | 0 | 525 | NA | 1st
C | 2 | 1 BHK | 305.16 |  | 0 | 520 | NA | 1st
C | 3 | 1 BHK | 228.84 |  | 0 | 385 | NA | 1st
C | 4 | 1 BHK | 272.44 |  | 0 | 460 | NA | 1st
C | 5 | 2 BHK | 474.69 |  | 0 | 800 | NA | 1st
C | 6 | 2 BHK | 370.82 |  | 0 | 625 | NA | 1st
2nd Floor
C | 1 | 1 BHK | 348 |  | 0 | 585 | NA | 2nd
C | 2 | 1 BHK | 305.16 |  | 0 | 520 | NA | 2nd
C | 3 | 1 BHK | 228.84 |  | 0 | 385 | NA | 2nd
C | 4 | 1 BHK | 305.16 |  | 0 | 520 | NA | 2nd
C | 5 | 2 BHK | 474.69 |  | 0 | 800 | NA | 2nd
C | 6 | 2 BHK | 370.82 |  | 0 | 625 | NA | 2nd
3rd Floor
C | 1 | 1 BHK | 312.8 |  | 0 | 525 | NA | 3rd
C | 2 | 1 BHK | 272.44 |  | 0 | 460 | NA | 3rd
C | 3 | 1 BHK | 228.84 |  | 0 | 385 | NA | 3rd
C | 4 | 1 BHK | 305.16 |  | 0 | 520 | NA | 3rd
C | 5 | 2 BHK | 474.69 |  | 0 | 800 | NA | 3rd
C | 6 | 2 BHK | 370.82 |  | 0 | 625 | NA | 3rd
Remarks: 1. Wing A = Construction work is same as last visit. (11/08/2022). The construction work was stopped. Wing B & C = Work same as visit (19/05/2021). 2. We have considered rate by verifying it from market inquire. 3. We have considered Other charges from cost sheet. 4. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 5. We adopted builder saleable area as per builder saleable area chart 6. We have updated NA order & Revised Plan date. 7. As building have received CC on 30/07/2014, still project work is pending.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Yash Apartment
Google Map :
Wing A
Wing A

## A%
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 25 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 1 | 0 | Progress |  |  | 10 | 10 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 7.5 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 3 | 0 |  | RCC | 10 | 7.5
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 3 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 20 | 37.5

## B%
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 3 | 75 | Progress | 10 | 30 | 5 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 30 | 22.5 | 5 | 0 | 0 | 0 | 0
| 3 | 1 | 33.3333
plaster | Total Floor | completed Floor
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 3 | 0 | 0 |  | RCC | 30 | 22.5
Finishing | Total Floor | completed Floor |  |  | Bricks | 5 | 5
| 3 | 0 | 0 |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 45 | 57.5

## C%
Particulars | totaL floor | 3
| total | completed
plinth | 10 | 5 | 50
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 4 | 0 | 0 | Progress | 5 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 25 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | 0
plaster | Total Floor | completed Floor
| 3 | 0 | 0
Flooring | Total Floor | completed Floor
| 3 | 0 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 5 | 25
| 3 | 0 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 3 | 0 | 0 |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 5 | 25

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Yash Apartment | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted