## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 12/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-12
Name of the builder group |  |  |  |  | M/s.Patil Builders
Name of the builder company |  |  |  |  | M/s.Patil Builders
Name of the Project |  |  |  |  | Vrindavan Complex Phase II & III
Contact Details ( Name & Contact No.) |  |  |  |  | 8888805000/7021577921
Site Person - Contact Details (Name & Contact No.) |  |  |  |  | Mr. Ravindra Patel 7021579421
Name / No of the Building |  |  |  |  | Phase II |  | Building No.1 Building No.4 Building No.5 (A & B Wings)
[5 empty] | Phase III |  | Building Type A (Wing A & B) Building Type B
Docouments Provided |  |  |  |  | Approved Plan, CC & Cost Sheet
RERA Name & No. |  |  |  |  | Vrindavan Complex Phase II (P99000018246) |  | Building No.1 (Type A) Building No.4 (Type C) Building No.5 (Type D)
[5 empty] | Vrindavan Complex Phase III (P99000054219) |  | Building No.A (Wing A & B) Building No.B
Project location details |  | Vrindavan Complex Phase II & III, S. No.321, 322/2, 322/3 (New S.No.322/B/K/D/E/E/F), Shirdhankar Ln Road, Saphale, Palghar.
S. No |  | 321, 322/2, 322/3 (New S.No.322/B/K/D/E/E/F)
Road |  | Shirdhankar Ln Road |  |  | Village |  | Saphale
City |  | Saphale East |  |  | District |  | Palghar
Taluka |  | Palghar |  |  | Pin Code |  | 401102
Near by Landmark |  | Kurlai Temple |  |  | Distance from city centre: |  | 1.5 Km from Saphale Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per Layout |  | Other Plot |  | Existing Road |  | Other Plot |  | Existing Road
At site |  | Open Plot |  | Internal Road |  | Open Plot |  | Shirdhankar Ln Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.575295,72.832045
Location Link |  | https://maps.app.goo.gl/yPVo2LRWibRdiyfy8
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Vrindavan Complex Phase II
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 4861.85
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0.19089
Total FSI availaible for the project |  |  |  |  | 1.1909
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 5789.94
Total number of Buildings |  |  |  |  | 04 Wings
Vrindavan Complex Phase III
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 4485.38
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0.59947
Total FSI availaible for the project |  |  |  |  | 1.5995
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 7174.24
Total number of Buildings |  |  |  |  | 07 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Zilla Parishad, Palghar
Layout Approval No. (Phase II) |  | MHSL/K-1/MJ1/VSP/S.R/359/97 |  |  |  | Dated | 25/05/2018.
Approved Floor plan No. (Phase II) |  | MHSL/K-1/MJ1/VSP/S.R/359/97 |  |  |  | Dated | 25/05/2018.
Commencement Certificate No. (Phase II) |  | MHSL/KS.1/T.1/ANAP/ASAR-359/2017 |  |  |  | Dated | 25/05/2018.
Valid Up to: Building No.1 - Type A = G + 1st to 4th Floor Building No.4 - Type C = G + 1st to 4th Floor Building No.5 - Type D = G + 1st to 4th Floor
Layout Approval No. (Phase III) |  | PJP/GP/PD/346 |  |  |  | Dated | 21/10/2022.
Approved Floor plan No. (Phase III) |  | PJP/GP/PD/346 |  |  |  | Dated | 21/10/2022.
Commencement Certificate No. (Phase III) |  | PJP/GP/PDKRN/346 |  |  |  | Dated | 21/10/2022.
Valid Up to: Building No.A = Gr + 1st to 7th Floor Building No.B = Gr + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : |  |  | Date of approval: | Dated | NA | NA
Phase II | Commencement date of construction |  |  | 25/05/2018. |  | Expected Completion |  | Completed
Phase III |  |  |  | 21/10/2022. |  |  |  | 31/12/2028
Building wise Construction details
Approved area of the building in Sq.Mt (Phase II) |  |  | 5789.94 |  | Approved no of units |  | Phase II | Flat =86 & shop =14
Approved area of the building in Sq.Mt (Phase III) Building Type A & B |  |  | 6069 |  |  |  | Phase III | Flat = 101
Approved no of Floors |  | Phase II | Building No.1 - Type A = G + 1st to 4th Floor Building No.4 - Type C = G + 1st to 4th Floor Building No.5 - Type D (A & B Wings) = G + 1st to 4th Floor
|  | Phase III | Building Type A (Wing A & B) = Gr + 1st to 7th Floor
Building Type B = Gr + 1st to 7th Floor
Proposed no of Floors |  | Phase II | Building No.1 - Type A = G + 1st to 4th Floor Building No.4 - Type C = G + 1st to 4th Floor Building No.5 - Type D (A & B Wings) = G + 1st to 4th Floor
|  | Phase III | Building Type A (Wing A & B) = Gr + 1st to 7th Floor
Building Type B = Gr + 1st to 7th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years
Material laying at Site: Cement, Aggregate,Steel etc. | [8 empty] | Under Construction
Construction details: |  | Building No.1 - Type A = G + 1st to 4th Floor Building No.5 - Type D (A & B Wings) = G + 1st to 4th Floor Building No.4 - Type C = G + 1st to 4th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100% |  | Piling Work in process | 1
[9 empty] | Excavation in process | 2
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Excavation Completed | 4
Excavation |  | 4 | 100% |  | 100% |  | 100% |  | Footing in Process | 1
Plinth |  | 4 | 100% | [5 empty] | Footing Completed | 2
RCC |  | 5 | 100% | [5 empty] | Basement 1 | 0
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 2 | 0
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 3 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 4 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Plinth in process | 3
Painting & Wooden |  | 4 | 100% | [5 empty] | Plinth completed | 4
Building Common Amenities | Building Common Amenities | 4 | 100%
Possession |  | 4 | 100%
Construction details: |  | Building Type A (Wing A) = Gr + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 6 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 6 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 72.5% |  | 88.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type A (Wing B) = Gr + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 5 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 6 Floor, External Plaster upto 5 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 71.07% |  | 87.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Construction details: |  | Building Type B = Gr + 1st to 7th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 25% |  | 56.25% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC |  | 3 | 37.5% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan : Yes
Violations Observed if any : NA
Proposed Amenities : |  | Compound Wall, Rain Water Harvesting System, Open Space, Community Building, Internal Road, Lift, Parking etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3650
Recommended rate of the Office Per Sq. Ft. ( on Saleable area) | [5 empty] | 5000
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Any Other amenities | [5 empty] | NA
Society formation charges | [5 empty] | 50000/- |  |  | 3200 to 3550 | 2023-07-06 | Gaurav | cost sheet
Recommended rate of Parking | [5 empty] | 150000/- |  |  | 3550 to 3650 | 2024-03-29 | Trupti | verbal
Development charges | [5 empty] | 100000/-
Distressed valuation of the Property | [5 empty] | 2920
Phase II | [9 empty] | `
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Building No.1 |  | 7 | 1302.0967 |  |  | 1888.0402
Building No.4 |  | 7 | 796.4284 |  |  | 1154.8211
Total |  | 14 | 2098.525 |  |  | 3042.8613
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Building No.1 |  | 25 | 13892.449 |  |  | 20872.128
Building No.4 |  | 25 | 9433.139 |  |  | 13715.0798
Building No.5 |  | 36 | 13401.5029 |  |  | 19432.1792
Total |  | 86 | 36727.0909 |  |  | 54019.387
Grand Total |  | 100 | 38825.616 |  |  | 57062.2483
Phase III
Residential Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Building Type A | Wing A | 28 | 15303.9323 |  |  | 22190.7018
| Wing B | 28 | 15251.9422 |  |  | 22115.3161
Building Type B |  | 45 | 22408.3876 |  |  | 32492.162
Total |  | 101 | 52964.262 |  |  | 76798.1799
Building details Floor Wise
Details of Residential & Commercial in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Phase II
Building No.1 (Type A)
Ground Floor for Commercial, Residential, Parking
1 |  | Office | 177.5816 |  | 0 | 257.4933 | N | Ground Floor for Commercial, Residential, Parking
2 |  | Office | 169.4254 |  | 0 | 245.6668 | N
3 |  | Office | 213.6654 |  | 0 | 309.8148 | N
4 |  | Office | 191.9221 |  | 0 | 278.2871 | N
5 |  | Office | 224.2141 |  | 0 | 325.1105 | N
6 |  | Office | 157.0468 |  | 0 | 227.7178 | N
7 |  | Office | 168.2413 |  | 0 | 243.9499 | N
8 |  | 1BHK | 335.8368 |  | 0 | 486.9634 | N
1st & 3rd Floor
1 |  | 1BHK | 481.7966 |  | 0 | 698.6051 | N | 1st & 3rd Floor
2 |  | 1BHK | 475.6612 |  | 0 | 689.7087 | N
3 |  | 1BHK | 453.0568 |  | 0 | 656.9323 | N
4 |  | 2BHK | 555.853 |  | 50.1602 | 856.147 | N
5 |  | 2BHK | 742.6084 |  | 0 | 1076.7821 | N
6 |  | 2BHK | 715.6984 |  | 45.3164 | 1083.0791 | N
2nd & 4th Floor
1 |  | 1BHK | 457.7929 |  | 42.4102 | 706.2099 | N | 2nd & 4th Floor
2 |  | 1BHK | 451.6574 |  | 42.4102 | 697.3134 | N
3 |  | 1BHK | 427.0079 |  | 45.6394 | 664.8008 | N
4 |  | 2BHK | 557.3599 |  | 87.8342 | 896.0061 | N
5 |  | 2BHK | 742.6084 |  | 0 | 1076.7821 | N
6 |  | 2BHK | 717.2053 |  | 50.2679 | 1090.2156 | N
Building No.4 (Type C)
Ground Floor for Commercial, Residential, Parking
1 |  | Office | 108.5011 |  | 0 | 157.3266 | N | Ground Floor for Commercial, Residential, Parking
2 |  | Office | 94.9385 |  | 0 | 137.6608 | N
3 |  | Office | 145.0987 |  | 0 | 210.3931 | N
4 |  | Office | 145.0987 |  | 0 | 210.3931 | N
5 |  | Office | 92.7857 |  | 0 | 134.5392 | N
6 |  | Office | 106.7789 |  | 0 | 154.8294 | N
7 |  | Office | 103.2268 |  | 0 | 149.6788 | N
8 |  | 1BHK | 353.0592 |  | 0 | 511.9358 | N
1st Floor
1 |  | 1BHK | 359.3023 |  | 0 | 520.9884 | N | 1st Floor
2 |  | 1BHK | 360.3787 |  | 0 | 522.5491 | N
3 |  | 1BHK | 353.0592 |  | 0 | 511.9358 | N
4 |  | 2BHK | 477.5987 |  | 18.5141 | 711.0322 | N
5 |  | 1BHK | 360.3787 |  | 18.5141 | 541.0632 | N
6 |  | 1BHK | 359.3023 |  | 0 | 520.9884 | N
2nd to 4th Floor
1 |  | 1BHK | 359.3023 |  | 0 | 520.9884 | N | 2nd to 4th Floor
2 |  | 1BHK | 360.3787 |  | 0 | 522.5491 | N
3 |  | 1BHK | 353.0592 |  | 0 | 511.9358 | N
4 |  | 2BHK | 477.5987 |  | 0 | 692.5181 | N
5 |  | 1BHK | 360.3787 |  | 0 | 522.5491 | N
6 |  | 1BHK | 359.3023 |  | 0 | 520.9884 | N
Building No.5 (Type D)
A Wing | [10 empty] | o | fb
Ground Floor for Residential, Parking | [10 empty] | 6.4125 | 1.725 | 8.1375 | 64.24
1 |  | 1BHK | 352.0904 |  | 0 | 510.5311 | N | Ground Floor |  |  | 2.175 | 6.075
2 |  | 1BHK | 351.2293 |  | 0 | 509.2825 | N
1st to 4th Floor
1 |  | 1BHK | 359.5176 |  | 0 | 521.3005 | N | 1st to 4th Floor
2 |  | 2BHK | 437.449 |  | 0 | 634.301 | N
3 |  | 1BHK | 351.2293 |  | 0 | 509.2825 | N
4 |  | 1BHK | 351.2293 |  | 0 | 509.2825 | N
B Wing
Ground Floor for Residential, Parking
1 |  | 1BHK | 351.1217 |  | 0 | 509.1264 | N | Ground Floor
2 |  | 1BHK | 352.0904 |  | 0 | 510.5311 | N |  | 10.764
1st to 4th Floor
1 |  | 1BHK | 351.2293 |  | 0 | 509.2825 | N | 1st to 4th Floor |  | e
2 |  | 1BHK | 351.2293 |  | 0 | 509.2825 | N |  | 54.4525 | 57.3
3 |  | 2BHK | 437.449 |  | 0 | 634.301 | N |  | 47.0575 | 50.09
4 |  | 1BHK | 359.41 |  | 0 | 521.1444 | N
Phase III
Building Type A
Wing A
Ground Floor For Entrance Lobby & Parking
1st to 7th Floor For Residential
1 |  | 3BHK | 691.4794 |  | 0 | 1002.6451 | N | 1st to 7th Floor For Residential
2 |  | 2BHK | 613.8709 |  | 0 | 890.1128 | N
3 |  | 1BHK | 440.4629 |  | 0 | 638.6712 | N
4 |  | 1BHK | 440.4629 |  | 0 | 638.6712 | N
Wing B
Ground Floor For Entrance Lobby, Society Office, Driver Room & Parking | [8 empty] | 99.4055 | 86.4618
1st to 7th Floor For Residential
1 |  | 2BHK | 532.818 |  | 0 | 772.5861 | N | 1st to 7th Floor For Residential
2 |  | 1BHK | 440.4629 |  | 0 | 638.6712 | N
3 |  | 2BHK | 602.784 |  | 0 | 874.0368 | N
4 |  | 2BHK | 602.784 |  | 0 | 874.0368 | N
Building Type B
Ground Floor For Residential & Parking
1 |  | 2BHK | 577.058 |  | 0 | 836.7342 | N | Ground Floor For Residential & Parking
2 |  | 2BHK | 500.7413 |  | 0 | 726.0749 | N
3 |  | 1RK | 267.0548 |  | 0 | 387.2295 | N
1st to 7th Floor For Residential
1 |  | 2BHK | 602.784 |  | 0 | 874.0368 | N | 1st to 7th Floor For Residential
2 |  | 2BHK | 602.784 |  | 0 | 874.0368 | N
3 |  | 2BHK | 550.3633 |  | 0 | 798.0268 | N
4 |  | 1BHK | 446.706 |  | 0 | 647.7237 | N
5 |  | 1BHK | 372.542 |  | 0 | 540.186 | N
6 |  | 1BHK | 433.8968 |  | 0 | 629.1504 | N
Remarks:
1 .Bldg no.1, 4 & 5 (A & B Wing) = All work completed. Please provide OC. Building Type A (Wing A) = Construction work is in process at the time of Visit (Slow Speed). Building Type A (Wing B) & Type B = Construction work is in process at the time of Visit. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + Open Balcony + F.B Area 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Recommended Rates / Other charges of the Property have been revised on 29/03/2024. 8. We have updated Phase III revised approved floor plan & C.C (on 13/04/2024).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Yadnesh Patil |  | Report Prepared By : |  |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Vrindavan Complex Phase II & III
Layout :
Google Map :
Bldg No. 1
Building Type A
Building Type B
Vrindavan Complex Phase III
Building No.4
Building No.5
Building No.1
Vrindavan Complex Phase II
Building No.2
Building No.3
Vrindavan Complex Phase I
Building Type C
Bldg Type A (A wing)
Phase III : Bldg Type A (A wing)
Phase III : Bldg Type A (B wing)
Phase III : Bldg Type B
Phase III : Bldg Type B
Type A (A wing )
Type A (Bwing )
Type B

## 1%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 2 | 50% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 5 | 0 | 0 | 0
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 5 | 0 | 0 | 0
Bricks | 15 | 15
Plaster | 5 | 5
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 70% | 80% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 4%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 2 | 40% |  | Parking |  | Rate
Bricks | 4 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 4 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 4 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 16 | 0 | 0 | 0 | 0 | 0
RCC | 16 | 12 |  | Recommended |  | 30 | 12 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 26% | 42% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## 5%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 4
Particulars | total floor | 4
plinth | 10 | 10 | 100%
slab | 5 | 5 | 100% |  | Parking |  | Rate
Bricks | 4 | 4 | 100% |  | Palghar |  | 100000/-
plaster | 4 | 4 | 100% |  | Ulwe, karanjade |  | 200000/-
Flooring | 4 | 4 | 100% |  | Panvel |  | 300000/-
Wood & painting | 4 | 4 | 100% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 4 | 1 | 25% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 40 | 15 | 10 | 10 | 5 | 1.25
RCC | 40 | 30 |  | Recommended |  | 30 | 30 | 15 | 10 | 5 | 5 | 1.25
Bricks | 15 | 15
Plaster | 10 | 10
Flooring | 10 | 5
Wood & painting | 5 | 5
Finishing | 1.25 | 1.25
total | 91.25% | 96.25% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
2020-10-19 | Pratiksha
2021-01-05 | Pratiksha

## Valuation
2020-10-17 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Magic Brick | [5 empty] | 55800000
| Magic Brick | [5 empty] | 120000000
| Magic Brick | [5 empty] | 76300000
| Magic Brick | [5 empty] | 118500000
| Magic Brick | [5 empty] | 139000000
| 99 Acres | [5 empty] | 77400000
| 99 Acres | [5 empty] | 86300000
| Average |  |  |  |  | #DIV/0!
| Valuation Adopted |  |  |  |  | 32000

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0