## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 20/08/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | Metro Enterprises
Name of the builder company |  |  |  | Metro Enterprises
Name of the Project |  |  |  | Metro Crown
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Ritesh Dargar 9769225559
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Mitesh patil
Name / No of the Building |  |  |  | 1 Building
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | Metro Crown (Residential) - P51800047023 Metro Crown (Commercial) - P51800046960
Project location details |  | Metro Crown, CTS No.43, near UHDE House, LBS Road, Surya Nagar, Hariyali, Vikhroli (West), Kurla, Mumbai - 400083.
CTS No |  | 43
Locality |  | Surya Nagar
Road |  | LBS Road |  | Locality/Village |  | Hariyali
City |  | Vikhroli (West) |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400083
Nearby Landmark |  | UHDE House |  | Distance from city centre: |  | 0.350KM from Vikhroli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane | [5 empty] | 17151300
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | LBS Road
West | NA | NA |  |  | Godrej RMC Plant
North | NA | NA |  |  | Uhde House
South | NA | NA |  |  | VEGA Guest House
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.11113504, 72.9252482
Location Link |  | https://goo.gl/maps/tbUS4MtBS7VLfguk7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 7202.8
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 0.87621
Total FSI availaible for the project |  |  |  | 3.8762
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 27919.54
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority (SRA)
Layout Approval No |  | S/PVT/0175/20210803/AP/C |  |  | Dated | 2022-12-22
Approved Floor plan No. |  | S/PVT/0175/20210803/AP/C |  |  | Dated | 2022-12-22
Commencement-CC No Valid Up to: |  | S/PVT/0175/20210803/AP/C |  |  | Dated | 2022-10-21
This C.C is further extended from ground + 1st to 17th upper floor of composite building as per last approved amended plans dated 13/10/2022.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 27919.54
Approved no of units |  |  | Flats - 73, Shops - 3, Offices - 6
Approved no of Floors |  |  | B + G + 1st to 20th Floor
Proposed no of Floors |  |  | B + G + 1st to 22nd Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Fitness Center, Car Parking Tower, Amenity Area
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | B + G + 1st to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 21 Floor, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor, Flooring upto 6 Floor, Painting upto 2 Floor, Finishing upto 2 Floor Completed | , Brickwork upto 21 Floor, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor, Flooring upto 6 Floor, Painting upto 2 Floor, Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 21 Floor, Internal Plaster upto 15 Floor, External Plaster upto 15 Floor, Flooring upto 6 Floor, Painting upto 2 Floor, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 72.73% |  | 87.95% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 21 | 95.45% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 15 | 68.18% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 68.18% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 6 | 27.27% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 2 | 9.091% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 9.091% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | #REF! | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | 20 | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | 0 | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | #REF! | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | #REF! | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | #REF! | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 15600 |  |  | 15000 to 1600 | sanket | 2023-11-09 | by verbal
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 35000 |  |  |  | 14838.7097 | 14322.9167
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 25000 |  |  |  |  | 13937.2822
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges |  |  |  |  | 11
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1000000
Distressed valuation of the Property |  |  |  |  | 12480 |  |  |  | MIS
Commercial Area Details : | [8 empty] | 4421 - Blumen | 17600 | 60%, 50%
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 3 |  | 2072.7158 |  | 3316.3453
Offices |  | 6 |  | 4456.5113 |  | 7130.418
Total |  | 9 |  | 6529.2271 |  | 10446.7634
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 73 |  | 32971.2084 |  | 51105.373
Total |  | 73 |  | 32971.2084 |  | 51105.373
Grand Total |  | 82 |  | 39500.4355 |  | 61552.1364
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Basement Floor For Domestic Tank, Flushing Tank, Fire Tank & Pump Room
Ground Floor For Commercial, Meter Room & Parking | [8 empty] | 10.764
1 |  | Shop | 793.845 | 0 | 1270.152 | Ground Floor For Commercial, Meter Room & Parking
2 |  | Shop | 733.2437 | 0 | 1173.1899 |  |  |  | 68.9384
3 |  | Shop | 545.6272 | 0 | 873.0035
1st Floor For Commercial & Parking
1 |  | Office | 684.1598 | 0 | 1094.6557 | 1st Floor For Commercial & Parking
2 |  | Office | 781.7893 | 0 | 1250.8629 | 1st Floor For Commercial & Parking
3 |  | Office | 762.3065 | 0 | 1219.6904 | 1st Floor For Commercial & Parking
2nd Floor For Commercial & Parking
1 |  | Office | 684.1598 | 0 | 1094.6557 | 2nd Floor For Commercial & Parking
2 |  | Office | 781.7893 | 0 | 1250.8629 | 2nd Floor For Commercial & Parking
3 |  | Office | 762.3065 | 0 | 1219.6904 | 2nd Floor For Commercial & Parking
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
3rd Floor For Service
4th to 7th, 9th to 14th Floor For Residential & Parking
1 |  | 1 | 371.5733 | 0 | 575.9386 | 4th to 7th, 9th to 14th Floor For Residential & Parking |  |  | 33.1594 | 46.2391
2 |  | 2 | 555.6377 | 0 | 861.2384 |  |  |  | 2.2875 | 5.451
3 |  | 2 | 555.6377 | 0 | 861.2384 |  |  |  | 35.4469 | 51.6901
4 |  | 1 | 371.5733 | 0 | 575.9386
8th Floor (Part Refuge Area)
1 |  | 1 | 371.5733 | 0 | 575.9386 | 8th Floor (Part Refuge Area) |  |  | 14237.6292 | 19099.2587
2 |  | 2 | 555.6377 | 0 | 861.2384 |  |  |  | 15094.5429 | 18113.4514
3 |  | Refuge Area
4 |  | 1 | 371.5733 | 0 | 575.9386 |  |  |  |  | 14838.7097
15th Floor (Part Refuge Area) & Fitness Center | [9 empty] | 42168.6747
1 |  | 1 | 371.5733 | 0 | 575.9386 | 15th Floor (Part Refuge Area) & Fitness Center
2 |  | 2 | 555.6377 | 0 | 861.2384
3 |  | Refuge Area
4 |  | 1 | 371.5733 | 0 | 575.9386
16th to 19th Floor
1 |  | 1 | 371.5733 | 0 | 575.9386 | 16th to 19th Floor
2 |  | 2 | 555.6377 | 0 | 861.2384
3 |  | 2 | 555.6377 | 0 | 861.2384
4 |  | 1 | 371.5733 | 0 | 575.9386
5 |  | 1 | 389.1186 | 0 | 603.1338 |  |  |  | 34.345
6 |  | 1 | 389.1186 | 0 | 603.1338 |  |  |  | 2.8325
20th Floor (Part Terrace Area)
1 |  | 1 | 371.5733 | 0 | 575.9386 | 20th Floor (Part Terrace Area)
2 |  | 2 | 555.6377 | 0 | 861.2384
3 |  | Terrace Area & Society Office
4 |  | 1 | 371.5733 | 0 | 575.9386
5 |  | Terrace Area
6
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Construction work is in process at the time of visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates of the Property have been revised on 09/11/2023.
* | Please provide revised approved CC & Plans, As the construction work goes beyond the CC permission and approved no of floors.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Metro Crown
Layout :
Google Map :
Formulas:
Hariyali = [Hariyali, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted