## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 16/08/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-13
Name of the builder group |  |  |  | Lohitka Properties LLP
Name of the builder company |  |  |  | Lohitka Properties LLP
Name of the Project |  |  |  | Montana Phase 4
Contact Details ( Name & Contact No.) |  |  |  | Tejal Shah 8879619137 |  |  |  | Mr avinash CRM 8879975804
Site Person - Contact Details (Name & Contact No.) |  |  |  | Tejal Shah 8879619137
Name / No of the Building As per Approved Plan |  |  |  | Building No.10 (Wing C1 & C2)
Name / No of the Building As per Builder |  |  |  | Blissberg (Wing A & B)
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P51800026393
Project location details |  | Montana Phase 4, CTS No.514, 531 (PT), 531/1 to 14, 532A (PT) & 534, near Cascade Vasant Oscar Apartment Complex, L.B.S. Marg, Moti Nagar, Nahur, Mulund West, Kurla, Mumbai - 400082.
CTS No |  | 514, 531 (PT), 531/1 to 14, 532A (PT) & 534
Locality |  | Moti Nagar
Road |  | L.B.S. Marg |  | Village |  | Nahur
City |  | Mulund West |  | District |  | Mumbai
Taluka |  | Kurla |  | Pin Code |  | 400082
Nearby Landmark |  | Cascade Vasant Oscar Apartment Complex |  | Distance from city centre: |  | 2.90KM from Mulund Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | LBS Marg |  |  | LBS Marg
West | NA | Tansa Pipe Line |  |  | Pipe Line
North | NA | CTS NO. 547 |  |  | Slum
South | NA | 18.30 M. Wide Road |  |  | Marathon Ave
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.171688,72.93709
Location Link |  | https://maps.app.goo.gl/wZQmnAsLUydg4zGfA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 57838.66
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 1.7998
Total FSI availaible for the project |  |  |  | 2.7998
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 161939.02
Total number of Buildings |  |  |  | 02 Wing
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No |  | CHE/ES/2036/T/337( NEW) |  |  | Dated | 2023-03-20
Approved Floor plan No. |  | CHE/ES/2036/T/337( NEW) |  |  | Dated | 2023-03-20
Commencement-CC No Valid Up to: |  | CHE/ES/2036/T/337(NEW)/FCC/4/Amend |  |  | Dated | 2024-10-21
|  | Full C.C. for wing ‘C’ of building No. 10 is granted as per amended approved plan dated 20.03.2023 subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy and taking all sorts of precautions during construction and for air pollution. |  |  | Valid Upto Date | 2025-10-14
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 46304.55
Approved no of units |  |  | Flats - 374
Approved no of Floors |  |  | Building No.10 (Wing C1 & C2) = Gr/Stilt + 1st to 5th Podium + 6th Podium / E-Deck Floor + 1st to 43rd Floor (Residential)
Proposed no of Floors |  |  | Building No.10 (Wing C1 & C2) = Gr/Stilt + 1st to 5th Podium + 6th Podium / E-Deck Floor + 1st to 45th Floor (Residential)
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Swimming Pool, Spa, Jogging Track, Kids play area, Yoga oom, Banquet Hall, Party Lawn, Fitness Centre, Games Room, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.10 (Wing C1) = Gr/Stilt + 1st to 5th Podium + 6th Podium / E-Deck Floor + 1st to 45th Floor (Residential) | [5 empty] | Excavation, Plinth Completed, RCC upto 49 Slab, Brickwork upto 42 Floor, Internal Plaster upto 31.5 Floor, External Plaster upto 27.3 Floor Completed | , RCC upto 49 Slab, Brickwork upto 42 Floor, Internal Plaster upto 31.5 Floor, External Plaster upto 27.3 Floor
Basement | 0 | Ground | 1 | Podium | 6 | Floors | 45 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 49 Slab, Brickwork upto 42 Floor, Internal Plaster upto 31.5 Floor, External Plaster upto 27.3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 11.25
Excavation |  | 45 | 100% | 66.01% |  | 84.47% |  | Excavation in process | 22.5
Plinth |  | 45 | 100% |  |  |  |  | Excavation Completed | 45
RCC (Including podiums) |  | 49 | 94.23% |  |  |  |  | Footing in Process | 11.25
Brickwork | Brickwork & Internal Plaster | 42 | 93.33% |  |  |  |  | Footing Completed | 22.5
Internal Plaster | Brickwork & Internal Plaster | 31.5 | 70% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 27.3 | 60.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 33.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 45
Construction details: |  | Building No.10 (Wing C2) = Gr/Stilt + 1st to 5th Podium + 6th Podium / E-Deck Floor + 1st to 45th Floor (Residential) | [5 empty] | Excavation, Plinth Completed, RCC upto 49 Slab, Brickwork upto 42 Floor, Internal Plaster upto 31.5 Floor, External Plaster upto 27.3 Floor Completed | , RCC upto 49 Slab, Brickwork upto 42 Floor, Internal Plaster upto 31.5 Floor, External Plaster upto 27.3 Floor
Basement | 0 | Ground | 1 | Podium | 6 | Floors | 45 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 49 Slab, Brickwork upto 42 Floor, Internal Plaster upto 31.5 Floor, External Plaster upto 27.3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 11.25
Excavation |  | 45 | 100% | 66.01% |  | 84.47% |  | Excavation in process | 22.5
Plinth |  | 45 | 100% |  |  |  |  | Excavation Completed | 45
RCC (Including podiums) |  | 49 | 94.23% |  |  |  |  | Footing in Process | 11.25
Brickwork | Brickwork & Internal Plaster | 42 | 93.33% |  |  |  |  | Footing Completed | 22.5
Internal Plaster | Brickwork & Internal Plaster | 31.5 | 70% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 27.3 | 60.67% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 33.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 45
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 17000 |  |  |  | 15500 to 17000 | 2023-12-29 | Viraj | verbal
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
One time Club house charges towards membership |  |  |  |  | 350000
Society formation charges |  |  |  |  | 20000
Electric Connection Charges/Water Charges |  |  |  |  | 40000
12 Months Advance Maintenance |  |  |  |  | 171000
Infrastructure/Development Charges |  |  |  |  | 471000
Apex body charges |  |  |  |  | 200000
Pipe line Gas Connection |  |  |  |  | 15000
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 13600
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.10 | Wing C1 | 202 |  | 187615.8742 |  | 281423.8112
| Wing C2 | 172 |  | 113019.2014 |  | 169528.802
Total |  | 374 |  | 300635.0755 |  | 450952.6133
Building details Floor Wise
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building No.10 ( Blissberg )
Wing C1
Ground Floor for Parking, Society Office & Domestic water tank
1st to 5th Floor for Podium for Parking
6th Floor for Podium / E-Deck
1st, 8th, 15th, 22nd & 29th Floor for Residential (Part Refuge Area)
1 |  | 2BHK | 658.6492 | 0 | 987.9737 | 1st, 8th, 15th, 22nd & 29th Floor for Residential (Part Refuge Area)
2 |  | 3.5BHK | 1353.0348 | 0 | 2029.5522 |  |  | 0.82151 | 244.6831
3 |  | Refuge Area | [7 empty] | #DIV/0!
4
5 |  | 2BHK | 627.1106 | 0 | 940.666 |  |  | 0.38076 | 244.6831
2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th, 30th to 35th & 37th to 43rd Floor | [7 empty] | 37
1 |  | 2BHK | 658.6492 | 0 | 987.9737 | 2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th, 30th to 35th & 37th to 43rd Floor |  |  |  | 61438.8799
2 |  | 3.5BHK | 1353.0348 | 0 | 2029.5522 |  |  | 10.764 |  | 29908.0753
3 |  | 2.5BHK | 903.8531 | 0 | 1355.7796 |  |  |  |  | 22865.073
4 |  | 3BHK | 1117.0879 | 0 | 1675.6319 |  |  |  |  | 18500.4835
5 |  | 2BHK | 627.1106 | 0 | 940.666 |  |  |  |  | 32955.3756
36th Floor (Part Refuge Area)
1 |  | 2BHK | 658.6492 | 0 | 987.9737 | 36th Floor (Part Refuge Area)
2 |  | 3.5BHK | 1353.0348 | 0 | 2029.5522
3 |  | Refuge Area
4
5
Wing C2
Ground Floor for Parking, Society Office & Domestic water tank
1st to 5th Floor for Podium for Parking
6th Floor for Podium / E-Deck
1st, 8th, 15th, 22nd & 29th Floor for Residential (Refuge Area At Wing C1)
1 |  | 1.5BHK | 600.5236 | 0 | 900.7853 | 1st, 8th, 15th, 22nd & 29th Floor for Residential (Refuge Area At Wing C1)
2 |  | 1.5BHK | 600.5236 | 0 | 900.7853 |  |  | 0.36462 | 244.6831
3 |  | 2BHK | 713.6532 | 0 | 1070.4798 |  |  |  |  | 28958.9771
4 |  | 2BHK | 713.6532 | 0 | 1070.4798
2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th, 30th to 35th & 37th to 43rd Floor | [7 empty] | 37
1 |  | 1.5BHK | 600.5236 | 0 | 900.7853 | 2nd to 7th, 9th to 14th, 16th to 21st, 23rd to 28th, 30th to 35th & 37th to 43rd Floor |  |  |  | 67385.6437
2 |  | 1.5BHK | 600.5236 | 0 | 900.7853 |  |  | 10.764 |  | 67385.6437
3 |  | 2BHK | 713.6532 | 0 | 1070.4798 |  |  |  |  | 28958.9771
4 |  | 2BHK | 713.6532 | 0 | 1070.4798 |  |  |  |  | 28958.9771
36th Floor (Refuge Area At Wing C1)
1 |  | 1.5BHK | 600.5236 | 0 | 900.7853 | 36th Floor (Refuge Area At Wing C1)
2 |  | 1.5BHK | 600.5236 | 0 | 900.7853
3 |  | 2BHK | 713.6532 | 0 | 1070.4798
4 |  | 2BHK | 713.6532 | 0 | 1070.4798
Remarks:
* | Construction work is in process at the time of Visit. Internal photographs was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + D.B Area + Deck.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Miss. Tejal Shah - 8879619137.
* | As per the approved floor plan dtd. 04/01/2022, of Building No. 10, Wing C (consists of 4 flats on each floor), but according to Miss. Tejal, the contact person, Building No. 10 wing C will be bifurcated in to A & B Wing, and Wing A will consists of 5 flats on each floor & Wing B will consists of 4 flats on each floor. The above changes will be done in the amended plans.
* | We have updated latest approved floor plans on (29/03/2023).
* | We have updated latest approved CC (on 19/06/2023).
* | As Per Approved Plan |  |  | As Per Builder
| Building No. 10 Wing C1 |  | Building No. 10 Wing C1 | Blissberg Wing A
| Building No. 10 Wing C2 |  | Building No. 10 Wing C2 | Blissberg Wing B
* | We have updated latest approved plan, Construction set (on 08/12/2023).
* | Recommended Rates/Other Charges of the Property have been revised on 29/12/2023.
* | Validity of CC is expired on 14/10/2023. Please provide latest CC.
* | We have updated latest CC from MCGM site (On 25/11/2024).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Nainesh Tambe |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Montana Phase 4
Layout Plan :
Google Map :
Formulas:
Nahur = [Nahur, row above]
Montana Phase III Giona (Building No.10 : Wing A & B)
Montana Phase 4
Blissberg
(Building No.10 : Wing C1 & C2)
Montana Phase I Blissberg (Building No.7 : Wing A & B)
Building No 10
Building No. 7
Building No. 10
Wing C1
Building No. 10
Wing C2
C1
C2
C1
C2

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted