## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 20/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-14
Name of the builder group |  |  |  | Parsn Construction And Developers Private Limited
Name of the builder company |  |  |  | Parsn Construction And Developers Private Limited
Name of the Project As per Builder Name |  |  |  | Shiv Vaibhav
Name of the Project As Per Rera Name |  |  |  | Nehru Nagar Shiv Vaibhav CHS Ltd Bldg No.38
Provided Contact Details (Name & Contact No.) |  |  |  | 9821221738
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Yohan Patel 9326105537
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building |  |  |  | Bldg No.38 Shiv Vaibhav CHS Ltd. | [6 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans | [6 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51800032409 |  |  |  | #N/A |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Nehru Nagar Shiv Vaibhav CHS Ltd Bldg No.38, CTS No.12(PT), Redevlopement of " Bldg No. 38 Shiv Vaibhav CHS Ltd.", near Sai Sadan Co-operative Housing Society, Kedarnath Mandir Road, Nehru Nagar Mhada Colony, Kurla III, Kurla East, Kurla, Mumbai - 400071. | [8 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 12(PT), Redevlopement of " Bldg No. 38 Shiv Vaibhav CHS Ltd." | [8 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Nehru Nagar Mhada Colony | [8 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Kedarnath Mandir Road |  | Locality/Village |  | Kurla III |  |  |  |  | Ambernath | Dahanu |  | Pen | Shirur
City |  | Kurla East |  | District |  | Mumbai |  |  |  |  | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Kurla |  | Pin Code |  | 400071 | [7 empty] | Mahad | Daund
Nearby Landmark |  | Sai Sadan Co-operative Housing Society |  | Distance from city centre: |  | 0.55 KM from Kurla Railway Station | [7 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [9 empty] | Mangaon | Ambegaon
[14 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [9 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [9 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [9 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Scheme Amenity |  |  | Shops/SG Barve Road
West | NA | Bldg No.41, Bldg No.40 |  |  | Sai Sadan Co-operative Housing Society
North | NA | Bldg No. 39 |  |  | Mitra Sahakar Co-operative Housing Society
South | NA | 18.30 MTR Wide Existing Road |  |  | Kedarnath Mandir Road/Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.062106,72.882955
Location Link |  | https://goo.gl/maps/9uzQPQXoDFkRVAKy5
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1288.85
Permissible FSI |  |  |  | 3
Permissible TDR/Paid FSI |  |  |  | 3.1295
Total FSI availaible for the project |  |  |  | 0
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7900
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Maharashtra Housing and Area Development Authority ( MHADA )
Layout Approval No |  | Mhada - 22/597/2024 |  |  | Dated | 2024-03-28
Approved Floor plan No. |  | Mhada - 22/597/2024 |  |  | Dated | 2024-03-28
Commencement-CC No Valid Up to: |  | MH/EE/(BP)/GM/MHADA-22/597/2024/FCC/1/Amend |  |  | Dated | 2024-12-17
|  | This full C.C. is issued for building comprising of Basement for Pump Room + Stilt Part for Parking & Utility + Part Ground for Fitness Centre & Society Office + 1st to 16th upper floor for residential use having height 50.42 mt.+ OHT & LMR as per approved amended plans dated 28/03/2024. |  |  | Valid Upto Date | 2025-07-22
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Approved area of building (Sq.Mt) |  |  | 7900
Approved no of units |  |  | Flats = 128
Approved no of Floors |  |  | G + 1st to 16th Floor
Proposed no of Floors |  |  | G + 1st to 16th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Lavish Lobby, Garden Deck, Children Play Area, Power Back up, Terrace Gym, CCTV Surveillance, Hi-Tech Fire Fighting System. |  |  |  |  | https://www.clicbrics.com/parsn-nehru-nagar-shiv-vaibhav-chs-ltd-bldg-no-38-mumbai
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | G + 1st to 16th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 15 Slab, Brickwork upto 10 Floor, Internal Plaster upto 5 Floor Completed | , RCC upto 15 Slab, Brickwork upto 10 Floor, Internal Plaster upto 5 Floor | https://www.propi.in/project-rera/nehru-nagar-shiv-vaibhav-chs-ltd-bldg-no-38-kurla-by-parsn-foundation-amp-engg-corporation/P51800032409#Wing-Nehru-Nagar-Shiv-Vaibhav-Chs-Ltd-Bldg-No-38
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 15 Slab, Brickwork upto 10 Floor, Internal Plaster upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 52.33% |  | 76.16% |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 15 | 88.24% |  |  |  |  | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 10 | 62.5% |  |  |  |  | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 5 | 31.25% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 16
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | #REF! | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | 20 | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | 0 | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | #REF! | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | #REF! | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | #REF! | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 16000 |  |  |  | rate revised by sanjay on 03/05/25
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 12800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 128 |  | 76925.5718 |  | 115388.3578
Total |  | 128 |  | 76925.5718 |  | 115388.3578
Grand Total |  | 128 |  | 76925.5718 |  | 115388.3578
Building details Floor Wise
Details of Residential & Commercials in Building | [7 empty] | 10.764
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
45%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Ground Floor For Entrance Lobby, Fitness Center, Meter Room, Society Office & Parking
1st to 6th Floor For Residential
1 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 1st to 6th Floor For Residential
2 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 1st to 6th Floor For Residential
3 |  | 1RK | 260.0582 | 0 | 390.0874 | 1st to 6th Floor For Residential
4 |  | 1BHK | 460.2686 | 0 | 690.403 | 1st to 6th Floor For Residential
5 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 1st to 6th Floor For Residential
6 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 1st to 6th Floor For Residential
7 |  | 2BHK | 653.4824 | 0 | 980.2237 | 1st to 6th Floor For Residential
8 |  | 2BHK | 655.2047 | 0 | 982.807 | 1st to 6th Floor For Residential
7th Floor (Refuge Area at midlanding of the staircase)
1 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 7th Floor (Refuge Area at midlanding of the staircase)
2 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 7th Floor (Refuge Area at midlanding of the staircase)
3 |  | 1RK | 260.0582 | 0 | 390.0874 | 7th Floor (Refuge Area at midlanding of the staircase)
4 |  | 1BHK | 460.2686 | 0 | 690.403 | 7th Floor (Refuge Area at midlanding of the staircase)
5 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 7th Floor (Refuge Area at midlanding of the staircase)
6 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 7th Floor (Refuge Area at midlanding of the staircase)
7 |  | 2BHK | 653.4824 | 0 | 980.2237 | 7th Floor (Refuge Area at midlanding of the staircase)
8 |  | 2BHK | 655.2047 | 0 | 982.807 | 7th Floor (Refuge Area at midlanding of the staircase)
8th, 10th, 12th, 14th & 16th Floor
1 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 8th, 10th, 12th, 14th & 16th Floor
2 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 8th, 10th, 12th, 14th & 16th Floor
3 |  | 1RK | 260.0582 | 0 | 390.0874 | 8th, 10th, 12th, 14th & 16th Floor
4 |  | 1BHK | 460.2686 | 0 | 690.403 | 8th, 10th, 12th, 14th & 16th Floor
5 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 8th, 10th, 12th, 14th & 16th Floor
6 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 8th, 10th, 12th, 14th & 16th Floor
7 |  | 2BHK | 653.4824 | 0 | 980.2237 | 8th, 10th, 12th, 14th & 16th Floor
8 |  | 2BHK | 655.2047 | 0 | 982.807 | 8th, 10th, 12th, 14th & 16th Floor
9th, 11th, 13th & 15th Floor (Refuge Area at midlanding of the staircase)
1 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 9th, 11th, 13th & 15th Floor (Refuge Area at midlanding of the staircase)
2 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 9th, 11th, 13th & 15th Floor (Refuge Area at midlanding of the staircase)
3 |  | 1RK | 260.0582 | 0 | 390.0874 | 9th, 11th, 13th & 15th Floor (Refuge Area at midlanding of the staircase)
4 |  | 1BHK | 460.2686 | 0 | 690.403 | 9th, 11th, 13th & 15th Floor (Refuge Area at midlanding of the staircase)
5 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 9th, 11th, 13th & 15th Floor (Refuge Area at midlanding of the staircase)
6 |  | 2BHK | 694.7086 | 0 | 1042.0628 | 9th, 11th, 13th & 15th Floor (Refuge Area at midlanding of the staircase)
7 |  | 2BHK | 653.4824 | 0 | 980.2237 | 9th, 11th, 13th & 15th Floor (Refuge Area at midlanding of the staircase)
8 |  | 2BHK | 655.2047 | 0 | 982.807 | 9th, 11th, 13th & 15th Floor (Refuge Area at midlanding of the staircase)
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Construction work is in process at the time of Visit. (Internal visit was not allowed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | We have updated Approved plans & Approved CC (On date 23/12/2024).
* | Please check for Fire Noc.
* | Recommended Rates / Other charges of the Property have been revised on 03/05/2025.
* | Validity of CC is expired on 22/07/2025. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Akash Kadam |  | Report By : |  | Kunal Kadam
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Nehru Nagar Shiv Vaibhav CHS Ltd Bldg No.38
Layout :
Google Map :
Formulas:
Kurla III = [Kurla III, row above]
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on D56: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC