## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/08/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder As per RERA |  |  |  | Yamutai Balaji Vichare
Name of the builder company |  |  |  | Y. B. Developers
Name of the Project |  |  |  | Heetraj Heights
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Abhishek 8097639370
Site Person - Contact Details (Name & Contact No.) |  |  |  | Miss. Priyansha Mishra 961913297
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleble Area, Cost Sheet | [8 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000050015 |  |  |  | #N/A |  |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Heetraj Heights, CTS No.443, near Radhe Galaxy, Internal Road, Bhisegaon, Karjat, Karjat West, Karjat, Raigad - 410201. | [10 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 443 | [10 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Bhisegaon | [10 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Karjat | [6 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Karjat West |  | District |  | Raigad | [6 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Karjat |  | Pin Code |  | 410201 | [9 empty] | Mahad | Daund
Nearby Landmark |  | Radhe Galaxy |  | Distance from city centre: |  | 0.210KM from Karjat Railway Station | [9 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [11 empty] | Mangaon | Ambegaon
[16 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [11 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [11 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [11 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Internal Road/ S.No.447C |  |  | Internal Road
West | NA | Other Plot |  |  | Radhe Galaxy
North | NA | S.No.447B |  |  | Bungalow
South | NA | Survey No. 43C |  |  | Siddhivinayak Residency
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 18.912899,73.318968
Location Link |  | https://goo.gl/maps/GMtA8bR6ebTqE9g66
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1109.2
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.1706
Total FSI availaible for the project |  |  |  | 2.2706
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 2518.54
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Karjat Municipal Council
Layout Approval No |  | S.R.31/21-22 |  |  | Dated | 2021-12-16
Approved Floor plan No. |  | S.R.31/21-22 |  |  | Dated | 2021-12-16
Commencement-CC No Valid Up to: |  | Imarat/SB.1/KT-1/S.R.31/21-22 |  |  | Dated | 2021-12-16
Gr + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 2518.54
Approved no of units |  |  | Flats - 45, Shops - 6, Offices - 4
Approved no of Floors |  |  | Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/03/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Entrance Lobby, Vitrified Tiles, Kitchen Platform
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor, External Plaster upto 1 Floor Completed | , Internal Plaster upto 3 Floor, External Plaster upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor, External Plaster upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 62.14% |  | 82.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 3 | 42.86% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 14.29% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  |  | Builder | Visitor
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3500 |  |  | 4000 | 11000 | 4444.4444
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 7000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 6000
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 150000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 50000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 2800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 6 |  | 1214.1523 |  | 2462
Offices |  | 4 |  | 1731.4497 |  | 3539
Total |  | 10 |  | 2945.602 |  | 6001
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 45 |  | 17901.9313 |  | 28461
Total |  | 45 |  | 17901.9313 |  | 28461
Grand Total |  | 55 |  | 20847.5333 |  | 34462
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable area | Floor
Ground Floor For Commercial & Parking | [8 empty] | 10.764
1 |  | Shop | 211.8355 | 0 | 426 | Ground Floor For Commercial & Parking |  |  |  | 426 | 2.011
2 |  | Shop | 206.319 | 0 | 424 |  |  |  |  | 424 | 2.0551
3 |  | Shop | 210.7053 | 0 | 426 |  |  |  |  | 426 | 2.0218
4 |  | Shop | 210.7053 | 0 | 426 |  |  |  |  | 426 | 2.0218
5 |  | Shop | 163.8819 | 0 | 334 |  |  |  | 15.225 | 334 | 2.0381
6 |  | Shop | 210.7053 | 0 | 426 |  |  |  |  | 426 | 2.0218
1st Floor For Part Commercial | [10 empty] | #DIV/0!
1 |  | Office | 593.6949 | 0 | 1180 | 1st Floor For Part Commercial |  |  |  | 1180 | 1.9876
2 |  | Office | 403.2463 | 0 | 809 |  |  |  |  | 809 | 2.0062
3 |  | Office | 276.7693 | 0 | 562 |  |  |  |  | 562 | 2.0306
4 |  | Office | 457.7391 | 0 | 988 |  |  |  |  | 988 | 2.1584
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
1st Floor For Part Residential
1 |  | 1 | 375.1254 | 0 | 585 | 1st Floor For Part Residential |  |  | 28.625 | 585
2 |  | 1 | 396.2228 | 0 | 600 | 1st Floor For Part Residential |  |  | 30.67 | 600
3 |  | 1 | 372.542 | 0 | 586 | 1st Floor For Part Residential |  |  |  | 586
4 |  | 1 | 372.542 | 0 | 586 | 1st Floor For Part Residential |  |  |  | 586
2nd Floor For Residential
1 |  | 1 | 375.1254 | 0 | 585 | 2nd Floor For Residential |  |  |  | 585 | 1.5595
2 |  | 1 | 396.2228 | 0 | 600 | 2nd Floor For Residential |  |  |  | 600 | 1.5143
3 |  | 1 | 372.542 | 0 | 585 | 2nd Floor For Residential |  |  |  | 585 | 1.5703
4 |  | 1 | 372.542 | 0 | 585 | 2nd Floor For Residential |  |  |  | 585 | 1.5703
5 |  | 1 | 319.6908 | 84.8203 | 620 | 2nd Floor For Residential |  |  |  | 620 | 1.9394
6 |  | 1 | 299.3468 | 181.2388 | 689 | 2nd Floor For Residential |  |  |  | 689 | 2.3017
7 |  | 2 | 461.8832 | 250.9357 | 960 | 2nd Floor For Residential |  |  |  | 960 | 2.0784
3rd to 6th Floor
1 |  | 1 | 375.1254 | 0 | 585 | 3rd to 6th Floor |  |  |  | 585 | 1.5595 | 2340000
2 |  | 1 | 396.2228 | 0 | 600 | 3rd to 6th Floor |  |  |  | 600 | 1.5143 | 2400000
3 |  | 1 | 372.542 | 0 | 586 | 3rd to 6th Floor |  |  |  | 586 | 1.573 | 2344000
4 |  | 1 | 372.542 | 0 | 586 | 3rd to 6th Floor |  |  |  | 586 | 1.573 | 2344000
5 |  | 1 | 372.542 | 0 | 586 | 3rd to 6th Floor |  |  |  | 586 | 1.573 | 2344000
6 |  | 1 | 387.0734 | 0 | 614 | 3rd to 6th Floor |  |  |  | 614 | 1.5863 | 2456000
7 |  | 2 | 556.6064 | 0 | 856 | 3rd to 6th Floor |  |  |  | 856 | 1.5379 | 3424000
7th Floor (Part Terrace Area)
- |  | Terrace Area |  |  |  | 7th Floor (Part Terrace Area)
1 |  | 1 | 396.2228 | 0 | 600 |  |  |  |  | 600
2 |  | 1 | 372.542 | 0 | 586 |  |  |  |  | 586
3 |  | 1 | 372.542 | 0 | 586 |  |  |  |  | 586
4 |  | 1 | 372.542 | 0 | 586 |  |  |  |  | 586
5 |  | 1 | 387.0734 | 0 | 614 |  |  |  |  | 614
6 |  | 2 | 556.6064 | 0 | 856 |  |  |  |  | 856
Ground Floor
1 |  |  |  | 0 | #REF! | Ground Floor
2 |  |  |  | 0 | #REF! | Ground Floor
3 |  |  |  | 0 | #REF! | Ground Floor
4 |  |  |  | 0 | #REF! | Ground Floor
2nd Floor
201 |  |  |  | 0 | #REF! | 2nd Floor
202 |  |  |  | 0 | #REF! | 2nd Floor
203 |  |  |  | 0 | #REF! | 2nd Floor
204 |  |  |  | 0 | #REF! | 2nd Floor
205 |  |  |  | 0 | #REF! | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | #REF! | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | #REF! | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | #REF! | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | #REF! | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | #REF! | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | #REF! | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | #REF! | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | #REF! | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | #REF! | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | #REF! | 2nd & 5th Floor
Remarks:
* | Construction work is in process at the time of visit (Slow Speed).
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As per subsequent report dated 10/07/2024, The project has been temporarily suspended on RERA by the authority.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report By : |  | Kunal Kadam
PHOTOGRAPHS OF PROPERTY : |  |  | Heetraj Heights
Layout :
Google Map :
Formulas:
Karjat = [Karjat, row above]
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC