## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 14/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-12
Name of the builder |  |  |  |  | M/s.Jollity Infracon
Name of the builder company |  |  |  |  | M/s.Jollity Infracon
Name of the Project |  |  |  |  | Jollity Safalya
Contect Details ( Name & Contect No.) |  |  |  |  | 2228942354
Name / no of the Building |  |  |  |  | Jollity Safalya/1 Building (C & D Wings)
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, NA Order cum CC.
Rera No |  |  |  |  | P99000010327
Project location details |  | Jollity Safalya (Building no.2 - C & D Wings), G.No. 101/1 142/1, Village-Warangade, Near Theem Engineering Collage, Boisar East, Palghar.
Plot No | NA | S No /G. No |  | G.No. 101/1 142/1 |  |  | Locality | Warangade
Road | Boisar Road |  |  |  | District | Palghar
City | Boisar East |  |  |  | Pin Code | 401501
Near by Landmark |  | Near Theem Engineering Collage |  |  | Distance from city centre: |  | About 5.1 KM from Boisar Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 5 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open Plot |  | Open Plot |  | Road |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | Latitude |  | 19.7865 |  | Longitude |  | 72.7802
Location Link |  | https://goo.gl/maps/U3gueq9jA3UUqTaK9?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential (Restrictive Covenants in regard to Land Use, if any) : No
Total land area of the project in Sq. Mt. |  |  |  |  | 14170
Permissible FSI |  |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.75
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 10627.5
Total number of Buildings |  |  |  |  | 2 Wings
Approval Detail : Plan approval
Layout Approval No |  | BS/BP/Warangade/Palghar/1269 |  |  |  | Dated | 27/10/2016.
Building plan approval No |  | BS/BP/Warangade/Palghar/1269 |  |  |  | Dated | 27/10/2016.
NA Order cum Commencement Certificate No. |  | MHSUL/CLASS.1/T.1/NAP/SR-67/2016. Valid Upto : G + 1st to 2nd Floor |  |  |  | Dated | 21/12/2016.
O. Certificate No.: |  |  |  |  | Date of approval: |  |  | Expiry date: NA
Commencement date of construction |  |  | 21/12/2016. |  | Expected Completion |  | 2025-03-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 10627.5 |  | Approved no of units residential |  |  | Flats = 29
Approved no of Floors |  | G + 1st to 2 Floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  |  |  | Projected life : 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details:
Stage of construction Building no.2 : Plinth, RCC, Brick Work, Plaster work & Flooring upto 1st floor is completed. Other work is in process……………
|  | Type of Work |  |  | % Complition
|  | Plinth |  |  | 100
|  | RCC |  |  | 100
|  | Brick |  |  | 100
|  | Plaster |  |  | 100
|  | Flooring |  |  | 14.2857
|  | Painting & Wooden Work |  |  | 0
|  | Finishing |  |  | 0
% Progress |  |  | 76.4286 |  | % Disbursement |  |  | 28
Stage of construction Building no.3 : Work not yet Started.
|  | Type of Work |  |  | % Complition
|  | Plinth |  |  | 0
|  | RCC |  |  | 0
|  | Brick |  |  | 0
|  | Plaster |  |  | 0
|  | Flooring |  |  | 0
|  | Painting & Wooden Work |  |  | 0
|  | Finishing |  |  | 0
% Progress |  |  | 0 |  | % Disbursement |  |  | 0
Construction details: |  | (Building no.2 - C & D Wing) = Gr + 1st to 2nd Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 1 Floor completed, External Plaster upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 2 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 3 Slab completed, Brickwork upto 2 Floor completed, Internal Plaster upto 1 Floor completed, External Plaster upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 0.5
Excavation |  | 2 | 100% |  | 71.25% |  | 87.5% |  | Excavation in process |  | 1
Plinth |  | 2 | 100% | [5 empty] | Excavation Completed |  | 2
RCC (Including podiums) |  | 3 | 100% | [5 empty] | Footing in Process |  | 0.5
Brickwork | Brickwork & Internal Plaster | 2 | 100% | [5 empty] | Footing Completed |  | 1
Internal Plaster | Brickwork & Internal Plaster | 1 | 50% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 100% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 1.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 2
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the Flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 2600
Recommended rate of the Shop Per Sq. Ft. ( on Carpet area) | [5 empty] | 6000
Water/Electricity connection | [5 empty] | 25064/-
Society Maintain charges | [5 empty] | 28200/-
Society formation charges | [5 empty] | 45186/-
Recommended rate of Parking | [5 empty] | NA
Development charges | [5 empty] | 130500/-
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 2080
Building details Floor Wise
Details of Flats in Building
Flat No. | Description | Gross Carpet area | Built-up Area |  | Attached Terrace area | Builder Saleable area | PLC Y/N | Floor
Building no.2
C Wing - Type 4
Ground Floor For Parking
1 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA | Ground Floor
2 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
3 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
4 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
5 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
6 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
1st & 2nd Floor
1 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA | 1st & 2nd Floor
2 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
3 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
4 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
5 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
6 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
D Wing - Type 1
Ground Floor For Parking
1 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA | Ground Floor
2 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA |  |  | 136500
3 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
1st & 2nd Floor
1 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA | 1st & 2nd Floor
2 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
3 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
4 | 1 BHK | 274.9126 | 329.8951 |  | 0 | 455 | NA
Remarks: 1. Construction work was stopped from last visit (21/07/2021). 2. We adopted Carpet Area & Built-up area as per Approved Plan. 3. The Saleable Area is adopted as per builder Area statement. 4. We have considered rate by verifying it from market inquire. 5. We have considered Other charges from cost sheet. 6. Car parking is subjected to authentic documentation. 7. Since the project has received first CC on 21/12/2016., but still project is under construction. 8. As per RERA, completion period of project Jollity Safalya is expired on 31/03/2025 but still project is under construction. 9. As checked on RERA portal on dated 14/08/2025, we have observed that above project is kept under abeyance. 7. On site, we meet Mr.Paresh - 7499701408.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The Saleable Area is as per builder Area statement.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  |  |  | Jollity Safalya
Google Map :

## Construction %
Particulars | totaL floor | 2
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 3 | 3 | 100 | Progress | 10 | 40 | 15 | 5 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 30 | 30 | 15 | 5 | 0 | 0 | 0
| 2 | 2 | 100
plaster | Total Floor | completed Floor
| 2 | 1 | 50
Flooring | Total Floor | completed Floor
| 2 | 0 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 2 | 0 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  |  | Bricks | 15 | 15
| 2 | 0 | 0 |  | Plaster | 5 | 5
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 70 | 80

## Note
16/03/2020. | Dhanashree OLD APF | 1.Rate is Approx. Index II
|  | In Previous report - | We considered rate as per builder cost sheet.
22/08/2020. | Pratiksha
2021-02-04 | Pratiksha

## valuation
2021-02-04 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Housing |  |  |  |  | #DIV/0!
| Proptiger |  |  |  |  | #DIV/0!
| Magic Brick |  |  |  |  | #DIV/0!
| Magic Brick |  |  |  |  | #DIV/0!
| Magic Brick |  |  |  |  | #DIV/0!
| 99 Acres |  |  |  |  | #DIV/0!
| 99 Acres |  |  |  |  | #DIV/0!
| Average |  |  |  |  | #DIV/0!
| Valuation Adopted |  |  |  |  | 32000

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3 | 4.5 | 13.5 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.1 | 1.9 | 3.99 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.75 | 2.75 | 7.5625 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 0.9 | 1.08 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.1 | 1.2 | 2.52 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 0.9 | 2.9 | 2.61 |  |  |  | 0 |  |  | 0
| passage2 | 1.1 | 0.8 | 0.88 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 345.9819 | 32.1425 |  |  | 0 | 0 |  | 0 | 0

## Construction % (2) (hidden)
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 100 | Progress | 10 | 40 | 15 | 10 | 1.4286 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 30 | 30 | 15 | 10 | 0.71429 | 0 | 0
| 7 | 7 | 100
plaster | Total Floor | completed Floor
| 7 | 7 | 100
Flooring | Total Floor | completed Floor
| 7 | 1 | 14.2857 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 10 | 30
| 7 | 0 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  |  | Bricks | 15 | 15
| 7 | 0 | 0 |  | Plaster | 10 | 10
[5 empty] | Flooring | 1.4286 | 0.71429
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 76.4286 | 85.7143

## Construction % (3) (hidden)
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 0 | 0
slab | total slab | completed slab |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 | 0 | Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | Recommended | 20 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 0 | 20
| 4 | 0 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 4 | 0 | 0 |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 0 | 20