## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/08/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | Oyster Living LLP
Name of the builder company |  |  |  | Oyster Living LLP
Name of the Project |  |  |  | Anantam Phase I & II
Provided Contact Details ( Name & Contact No.) |  |  |  | Saud Shaikh - 8291040036 / 9819666272
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Saud Shaikh 8291040036 Mr. Rajiv 9819666272
Name / No of the Building |  |  |  | A to C Wing & Commercial Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Cost Sheet
RERA No. |  |  |  | Phase I (Wing B & C) : P51700017123 Phase II (Wing A) : P51700017195
Project location details |  | Anantam Phase I & II, Survey No.12, H. No. 41, S. No.13, H. No. 2 & S. No. 18, H. No. 2 (Old S. No. 246, H. No. 41, Old S. No.245, H. No. 12, S. No. 247, H. No. 2), near Aashirwad Palace, Pimplas Road, Pimpalas, Pimpalas, Bhiwandi , Bhiwandi, Thane - 421302.
Survey No |  | 12, H. No. 41, S. No.13, H. No. 2 & S. No. 18, H. No. 2 (Old S. No. 246, H. No. 41, Old S. No.245, H. No. 12, S. No. 247, H. No. 2)
Locality |  | Pimpalas
Road |  | Pimplas Road |  | Locality/Village |  | Pimpalas
City |  | Bhiwandi |  | District |  | Thane
Taluka |  | Bhiwandi |  | Pin Code |  | 421302
Nearby Landmark |  | Aashirwad Palace |  | Distance from city centre: |  | 4.2 KM from Bhiwandi Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Aashirwad Palace
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.2502 |  | Longitude |  | 73.0717
Location Link |  | https://goo.gl/maps/U81D51QKUnUB8Nyc9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 12130
Permissible FSI |  |  |  | 0.95
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 0.95
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 11523.5
Total number of Buildings |  |  |  | 3 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Mumbai Metropolitan Region Development Authority (MMRDA)
Layout Approval No |  | SROT/BSNA/2501/BP/Pimpalas-05/668/2018 |  |  | Dated | 2018-04-23
Approved Floor plan No. |  | SROT/BSNA/2501/BP/Pimpalas-05/668/2018 |  |  | Dated | 2018-04-23
Commencement-CC No Valid Up to: |  | SROT/BSNA/2501/BP/Pimpalas-05/668/2018 |  |  | Dated | 2018-04-23
Wing A to C = Up to Plinth Level Only
Commencement-CC No Valid Up to: |  | SROT/BSNA/2501/BP/Revised CC/Pimpalas-05/552/2023 |  |  | Dated | 2023-04-11
Wing B & C = Gr(Pt)/St(Pt) + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 11523.5
Approved no of units |  |  | Flats -170, Shops -36
Approved no of Floors |  |  | Phase I (Wing B & C) = G + 1st to 7th Floor Phase II (Wing A) = G + 1st to 7th Floor D Wing = G + 1st to 2nd Floor
Proposed no of Floors |  |  | Phase II (Wing A) = G + 1st to 7th Floor
Phase I (Wing B & C) = G + 1st to 7th Floor
D Wing = G + 1st to 2nd Floor
Expected Completion |  |  | As per RERA - Phase I (Wing B & C) = 31/08/2024 Phase II (Wing A) = 30/06/2023
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Phase II (Wing A) = G + 1st to 7th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Phase I (Wing B & C) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 5 Slab Completed | , RCC upto 5 Slab
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 5 Slab Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 35% |  | 63.75% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 5 | 62.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | D Wing = G + 1st to 2nd Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 2 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.5
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 1
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 2
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 1
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 1.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 2
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 6500
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges & Other Legal Charges |  |  |  |  | 120000
Advance Maintenance Charges (For 24 months) |  |  |  |  | 35000
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 3200
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 14 |  | 1844.4114 |  | 2766.6171
Wing B & C |  | 12 |  | 1531.179 |  | 2296.7685 |  |  | rate sheet
D Wing |  | 10 |  | 1046.6914 |  | 1570.037 |  |  | builder | market
Total |  | 26 |  | 3375.5904 |  | 5063.3856 |  | shop |  |  | 75681.1889
Residential Area Details : | [7 empty] | flat | 3000 | 4000 | 52077.5237
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 70 |  | 22137.2424 |  | 32099.0015
Wing B |  | 42 |  | 11238.9077 |  | 16296.4161
Wing C |  | 42 |  | 15325.7832 |  | 22222.3856
D Wing |  | 16 |  | 5838.3936 |  | 8465.6707
Total |  | 154 |  | 48701.9333 |  | 70617.8033
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
50%
Phase II
Wing A
Ground Floor For Commercial & Parking
1A |  | Shop | 127.2305 | 0 | 190.8457 | Ground Floor For Commercial & Parking |  | 11.8215 | 10.764
1B |  | Shop | 138.5327 | 0 | 207.799
2 |  | Shop | 137.241 | 0 | 205.8615
3 |  | Shop | 150.696 | 0 | 226.044
4 |  | Shop | 64.584 | 0 | 96.876
5 |  | Shop | 64.584 | 0 | 96.876
6 |  | Shop | 150.696 | 0 | 226.044
7 |  | Shop | 150.696 | 0 | 226.044
8 |  | Shop | 160.9218 | 0 | 241.3827
9A |  | Shop | 114.0984 | 0 | 171.1476
9B |  | Shop | 122.279 | 0 | 183.4186
10 |  | Shop | 188.37 | 0 | 282.555
11A |  | Shop | 160.3836 | 0 | 240.5754
11B |  | Shop | 114.0984 | 0 | 171.1476
Phase I
Wing B & C
Ground Floor For Commercial & Parking
1 |  | Shop | 118.404 | 0 | 177.606 | Ground Floor For Commercial & Parking |  | 10.597
2 |  | Shop | 86.112 | 0 | 129.168
3 |  | Shop | 118.404 | 0 | 177.606
4 |  | Shop | 86.112 | 0 | 129.168
5 |  | Shop | 161.9982 | 0 | 242.9973 |  |  | 15.12
6 |  | Shop | 161.9982 | 0 | 242.9973
7 |  | Shop | 209.898 | 0 | 314.847 |  |  | 18.76
8 |  | Shop | 139.932 | 0 | 209.898
9 |  | Shop | 94.7232 | 0 | 142.0848
10 |  | Shop | 108.1782 | 0 | 162.2673
11 |  | Shop | 94.7232 | 0 | 142.0848
12 |  | Shop | 150.696 | 0 | 226.044
D Wing
Ground Floor For Commercial & Parking
1 |  | Shop | 118.1887 | 0 | 177.2831 | Ground Floor For Commercial & Parking
2 |  | Shop | 91.6016 | 0 | 137.4025 | Ground Floor For Commercial & Parking
3 |  | Shop | 113.022 | 0 | 169.533 | Ground Floor For Commercial & Parking |  | 11.16
4 |  | Shop | 85.4662 | 0 | 128.1992 | Ground Floor For Commercial & Parking
5 |  | Shop | 118.1887 | 0 | 177.2831 | Ground Floor For Commercial & Parking
6 |  | Shop | 118.1887 | 0 | 177.2831 | Ground Floor For Commercial & Parking
7 |  | Shop | 85.4662 | 0 | 128.1992 | Ground Floor For Commercial & Parking
8 |  | Shop | 113.9908 | 0 | 170.9861 | Ground Floor For Commercial & Parking
9 |  | Shop | 84.3898 | 0 | 126.5846 | Ground Floor For Commercial & Parking
10 |  | Shop | 118.1887 | 0 | 177.2831 | Ground Floor For Commercial & Parking
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Phase II
Wing A
1st to 7th Floor For Residential
101 to 701 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st to 7th Floor For Residential |  | 32.0529 | 3061.7775 |  |  | 101 | 701 | 101 to 701
102 to 702 |  | 1BHK | 364.8996 | 0 | 529.1044 | [6 empty] | 102 | 702 | 102 to 702
103 to 703 |  | 1BHK | 364.8996 | 0 | 529.1044 | [6 empty] | 103 | 703 | 103 to 703
104 to 704 |  | 1BHK | 364.8996 | 0 | 529.1044 | [6 empty] | 104 | 704 | 104 to 704
105 to 705 |  | 1RK | 267.593 | 0 | 388.0099 |  |  | 24.8614 | 3054.0457 |  |  | 105 | 705 | 105 to 705
106 to 706 |  | 1RK | 267.593 | 0 | 388.0099 |  |  | 3608.1553 |  |  |  | 106 | 706 | 106 to 706
107 to 707 |  | 1RK | 267.593 | 0 | 388.0099 | [6 empty] | 107 | 707 | 107 to 707
108 to 708 |  | 1BHK | 364.8996 | 0 | 529.1044 |  |  | 4271.3686 |  |  |  | 108 | 708 | 108 to 708
109 to 709 |  | 1RK | 267.593 | 0 | 388.0099 | [6 empty] | 109 | 709 | 109 to 709
110 to 710 |  | 1RK | 267.593 | 0 | 388.0099 |  |  | 4556.5847 |  |  |  | 110 | 710 | 110 to 710
Phase I
Wing B
1st to 7th Floor For Residential
101 to 701 |  | 1RK | 267.593 | 0 | 388.0099 | 1st to 7th Floor For Residential |  | 23.2218 |  |  |  | 101 | 701 | 101 to 701
102 to 702 |  | 1RK | 267.593 | 0 | 388.0099 |  |  | 3608.1553 |  |  |  | 102 | 702 | 102 to 702
103 to 703 |  | 1RK | 267.593 | 0 | 388.0099 | [6 empty] | 103 | 703 | 103 to 703
104 to 704 |  | 1RK | 267.593 | 0 | 388.0099 | [6 empty] | 104 | 704 | 104 to 704
105 to 705 |  | 1RK | 267.593 | 0 | 388.0099 |  |  | 5927.6837 |  |  |  | 105 | 705 | 105 to 705
106 to 706 |  | 1RK | 267.593 | 0 | 388.0099 | [6 empty] | 106 | 706 | 106 to 706
Wing C
1st to 7th Floor For Residential
101 to 701 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st to 7th Floor For Residential |  | 31.9791 | 4552.9765 |  |  | 101 | 701 | 101 to 701
102 to 702 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st to 7th Floor For Residential |  | 6047.9555 |  |  |  | 102 | 702 | 102 to 702
103 to 703 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st to 7th Floor For Residential |  | 4271.3686 |  |  |  | 103 | 703 | 103 to 703
104 to 704 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st to 7th Floor For Residential |  | 4271.3686 |  |  |  | 104 | 704 | 104 to 704
105 to 705 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st to 7th Floor For Residential | [5 empty] | 105 | 705 | 105 to 705
106 to 706 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st to 7th Floor For Residential | [5 empty] | 106 | 706 | 106 to 706
D Wing
1st & 2nd Floor For Residential
101 to 701 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st & 2nd Floor For Residential | [5 empty] | 101 | 701 | 101 to 701
102 to 702 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st & 2nd Floor For Residential | [5 empty] | 102 | 702 | 102 to 702
103 to 703 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st & 2nd Floor For Residential | [5 empty] | 103 | 703 | 103 to 703
104 to 704 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st & 2nd Floor For Residential | [5 empty] | 104 | 704 | 104 to 704
105 to 705 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st & 2nd Floor For Residential | [5 empty] | 105 | 705 | 105 to 705
106 to 706 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st & 2nd Floor For Residential | [5 empty] | 106 | 706 | 106 to 706
107 to 707 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st & 2nd Floor For Residential | [5 empty] | 107 | 707 | 107 to 707
108 to 708 |  | 1BHK | 364.8996 | 0 | 529.1044 | 1st & 2nd Floor For Residential | [5 empty] | 108 | 708 | 108 to 708
Remarks:
* | Wing A = Work not yet started. Wing B & C = Construction Stage has incresed as compare to last visited date 09/05/2025 but at the time of visit no labour or no active work found on site.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | The provided approved floor plans and sale plans are mismatched.
* | In the approved layout plan, Wing A to D and the commercial building are mentioned. In RERA, Wing A to C are mentioned. So, Wings A to C are drafted for APF.
* | We have updated revised approved CC of Phase I (Wing B & C) on 14/02/2024.
* | Commercial Building Dimensions are not mension in the approved floor plan, so commercial building areas are not drafted.
* | As per RERA, the completion period of project Phase I (Wing B & C) & Anantam Phase II (Wing A) has expired on 31/08/2024 & 30/06/2023 but but still project is under construction.
* | Since Wing A have received CC on 23/04/2018, but as of construction work is not started.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Anantam Phase I & II
Layout Plan :
Google Map :
Formulas:
Pimpalas = [Pimpalas, row above]
Wing B & C
B & C Wing
A Wing
D Wing
Commercial Building
Wing B
Wing C
Wing B
Wing C
Wing B
Wing B
Wing C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted