## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/08/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | Kartik Enterprises
Name of the builder company |  |  |  | Kartik Enterprises
Name of the Project |  |  |  | Kartik Homes
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Jacky 8149694967
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Jacky Shamdasani 9518571220
Name / No of the Building |  |  |  | Wing A & B
Name / No of the Existing Building |  |  |  | NA | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700029229 |  |  |  | #N/A |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Kartik Homes, Survey No.74, H. No. 2, 3, near Dev Luxuria, Proposed Panvel Highway, Shirgaon, Shirgaon, Badlapur West, Ambernath, Thane - 421503. | [9 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 74, H. No. 2, 3 | [9 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Shirgaon | [9 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Proposed Panvel Highway |  | Locality/Village |  | Shirgaon | [5 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Badlapur West |  | District |  | Thane | [5 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Ambernath |  | Pin Code |  | 421503 | [8 empty] | Mahad | Daund
Nearby Landmark |  | Dev Luxuria |  | Distance from city centre: |  | 2.8 KM from Badlapur Railway Station | [8 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [10 empty] | Mangaon | Ambegaon
[15 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [10 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [10 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [10 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Not Provided |  |  | Dev Luxuria
West | NA | Not Provided |  |  | Open Plot
North | NA | Not Provided |  |  | Proposed Panvel Highway/Kartik Homes (Wing A)
South | NA | Not Provided |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.147750,73.232944
Location Link |  | https://maps.app.goo.gl/zVPfzvBktHx8n8yZ8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1610
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.633
Total FSI availaible for the project |  |  |  | 2.733
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 4400.06
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kulgoan Badlapur Municipal Council
Layout Approval No |  | KBNP/NRV/BD/1205 - 65 |  |  | Dated | 2021-02-10
Approved Floor plan No. |  | KBNP/NRV/BD/1205 - 65 |  |  | Dated | 2021-02-10
Commencement-CC No Valid Up to: |  | KBNP/NRV/BP/1205/2020-2021 Unique No.65 |  |  | Dated | 2021-02-10
Wing A - Below Ground (Sanitary Block) + Upper Ground (Driver Room and Society Office) + 1st to 7th Floor Wing B - Stilt(Pt) + 1st to 5th Floor
O. Certificate No.: |  | JVK/KBNP/NRV/2686 Approved upto : Wing A = Upper Ground (for 16 shops only) Wing B = Gr/St + 1st to 5th floor Residential Units = 26 Nos & Commercial Units = 4 Nos. |  |  | Dated | 2023-11-13
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 4400.06
Approved no of units |  |  | Flats - 84, Shops - 20
Approved no of Floors |  |  | Wing A = 1B + Gr + 1st to 7th Floor Wing B = Gr + 1st to 5th Floor
Proposed no of Floors |  |  | Wing A = 1B + Gr + 1st to 7th Floor
Wing B = Gr + 1st to 5th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 59 Years
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Decoratively designed entrance Lobby, Acrylic Paint on external Wall to both Buildings, Earthquake Resistant Structure, Good Lighting and Cross Ventilation, Staircase with Railings, Reputed brand elevators, Ample Parking Space, Fire fighting system for both Buildings, Generator Back up for lift & common Areas
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = 1B + Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 5.5 Floor, External Plaster upto 6 Floor Completed | , Internal Plaster upto 5.5 Floor, External Plaster upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 5.5 Floor, External Plaster upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 71.96% |  | 88.21% |  | Excavation in process | 3.5 | In ther Visit dtd15/08/2025 we see the labour in the visit photo but this labour is not doing the work in inside building work and so we maintian same stage as per continue.
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 5.5 | 78.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 85.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Wing B = Gr + 1st to 5th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 5 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work Completed. OC Received. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.25
Excavation |  | 5 | 100% | 100% |  | 100% |  | Excavation in process | 2.5
Plinth |  | 5 | 100% |  |  |  |  | Excavation Completed | 5
RCC (Including podiums) |  | 6 | 100% |  |  |  |  | Footing in Process | 1.25
Brickwork | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Footing Completed | 2.5
Internal Plaster | Brickwork & Internal Plaster | 5 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 5 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 100% |  |  |  |  | Plinth in process | 3.75
Possession |  | 5 | 100% |  |  |  |  | Plinth completed | 5
Possession |  | 100% |  | Disbursement % |  | 100% |  | Plinth completed | 5
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3800 |  |  | 3600 to 4000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 12800 |  |  | Shop 4 wing B as discussed 65 pc loading and from 10000 to 12800 rate rushikesh on 27/08/2024
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development & All Other Charges |  |  |  |  | 200000 |  |  | Added by rushikesh on 12/12/2023 |  | Flat No. B001 Loading 1.60
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 150000 |  |  | Shop 10 wing A as discussed 65 pc loading rushikesh on 21/09/2024
Distressed valuation of the Property |  |  |  |  | 3040
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops | Wing A | 16 |  | 1873.6895 |  | 2917.706
| Wing B | 4 |  | 828.9356 |  | 1301.965
Total |  | 20 |  | 2702.6251 |  | 4219.671
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 58 |  | 22986.9526 |  | 34603.9996 |  | 58
Wing B |  | 26 |  | 11049.8918 |  | 16713.9732
Total |  | 84 |  | 34036.8444 |  | 51317.9728 |  |  | 84
Grand Total |  | 104 |  | 36739.4695 |  | 55537.6438
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Wing A
Basement Floor For Entrance Lobby & Parking
Ground Floor For Commercial, Society Office & Driver Room | [9 empty] | 12800
1 |  | Shop | 161.6753 | 0 | 250.5967 | Ground Floor For Commercial, Society Office & Driver Room |  |  | 1.55 | 3207637.5552 | 1.55
2 |  | Shop | 163.2899 | 0 | 253.0993 |  |  | 14.875 |  | 3239671.2192
3 |  | Shop | 134.8729 | 0 | 209.053 |  |  |  |  | 2675878.7328
4 |  | Shop | 103.8726 | 0 | 161.0025 |  |  |  | 1.55 | 2060832.384 | 1.55
5 |  | Shop | 94.7232 | 0 | 146.821 |  |  |  |  | 1879308.288
6 |  | Shop | 134.8729 | 0 | 209.053 |  |  |  |  | 2675878.7328
7 |  | Shop | 134.8729 | 0 | 209.053 |  |  |  |  | 2675878.7328
8 |  | Shop | 94.7232 | 0 | 146.821 |  |  |  |  | 1879308.288
9 |  | Shop | 103.8726 | 0 | 161.0025 |  |  | 9.35 |  | 2060832.384
10 |  | Shop | 134.8729 | 0 | 222.5403 |  |  | Shop 10 wing A as discussed 65 pc loading rushikesh on 21/09/2024
11 |  | Shop | 94.7232 | 0 | 146.821 |  |  |  |  | 1879308.288
12 |  | Shop | 103.8726 | 0 | 161.0025 |  |  |  |  | 2060832.384
13 |  | Shop | 134.8729 | 0 | 209.053 |  |  |  |  | 2675878.7328
14 |  | Shop | 103.442 | 0 | 160.3352 |  |  |  |  | 2052290.0736
15 |  | Shop | 94.9385 | 0 | 147.1546 |  |  |  |  | 1883579.4432
16 |  | Shop | 80.1918 | 0 | 124.2973 |  |  | 7.15 |  | 1591005.312
Wing B
Ground Floor For Commercial, Entrance Lobby & Parking | [9 empty] | 1.55
1 |  | Shop | 219.2627 | 0 | 339.8572 | Ground Floor For Commercial, Entrance Lobby & Parking |  | 19.8 |  | 1.55
2 |  | Shop | 219.2627 | 0 | 339.8572 |  |  | 20.075 |  | 1.55
3 |  | Shop | 219.2627 | 0 | 339.8572 |  |  |  |  | 1.65
4 |  | Shop | 171.1476 | 0 | 282.3935 |  |  | Shop 4 wing B as discussed 65 pc loading and from 10000 to 12800 rate rushikesh on 27/08/2024
#VALUE!
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
[5 empty] | 50% |  |  | 10.764
Wing A
Ground Floor For Residential, Society Office, & Driver Room | [9 empty] | 3800
1 |  | 1RK | 253.0616 | 0 | 379.5925 | Ground Floor For Residential, Society Office, & Driver Room |  | 19.785 |  | 1442451.348
2 |  | 1BHK | 419.5807 | 0 | 629.3711 |  |  | 35.12 |  | 2391610.104
1st Floor For Residential | [9 empty] | 0
1 |  | 1RK | 253.0616 | 0 | 379.5925 | 1st Floor For Residential |  |  |  | 1442451.348 | t
2 |  | 1BHK | 391.0561 | 152.4182 | 662.7933 |  |  | 29.4975 | 5.6 | 2518614.54 | 13.63
3 |  | 1BHK | 405.8028 | 0 | 608.7042 |  |  |  |  | 2313075.96
4 |  | 1BHK | 405.8028 | 0 | 608.7042 |  |  |  |  | 2313075.96
5 |  | 1BHK | 405.8028 | 0 | 608.7042 |  |  |  |  | 2313075.96
6 |  | 2BHK | 538.8458 | 47.3616 | 855.6304 |  |  | 37.0025 | 8 | 3251395.368 | 4.4
7 |  | 1BHK | 367.8059 | 0 | 551.7088 |  |  |  |  | 2096493.516
8 |  | 1BHK | 419.5807 | 0 | 629.3711 |  |  |  |  | 2391610.104
2nd to 7th Floor | [9 empty] | 0
1 |  | 1RK | 253.0616 | 0 | 379.5925 | 2nd to 7th Floor |  |  |  | 1442451.348
2 |  | 1BHK | 391.0561 | 0 | 586.5842 |  |  |  |  | 2229019.884
3 |  | 1BHK | 405.8028 | 0 | 608.7042 |  |  |  |  | 2313075.96
4 |  | 1BHK | 405.8028 | 0 | 608.7042 |  |  |  |  | 2313075.96
5 |  | 1BHK | 405.8028 | 0 | 608.7042 |  |  |  |  | 2313075.96
6 |  | 2BHK | 538.8458 | 0 | 808.2688 |  |  |  |  | 3071421.288
7 |  | 1BHK | 367.8059 | 0 | 551.7088 |  |  |  |  | 2096493.516
8 |  | 1BHK | 419.5807 | 0 | 629.3711 |  |  |  |  | 2391610.104
Wing B
Ground Floor For Residential, Entrance Lobby & Parking
1 |  | 1RK | 258.9818 | 0 | 414.3709 | Ground Floor For Residential, Entrance Lobby & Parking |  | 23.1925
1st Floor
1 |  | 1BHK | 439.817 | 56.6186 | 716.3442 | 1st Floor |  |  |  |  | 5.225
2 |  | 1BHK | 439.817 | 56.6186 | 716.3442
3 |  | 1BHK | 405.5875 | 0 | 608.3813
4 |  | 1BHK | 439.7094 | 0 | 659.5641
5 |  | 1BHK | 433.251 | 0 | 649.8765
2nd to 5th Floor
1 |  | 1BHK | 439.817 | 0 | 659.7256 | 2nd to 5th Floor
2 |  | 1BHK | 439.817 | 0 | 659.7256
3 |  | 1BHK | 405.5875 | 0 | 608.3813
4 |  | 1BHK | 439.7094 | 0 | 659.5641
5 |  | 1BHK | 433.251 | 0 | 649.8765
Remarks:
* | Wing A = OC receievd upto upper ground floor only. Construction work was stopped. Work is same as last visit (dtd.25/11/2024). Wing B = All Work completed. OC received.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Otla + Balcony
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates/Other Charges of the Property have been revised on 12/12/2023 & for shop 27/08/2024.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | We have updated OC from Rera (On 22/11/2024).
* | As per RERA, completion period of project Kartik Homes is expired on 31/12/2024 but still project is under construction.
* | Since the project has received first CC on 10/02/2021., But construction work of Wing A is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Kartik Homes
Layout :
Google Map :
Formulas:
Shirgaon = [Shirgaon, row above]
Wing B
Wing A
Wing B
Wing A
Wing B
Wing A
Wing B
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC