## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | M/s.Rohan Developers Pvt Ltd
Name of the builder company |  |  |  | M/s.Rohan Developers Pvt Ltd
Name of the Project |  |  |  | Lifescapes Shubham
Contact Details ( Name & Contact No.) |  |  |  | 9167209944
Name / No of the Building |  |  |  | Building No.02 (Sale)
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | P51900002696
Project location details |  | Lifescapes Shubham, Redevelopment on plot bearing C.S. No.585, 588 & 589 of Girgaon division, situated at V.P. Road, Girgaon, Mumbai-400004
CTS No |  | 585,588 & 589
Road |  | V.P. Road |  | Locality/Village |  | Girgaon
City |  | Charni Road |  | District |  | Mumbai
Taluka |  | Mumbai |  | Pin Code |  | 400004
Nearby Landmark |  | Alaknanda Society |  | Distance from city centre: |  | 1.5km from Charni Road Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Building
West | NA | NA |  |  | Building
North | NA | NA |  |  | Kalpana building
South | NA | NA |  |  | V.P. Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 18.9569 |  | Longitude |  | 72.8219
Location Link |  | https://goo.gl/maps/191Ni5Ws4bQ2KvMB6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 5133.08
Permissible FSI |  |  |  | 4.72
Permissible TDR/Paid FSI |  |  |  | 1.3431
Total FSI availaible for the project |  |  |  | 6.0631
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 31122.15
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Layout Approval No |  | CHE/CITY/1015/D/337 (NEW) |  |  | Dated | 2022-01-14
Approved Floor plan No. |  | CHE/CITY/1015/D/337 (NEW) |  |  | Dated | 2022-01-14
Commencement Certificate No. |  | CHE/CTY/1015/D/337(NEW)/FCC/5/Amend |  |  | Dated | 2024-03-04
|  | Valid Up to: This CC is extended upto top of 28th floor + LMR + OHT i.e. Full CC as per amended approved plans dated 14.01.2022. |  |  | Valid Upto Date | 2024-10-13
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 31122.15
Approved no of units |  |  | Flats - 154
Approved no of Floors |  |  | 1B + G/St + P1 to P4 + 1st to 28th Floor
Proposed no of Floors |  |  | 1B + G/St + P1 to P4 + 1st to 28th Floor
Expected Completion |  |  | As per RERA - 31/05/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: |  | 1B + G/St + P1 to P4 + 1st to 28th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 26 Floor, Painting upto 23 Floor, Finishing upto 5 Floor Completed
Basement | 1 | Ground | 1 | Podium | 4 | Floors | 28
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 26 Floor, Painting upto 23 Floor, Finishing upto 5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% | 89.29% |  | 94.64% |  | Excavation in process | 14
Plinth |  | 28 | 100% |  |  |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 33 | 100% |  |  |  |  | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 28 | 100% |  |  |  |  | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 28 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 28 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 26 | 92.86% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 23 | 82.14% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 17.86% |  |  |  |  | Plinth in process | 21
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 28
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA | [7 empty] | 25.74
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 29000
Recommended rate of the shop Per Sq. Ft. ( on Saleable area)
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 8,00,000/-
Distressed valuation of the Property |  |  |  |  | 23200
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flat |  | 154 |  | 149929.0585 |  | 224920.6916
Total |  | 154 |  | 149929.0585 |  | 224920.6916
Grand Total |  | 154 |  | 149929.0585 |  | 224920.6916
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Open Balcony + Dry Balcony | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Building No.2 (Sale Building)
Basement For Parking & Pump Room | [8 empty] | 10.764
Ground Floor For Sub Station, Meter Room & Parking
1st to 4th Podium For Parking
1st Floor For Residential | [7 empty] | 1
1 |  | 3BHK | 1110.3066 | 75.7409 | 1186.0475 | 16.4043 | 1795.4756 | 98.0243
2 |  | 3BHK | 1123.0081 | 76.6451 | 1199.6532 | 10.6994 | 1810.1792 |  | 154
3 |  | 2BHK | 836.901 | 49.7286 | 886.6296 | 0 | 1329.9444 | 75.1855
4 |  | 2BHK | 840.9913 | 23.8466 | 864.8379 | 0 | 1297.2568
5 |  | 2BHK | 807.7306 | 22.9209 | 830.6514 | 0 | 1245.9771
6 |  | 2BHK | 843.467 | 22.627 | 866.094 | 0 | 1299.1411
2nd, 4th to 9th, 11th to 16th, 18th to 23rd, 25th to 27th Floor | [7 empty] | 22
1 |  | 3BHK | 1110.3066 | 75.7409 | 1186.0475 | 0 | 1779.0712 | 98.0243
2 |  | 3BHK | 1123.0081 | 50.763 | 1173.7711 | 0 | 1760.6567
3 |  | 2BHK | 836.901 | 23.8466 | 860.7476 | 0 | 1291.1213 | 75.1855
4 |  | 2BHK | 840.9913 | 23.8466 | 864.8379 | 0 | 1297.2568
5 |  | 2BHK | 807.7306 | 22.9209 | 830.6514 | 0 | 1245.9771
6 |  | 2BHK | 843.467 | 22.627 | 866.094 | 0 | 1299.1411
3rd, 10th, 17th & 24th Floor (Refuge Area At Midlanding) | [7 empty] | 4
1 |  | 3BHK | 1110.3066 | 75.7409 | 1186.0475 | 0 | 1779.0712 | 98.0243
2 |  | 3BHK | 1123.0081 | 50.763 | 1173.7711 | 0 | 1760.6567
3 |  | 2BHK | 904.6066 | 23.8466 | 928.4531 | 0 | 1392.6797 | 81.4894
- |  | Refuge Area | [5 empty] | 81.4894
- | [7 empty] | 81.4894
4 |  | 2BHK | 911.065 | 22.627 | 933.692 | 0 | 1400.5379
28th Floor for Yogalay and part Terrace | [7 empty] | 4
Remarks:
1 | Construction work is in process at the time of Visit. Internal photographs was not allowed.
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Open Balcony + Dry Balcony.
5 | We have considered rate by verifying it from market inquire.
6 | Car parking is subjected to authentic documentation.
7 | We have updated Revised approved plan & CC (15/02/2025).
8 | We have considered proposed No. of Floor for Stage Calculation.
9 | As per RERA, completion period of project Lifescapes Shubham is expired on 31/05/2025 but still project is under construction
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Karan Misal |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Lifescapes Shubham
Layout :
Google Map :
Formulas:
Girgaon = [Girgaon, row above]
Building No.2 (Sale)
Note on H97: SACHIN: Give loading of 50% for A Category

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  | 3BHK | 1106 | 1769.6 | 31532.5497 | 55800000
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted