## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/08/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | Samruddhi Builders & Developers
Name of the builder company |  |  |  | Samruddhi Builders & Developers
Name of the Project |  |  |  | Om Moreshwar
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Om Deshmukh 9326386514 Mr. Santosh 8087390139
Site Person - Contact Details (Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | 01 Building
Name / No of the Existing Building |  |  |  | Om Aarti Co Op Housing Society | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700052478 |  |  |  | #N/A |  |  |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Om Moreshwar, Survey No.23, Hissa No.1(Pt), Plot No. 6 & 7, Existing Building Name - Om Aarti Co op Housing Society., near Akashganga Complex, Internal Road, , Shirgaon, Badlapur , Ambernath, Thane - 421503. | [9 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 23, Hissa No.1(Pt), Plot No. 6 & 7, Existing Building Name - Om Aarti Co op Housing Society. | [9 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | NA | [9 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Shirgaon | [5 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Badlapur |  | District |  | Thane | [5 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Ambernath |  | Pin Code |  | 421503 | [8 empty] | Mahad | Daund
Nearby Landmark |  | Akashganga Complex |  | Distance from city centre: |  | 2 KM from Badlapur Railway Station | [8 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [10 empty] | Mangaon | Ambegaon
[15 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [10 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [10 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [10 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | 15.00 M Road |  |  | Road/Nav Rushikesh Building
West | NA | Other Plot |  |  | Akashganga Complex
North | NA | 15.00 M.W.D.P |  |  | Internal Road
South | NA | Other Plot |  |  | Moreshwar Apartment
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.160550,73.230070
Location Link |  | https://maps.app.goo.gl/WZNr552N6R5EebHeA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 724.07
Permissible FSI |  |  |  | 1.6
Permissible TDR/Paid FSI |  |  |  | 1.9269
Total FSI availaible for the project |  |  |  | 3.5269
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 2553.7
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kulgoan Badlapur Municipal Council
Layout Approval No |  | KBNP/NRV/BP/171-163 |  |  | Dated | 2023-02-01
Approved Floor plan No. |  | KBNP/NRV/BP/171-163 |  |  | Dated | 2023-02-01
Commencement-CC No Valid Up to: |  | KBNP/NRV/BP/2022-2023/171/Uuique No. 163 |  |  | Dated | 2023-02-01
1B + Gr + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 2553.7
Approved no of units |  |  | Flats - 36, Shops - 13, Offices - 8, Storages - 4
Approved no of Floors |  |  | 1B + Gr + 1st to 7th Floor
Proposed no of Floors |  |  | 1B + Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Meter Room, Vitrified Tiles, Modular Kitchen
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | 1B + Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 4 Floor, Finishing upto 3 Floor Completed | , Painting upto 4 Floor, Finishing upto 3 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 4 Floor, Finishing upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 90% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 57.14% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 42.86% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | #REF! | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | 20 | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | 0 | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Construction details: |  | #REF! | [5 empty] | #REF! | #REF!
Basement | 0 | Ground | 1 | Podium | 0 | Floors | #REF! | #REF! | #REF!
Stage of construction: |  | #REF! | [5 empty] | #REF! | #REF!
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | #REF!
Excavation |  | #REF! | #REF! | #REF! |  | #REF! |  | Excavation in process | #REF!
Plinth |  | #REF! | #REF! |  |  |  |  | Excavation Completed | #REF!
RCC (Including podiums) |  | #REF! | #REF! |  |  |  |  | Footing in Process | #REF!
Brickwork | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Footing Completed | #REF!
Internal Plaster | Brickwork & Internal Plaster | 0 | #REF! |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | #REF! |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | #REF! |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | #REF! |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | #REF! |  |  |  |  | Plinth in process | #REF!
Possession |  | 0 | #REF! |  |  |  |  | Plinth completed | #REF!
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4700 |  |  | 4500 to 4700 | Bhargav | 2025-05-22
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 12000
Recommended rate of the Storages Per Sq. Ft. (Basement Floor) |  |  |  |  | 8000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 10000
Floor Rise Rate from Floor
Development Charges
Club Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 3760
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  | Housing
Storages |  | 4 |  | 1034.0975 |  | 1551.1462 |  | 4482.6957
Shops |  | 13 |  | 1487.6924 |  | 2231.5387 |  | 4416.1877
Offices |  | 8 |  | 2791.8587 |  | 4187.788 |  | 4449.4417
Total |  | 25 |  | 5313.6486 |  | 7970.4729
Residential Area Details : | [7 empty] | https://housing.com/in/buy/projects/page/306526-samruddhi-om-moreshwar-by-samruddhi-builders-and-developers-in-badlapur-west
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 36 |  | 18902.6066 |  | 27408.7795
Grand Total |  | 61 |  | 24216.2552 |  | 35379.2524
Building details Floor Wise | [7 empty] | We have received the builder area sheet for rehab sale tenants, but we have not considered them.
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Basement Floor for Commercial & Parking
1 |  | Storage | 198.2729 | 0 | 198.2729 | 0 | 297.4093 | 18.2875 |  |  | 5858.5925
2 |  | Storage | 198.2729 | 0 | 198.2729 | 0 | 297.4093 | 18.2875 |  |  | 5858.5925
3 |  | Storage | 103.0115 | 0 | 103.0115 | 0 | 154.5172 | 9.5625 |  |  | 5866.0129
4 |  | Storage | 534.5402 | 0 | 534.5402 | 0 | 801.8104 | 49.5225 |  |  | 5860.7374
Ground Floor for Society Office, Entrance Lobby & Driver Room | [10 empty] | 5860.9838
1 |  | Shop | 81.6988 | 0 | 81.6988 | 0 | 122.5481 |  |  |  | 17129.5949
2 |  | Shop | 118.404 | 0 | 118.404 | 0 | 177.606 |  |  |  | 17539.948
3 |  | Shop | 130.2444 | 0 | 130.2444 | 0 | 195.3666 | 10.764 |  |  | 18099.3066
4 |  | Shop | 130.2444 | 0 | 130.2444 | 0 | 195.3666 |  |  |  | 18631.6392
5 |  | Shop | 99.1364 | 0 | 99.1364 | 0 | 148.7047 |  |  |  | 19173.5753
6 |  | Shop | 101.8274 | 0 | 101.8274 | 0 | 152.7412 |  |  |  | 19766.7741
7 |  | Shop | 130.2444 | 0 | 130.2444 | 0 | 195.3666 |  |  |  | 20228.6368
8 |  | Shop | 130.2444 | 0 | 130.2444 | 0 | 195.3666 |  |  |  | 18652.7821
9 |  | Shop | 74.164 | 0 | 74.164 | 0 | 111.2459
10 |  | Shop | 124.3242 | 0 | 124.3242 | 0 | 186.4863
11 |  | Shop | 124.3242 | 0 | 124.3242 | 0 | 186.4863
12 |  | Shop | 121.4179 | 0 | 121.4179 | 0 | 182.1269
13 |  | Shop | 121.4179 | 0 | 121.4179 | 0 | 182.1269
1st Floor
1 |  | Office | 443.6921 | 0 | 443.6921 | 0 | 665.5381
2 |  | Office | 475.4459 | 0 | 475.4459 | 0 | 713.1688
3 |  | Office | 273.9438 | 0 | 273.9438 | 0 | 410.9157 | 10.764 | 10707.7924 | as per Builder Sheet
4 |  | Office | 246.6032 | 0 | 246.6032 | 0 | 369.9049 |  | 10813.5914 | 405 | sale
5 |  | Office | 270.0688 | 0 | 270.0688 | 0 | 405.1031 |  | 10760.6919 | 602 | sale
6 |  | Office | 244.4504 | 0 | 244.4504 | 0 | 366.6757 |  |  | 604 to 606 | sale
7 |  | Office | 370.0663 | 0 | 370.0663 | 0 | 555.0995 |  |  | 701 to 706 | sale
8 |  | Office | 467.5882 | 0 | 467.5882 | 0 | 701.3822
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | AP Area/CP Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
2nd to 7th Floor for Residential
1 |  | 1BHK | 377.4935 | 53.2818 | 430.7753 | 0 | 624.6242 | 33.195 | 5031.6258
2 |  | 2BHK | 497.0815 | 87.1884 | 584.2699 | 0 | 847.1914 |  | 4975.4401
3 |  | 2BHK | 496.328 | 87.1884 | 583.5164 | 0 | 846.0988 |  | 4955.6444
4 |  | 1BHK | 350.0453 | 52.7974 | 402.8427 | 0 | 584.1219 |  | 5064.0113
5 |  | 2BHK | 522.5922 | 55.2193 | 577.8115 | 0 | 837.8267 |  | 5075.1844
6 |  | 2BHK | 496.5433 | 74.6752 | 571.2186 | 0 | 828.2669 |  | 4928.4112
Remarks: | [8 empty] | 5005.0529
* | Construction work is in process at the time of Visit (Labour found).
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + AP Area + C.P Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Recommended Rates / Other charges of the Property have been revised on 22/05/2025.
* | Please check for Environment Clearance Certificate.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Om Moreshwar
Layout :
Google Map :
Formulas:
Shirgaon = [Shirgaon, row above]
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC