## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 14/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-12
Name of the builder group |  |  |  |  | M/s. Regency Inc
Name of the builder company |  |  |  |  | M/s. Regency Inc
Name of the Project |  |  |  |  | Regency Palms Phase I, II & IV
Contect Details ( Name & Contect No.) |  |  |  |  | 02512560003
Site Person - Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Praveen 9324149916/7276606600
Name / No of the Building |  |  |  |  | Regency Palms Phase I = Tower A Regency Palms Phase II = Tower B Regency Palms Phase IV = Tower C & D
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | Regency Palms Phase I = P52000021209 Regency Palms Phase II = P52000021191 Regency Palms Phase IV = P51700046381
Project location details |  | Regency Palms Phase I, II & IV, Plot No.R/3A, Sector.14, Shankarnarayan Marg, Nerul, Navi Mumbai, Thane, Thane.
Plot No |  | R/3A |  |  | Sector |  | 14
Road |  | Shankarnarayan Marg |  |  | Locality/Village |  | Nerul
City |  | Navi Mumbai |  |  | District |  | Thane
Taluka |  | Thane |  |  | Pin Code |  | 400706
Near by Landmark |  | Emerald Bay Society |  |  | Distance from city centre: |  | About 1.7Km from Nerul Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Palm Beach Road |  | Road |  | Road |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.039711, 73.008839
Location Link |  | https://goo.gl/maps/vutrRpg7fuBBknSEA
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 16776.9
Permissible FSI |  |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1.5
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 46157.717
Total number of Buildings |  |  |  |  | 4 Buildings
Approval Detail : Plan approval
Layout Approval No |  | NRV/A-1349 |  |  |  | Dated | 2022-05-02
Approved Floor plan No. |  | NRV/A-1349 |  |  |  | Dated | 2022-05-02
Commencement Certificate No. |  | NMMC/TPO/B.P/1341/2022 Valid up to: Tower A & B = G + Podium 1 + Podium 2 + 1st to 28th Floor Tower C & D = Basement + Stilt/G + Podium 1 + Podium 2 + 1st to 34th Floor |  |  |  | Dated | 2022-05-02
O. Certificate No.: |  | NMMCC/PO/2025/APL/00013 Approved upto : Tower B = Gr/St + 1st to 31st Floor |  |  | Date of approval: | Dated | 2025-02-20 | NA |  |  | Tower B OC provided by bank officials on Whatsapp
Commencement date of construction |  |  | 2022-05-02 |  | Expected Completion |  | As per RERA : Phase I & II : Completed Phase IV : 31/05/2026
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 46157.717 |  | Approved no of units |  | Flats = 208 Shop = 18
Approved no of Floors |  | Tower A & B = Gr/St + P1 to P2 + 1st to 29th Floor Tower C & D = Basement + Stilt/G + Podium 1 + Podium 2 + 1st to 34th Floor | [7 empty] | For Tower B 29th floor not drafted
Proposed no of Floors |  | Tower A & B = Gr/St + P1 to P2 + 1st to 29th Floor Tower C & D = Basement + Stilt/G + Podium 1 + Podium 2 + 1st to 34th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Bricks, Cement & Steel etc.
Construction details: |  | Tower A = Gr/St + P1 to P2 + 1st to 29th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 32 Slab completed, Brickwork upto 29 Floor completed, Internal Plaster upto 29 Floor completed, External Plaster upto 29 Floor completed, Flooring upto 29 Floor completed, Painting upto 29 Floor completed, Finishing upto 29 Floor completed
Basement | 0 | Ground | 1 | Podium | 2 |  | Floors | 29 | All work Completed. Provide OC.
Stage of construction: |  | All work Completed. Provide OC. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 7.25
Excavation |  | 29 | 100% |  | 100% |  | 100% |  | Excavation in process |  | 14.5
Plinth |  | 29 | 100% | [5 empty] | Excavation Completed |  | 29
RCC (Including podiums) |  | 32 | 100% | [5 empty] | Footing in Process |  | 7.25
Brickwork | Brickwork & Internal Plaster | 29 | 100% | [5 empty] | Footing Completed |  | 14.5
Internal Plaster | Brickwork & Internal Plaster | 29 | 100% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 29 | 100% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 29 | 100% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 29 | 100% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 29 | 100% | [5 empty] | Plinth in process |  | 21.75
Possession |  | 29 | 100% | [5 empty] | Plinth completed |  | 29
Construction details: |  | Tower B = Gr/St + P1 to P2 + 1st to 29th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 32 Slab completed, Brickwork upto 29 Floor completed, Internal Plaster upto 29 Floor completed, External Plaster upto 29 Floor completed, Flooring upto 29 Floor completed, Painting upto 29 Floor completed, Finishing upto 29 Floor completed
Basement | 0 | Ground | 1 | Podium | 2 |  | Floors | 29 | All work Completed. Provide OC.
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  |  | 100%
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 7.25
Excavation |  | 29 | 100% |  | 100% |  | 100% |  | Excavation in process |  | 14.5
Plinth |  | 29 | 100% | [5 empty] | Excavation Completed |  | 29
RCC (Including podiums) |  | 32 | 100% | [5 empty] | Footing in Process |  | 7.25
Brickwork | Brickwork & Internal Plaster | 29 | 100% | [5 empty] | Footing Completed |  | 14.5
Internal Plaster | Brickwork & Internal Plaster | 29 | 100% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 29 | 100% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 29 | 100% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 29 | 100% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 29 | 100% | [5 empty] | Plinth in process |  | 21.75
Possession |  | 29 | 100% | [5 empty] | Plinth completed |  | 29
Construction details: |  | Tower C = Basement + Stilt/G + Podium 1 + Podium 2 + 1st to 34th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 36 Slab completed, Brickwork upto 33 Floor completed, Internal Plaster upto 29.7 Floor completed, External Plaster upto 28.05 Floor completed
Basement | 0 | Ground | 1 | Podium | 2 |  | Floors | 34 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 36 Slab completed, Brickwork upto 33 Floor completed, Internal Plaster upto 29.7 Floor completed, External Plaster upto 28.05 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 8.5
Excavation |  | 34 | 100% |  | 71% |  | 87.53% |  | Excavation in process |  | 17
Plinth |  | 34 | 100% | [5 empty] | Excavation Completed |  | 34
RCC (Including podiums) |  | 36 | 97.3% | [5 empty] | Footing in Process |  | 8.5
Brickwork | Brickwork & Internal Plaster | 33 | 97.06% | [5 empty] | Footing Completed |  | 17
Internal Plaster | Brickwork & Internal Plaster | 29.7 | 87.35% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 28.05 | 82.5% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 25.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 34
Construction details: |  | Tower D = Basement + Stilt/G + Podium 1 + Podium 2 + 1st to 34th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 37 Slab completed, Brickwork upto 34 Floor completed, Internal Plaster upto 30.6 Floor completed, External Plaster upto 28.9 Floor completed
Basement | 0 | Ground | 1 | Podium | 2 |  | Floors | 34 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 37 Slab completed, Brickwork upto 34 Floor completed, Internal Plaster upto 30.6 Floor completed, External Plaster upto 28.9 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process |  | 8.5
Excavation |  | 34 | 100% |  | 72.75% |  | 88.75% |  | Excavation in process |  | 17
Plinth |  | 34 | 100% | [5 empty] | Excavation Completed |  | 34
RCC (Including podiums) |  | 37 | 100% | [5 empty] | Footing in Process |  | 8.5
Brickwork | Brickwork & Internal Plaster | 34 | 100% | [5 empty] | Footing Completed |  | 17
Internal Plaster | Brickwork & Internal Plaster | 30.6 | 90% | [5 empty] | Basement 1 |  | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 28.9 | 85% | [5 empty] | Basement 2 |  | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 |  | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 |  | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process |  | 25.5
Possession |  | 0 | 0% | [5 empty] | Plinth completed |  | 34
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) For Tower A & B | [5 empty] | 25000 |  |  | Rate for OC Received bldg 25K & for other bldg 23K & Par 8L By smith Verbally On 09/06/2025
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) For Tower C & D | [5 empty] | 23000
Recommended rate of the Office Per Sq. Ft. ( on Saleable area) | [5 empty] | 30000
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 35000
Recommended rate of Parking | [5 empty] | 800000
Distressed valuation of the Property | [5 empty] | 20000
Commercial Area Details :
Building & Wing |  | No. of Units | Total Carpet Area |  |  | Total Saleable Area
Tower C Shop |  | 8 | 6372.1804 |  |  | 10195.4886
Tower D Shop |  | 10 | 13732.4959 |  |  | 21971.9935
Total |  | 18 | 20104.6763 |  |  | 32167.482
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
Tower A |  | 53 | 159074.8845 |  |  | 238612.3267
Tower B |  | 53 | 162354.8428 |  |  | 243532.2642
Tower C |  | 34 | 113948.9332 |  |  | 170923.3999
Tower D |  | 68 | 92515.073 |  |  | 138772.6096
Total |  | 208 | 527893.7336 |  |  | 791840.6004
Building details Floor Wise
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Tower A
Ground Floor is For Parking
1st Floor is For Podium Double height
2nd Floor is For Podium (Part Amenities)
1st to 3rd, 5th to 7th, 9th to 11th, 13th to 15th Floor
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | 1st to 3rd, 5th to 7th, 9th to 11th, 13th to 15th Floor |  |  | 23320.3479
2 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007
4th, 8th, 12th & 16th Floor (Refuge Area at Mid landing)
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | 4th, 8th, 12th & 16th Floor (Refuge Area at Mid landing) | 4th, 8th, 12th & 16th Floor (Refuge Area at Mid landing)
2 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | N
17th Floor
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | 17th Floor | 6th, 10th, 14th, 18th, 22nd & 26th Floor
2 |  | 8BHK Duplex with 18th floor | 5653.5149 |  | 0 | 8480.2724 | N
18th Floor
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | N | 6th, 10th, 14th, 18th, 22nd & 26th Floor
2 |  | 8BHK Duplex with 17th floor
19th, 21st, 22nd, 23rd, 25th & 26th Floor
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | 19th, 21st, 22nd, 23rd, 25th & 26th Floor | 19th, 21st, 22nd, 23rd, 25th & 26th Floor |  | 23320.3479
2 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | N | [5 empty] | 5717.4676
20th & 24th Floor (Refuge Area at Mid landing) | [12 empty] | 11434.9352
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | 20th & 24th Floor (Refuge Area at Mid landing)
2 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007
27th Floor (Pent House)
1 |  | 3BHK Duplex with 28th Floor | 5348.6202 |  | 294.9487 | 8022.9303 | 27th Floor (Pent House)
2 |  | 2BHK Duplex with 28th Floor | 5136.0595 |  | 805.793 | 7704.0892
28th Floor (Pent House)
1 |  | 3BHK Duplex with 27th Floor | [5 empty] | 28th Floor (Pent House)
2 |  | 3BHK Duplex with 27th Floor
Tower B
Ground Floor is For Parking
1st Floor is For Podium Double height
2nd Floor is For Podium (Part Amenities)
1st to 3rd, 5th to 7th, 9th to 11th, 13th to 15th & 17th Floor
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | 1st to 3rd, 5th to 7th, 9th to 11th, 13th to 15th & 17th Floor | 1st to 3rd, 5th to 7th, 9th to 11th, 13th to 15th & 17th Floor
2 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | N
4th, 8th, 12th & 16th Floor
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | 4th, 8th, 12th & 16th Floor | 4th, 8th, 12th & 16th Floor
2 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | N
18th Floor
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | 18th Floor | 18th Floor
2 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | N
19th, 21st, 22nd, 23rd, 25th & 26th Floor
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | 19th, 21st, 22nd, 23rd, 25th & 26th Floor | 19th, 21st, 22nd, 23rd, 25th & 26th Floor |  | 23320.3479 |  | 52
2 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | N
20th & 24th Floor (Refuge Area at Mid landing)
1 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007 | 20th & 24th Floor (Refuge Area at Mid landing)
2 |  | 4BHK | 2858.7338 |  | 0 | 4288.1007
27th + 28th Floor (Duplex Pent House)
1 |  | 7BHK | 13700.6854 |  | 1100.7417 | 20551.028 | 27th + 28th Floor (Duplex Pent House)
Tower C
Basement Floor is For Parking
Ground Floor is For Parking & commercial
11 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724 | Ground Floor is For Parking & commercial
12 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724
13 |  | Shop | 608.9733 |  | 0 | 974.3573
14 |  | Shop | 608.9733 |  | 0 | 974.3573
15 |  | Shop | 608.9733 |  | 0 | 974.3573
16 |  | Shop | 608.9733 |  | 0 | 974.3573
17 |  | Shop | 608.9733 |  | 0 | 974.3573
18 |  | Shop | 608.9733 |  | 0 | 974.3573
1st podium/ 1st residential Floor is For commercial
2nd podium/ 2nd residential Floor is For Amenities
1st to 3rd, 5th, 6th, 7th, 9th, 10th, 11th, 13th, 14th, 15th, 17th, 18th, 19th, 21st, 22nd, 23rd, 25th, 26th, 27th, 29th, 30th, 31st to 33rd & 34th Floor
1 |  | 4BHK | 3351.4392 |  | 0 | 5027.1588 | 1st to 3rd, 5th, 6th, 7th, 9th, 10th, 11th, 13th, 14th, 15th, 17th, 18th, 19th, 21st, 22nd, 23rd, 25th, 26th, 27th, 29th, 30th, 31st to 33rd & 34th Floor
4th, 8th, 12th, 16th, 20th, 24th, 28th & 32nd Floor (Refuge at midlanding)
1 |  | 4BHK | 3351.4392 |  | 0 | 5027.1588 | 4th, 8th, 12th, 16th, 20th, 24th, 28th & 32nd Floor (Refuge at midlanding)
Tower D
Basement Floor is For Parking
Ground Floor is For Parking & commercial
1 |  | Shop Duplex with 1st Floor | 1499.9634 |  | 0 | 2399.9414 | Ground Floor is For Parking & commercial
2 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724
3 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724
4 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724
5 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724
6 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724
7 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724
8 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724
9 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724
10 |  | Shop Duplex with 1st Floor | 1359.1703 |  | 0 | 2174.6724
1st podium/ 1st residential Floor is For commercial
2nd podium/ 2nd residential Floor is For Amenities
3rd Floor For Community Hall & Part Terrace
1st to 3rd, 5th, 6th, 7th, 9th, 10th, 11th, 13th, 14th, 15th, 17th, 18th, 19th, 21st, 22nd, 23rd, 25th, 26th, 27th, 29th, 30th, 31st to 33rd & 34th Floor
1 |  | 3BHK | 1360.5158 |  | 0 | 2040.7737 | 1st to 3rd, 5th, 6th, 7th, 9th, 10th, 11th, 13th, 14th, 15th, 17th, 18th, 19th, 21st, 22nd, 23rd, 25th, 26th, 27th, 29th, 30th, 31st to 33rd & 34th Floor
2 |  | 3BHK | 1360.5158 |  | 0 | 2040.7737
4th, 8th, 12th, 16th, 20th, 24th, 28th, 32nd Floor (Refuge at midlanding)
1 |  | 3BHK | 1360.5158 |  | 0 | 2040.7737 | 4th, 8th, 12th, 16th, 20th, 24th, 28th, 32nd Floor (Refuge at midlanding) | 4th, 8th, 12th, 16th, 20th, 24th, 28th, 32nd Floor (Refuge at midlanding)
2 |  | 3BHK | 1360.5158 |  | 0 | 2040.7737 | N
Remarks: | [9 empty] | Check OC OF WING A on RERA not signed verified on check on 14/08/2025
1. Phase I (Wing A) = All work completed. Please provide OC. Phase II (Wing B) = All work Completed. OC Received. Phase IV (Wing C & D) = Construction work was in process at the time of visit. (Internal Visit Not Allowed). 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area + F.B Area. 5. We considered rate as per Market Inquire. 6. Car parking is subjected to authentic documentation. 7. We have updated revised approved floor plan & C.C (on 15/05/2023). 8. We have updated OC for Tower B (On 09/06/2025). 9. Recommended Rates & Other charges of the Property have been revised on 09/06/2025. 7. On site, we meet Mr.Pravin (Sales) - 9324149916.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Anish Vishwakarma |  | Report Prepared By : |  |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Regency Palms Phase I, II & IV
Layout
Google Map :
Formulas:
Nerul = [Nerul, row above]
A Wing
D Wing
B Wing
C Wing
A Wing
B Wing
D Wing
A Wing
B Wing
C Wing
D Wing

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
99 Acres | Regency Palms | 4BHK | 0 | 3750 | 26666.6667 | 100000000
Magic Brick | Regency Palms |  |  | 0 | #DIV/0!
Magic Brick | Regency Palms |  |  | 0 | #DIV/0!
Magic Brick | Regency Palms |  |  | 0 | #DIV/0!
Magic Brick | Regency Palms |  |  | 0 | #DIV/0!
99 Acres | Regency Palms |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## C%
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 28
Particulars | total floor | 28
plinth | 10 | 10 | 100%
slab | 29 | 18 | 62.07% |  | Parking |  | Rate
Bricks | 28 | 17 | 60.71% |  | Palghar |  | 100000/-
plaster | 28 | 8.5 | 30.36% |  | Ulwe, karanjade |  | 200000/-
Flooring | 28 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 28 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 28 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 24.8276 | 9.1071 | 3.0357 | 0 | 0 | 0
RCC | 24.8276 | 18.6207 |  | Recommended |  | 30 | 18.6207 | 9.1071 | 3.0357 | 0 | 0 | 0
Bricks | 9.1071 | 9.1071
Plaster | 3.0357 | 3.0357
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 46.97% | 60.76% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## C% (2)
Basement | Podium | Ground | Upper Floor
0 | 0 | 1 | 28
Particulars | total floor | 28
plinth | 10 | 10 | 100%
slab | 29 | 9 | 31.03% |  | Parking |  | Rate
Bricks | 28 | 8 | 28.57% |  | Palghar |  | 100000/-
plaster | 28 | 4 | 14.29% |  | Ulwe, karanjade |  | 200000/-
Flooring | 28 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 28 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 28 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 12.4138 | 4.2857 | 1.4286 | 0 | 0 | 0
RCC | 12.4138 | 9.3103 |  | Recommended |  | 30 | 9.3103 | 4.2857 | 1.4286 | 0 | 0 | 0
Bricks | 4.2857 | 4.2857
Plaster | 1.4286 | 1.4286
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 28.13% | 45.02% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 5.81 | 8.25 | 47.9325 | CB | 3 | 0.6 | 1.8 |  |  | 0
|  | 4.66 | 3 | 13.98 | FB | 1 | 6.216 | 6.216 |  |  | 0
| Bal | 5.71 | 1.5 | 8.565 |  |  |  | 0 |  |  | 0
| kitch | 3.65 | 1.82 | 6.643 | CB | 2.28 | 0.6 | 1.368 |  |  | 0
|  | 3.05 | 2.43 | 7.4115 | FB |  |  | 0 |  |  | 0
| Bal | 3.88 | 1.5 | 5.82 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.28 | 3.3 | 10.824 | CB | 3 | 0.6 | 1.8 |  |  | 0
|  | 3.8 | 1.57 | 5.966 | FB |  |  | 0 |  |  | 0
| Bal | 4.18 | 1.5 | 6.27 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.65 | 4.27 | 15.5855 | CB |  |  | 0 |  |  | 0
| Bal | 3.95 | 1.5 | 5.925 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.65 | 3.647 | 13.3115 | CB |  |  | 0 |  |  | 0
| Bal | 3.88 | 1.383 | 5.366 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.835 | 2.5 | 4.5875 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.815 | 1.827 | 3.316 | DB |  |  | 0 |  |  | 0
| toilet3 | 2.45 | 1.83 | 4.4835 | DB |  |  | 0 |  |  | 0
|  | 2.45 | 1.83 | 4.4835 |  |  |  | 0 |  |  | 0
| passage1 | 4.851 | 1.38 | 6.6944 |  |  |  | 0 |  |  | 0
| passage2 | 5.739 | 1.38 | 7.9198 |  | 1.245 | 1.35 | 1.6808 |  |  | 0
| passage3 | 2.45 | 2 | 4.9 | Bed -1 | 3.575 | 3.18 | 11.3685 |  |  | 0
| passage4 | 2.45 | 0.6 | 1.47 |  | 3.055 | 1.14 | 3.4827 |  |  | 0
|  | 1.83 | 4.58 | 8.3814 |  | 3.435 | 1 | 3.435 |  |  | 0
|  | 3.88 | 1.38 | 5.3544 |  | 2.445 | 1.83 | 4.4744 |  |  | 0
|  |  |  | 0 |  | 1.2 | 1.2 | 1.44 |  |  | 0
| Total |  | 2208.6716 | 205.1906 |  |  | 398.9709 | 37.0653 |  | 0 | 0
|  |  | 2607.6425 | 242.2559

## Sheet1
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 5.81 | 8.25 | 47.9325 | CB | 3 | 0.6 | 1.8 |  |  | 0
|  | 4.66 | 3 | 13.98 | FB | 0.6 | 2.18 | 1.308 |  |  | 0
| Bal | 5.71 | 1.5 | 8.565 |  |  |  | 0 |  |  | 0
| kitch | 3.65 | 1.82 | 6.643 | CB | 2.28 | 0.6 | 1.368 |  |  | 0
|  | 3.05 | 2.43 | 7.4115 | FB |  |  | 0 |  |  | 0
| Bal | 3.88 | 1.5 | 5.82 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.28 | 3.3 | 10.824 | CB | 3 | 0.6 | 1.8 |  |  | 0
|  | 3.8 | 1.57 | 5.966 | FB |  |  | 0 |  |  | 0
| Bal | 4.18 | 1.5 | 6.27 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.65 | 4.27 | 15.5855 | CB |  |  | 0 |  |  | 0
| Bal | 3.95 | 1.5 | 5.925 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 | 3.65 | 3.647 | 13.3115 | CB |  |  | 0 |  |  | 0
| Bal | 3.88 | 1.383 | 5.366 | FB | 1 | 6.996 | 6.996 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.835 | 2.5 | 4.5875 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.815 | 1.827 | 3.316 | DB |  |  | 0 |  |  | 0
| toilet3 | 2.45 | 1.83 | 4.4835 | DB |  |  | 0 |  |  | 0
|  | 2.45 | 1.83 | 4.4835 |  |  |  | 0 |  |  | 0
| passage1 | 4.851 | 1.38 | 6.6944 |  |  |  | 0 |  |  | 0
| passage2 | 5.739 | 1.38 | 7.9198 |  | 1.245 | 1.35 | 1.6808 |  |  | 0
| passage3 | 2.45 | 2 | 4.9 | Bed -1 | 3.575 | 3.18 | 11.3685 |  |  | 0
| passage4 | 2.45 | 0.6 | 1.47 |  | 3.055 | 1.14 | 3.4827 |  |  | 0
|  | 1.83 | 4.58 | 8.3814 |  | 3.435 | 1 | 3.435 |  |  | 0
|  | 3.88 | 1.38 | 5.3544 |  | 2.445 | 1.83 | 4.4744 |  |  | 0
|  |  |  | 0 |  | 1.2 | 1.2 | 1.44 |  |  | 0
| Total |  | 2208.6716 | 205.1906 |  |  | 421.4461 | 39.1533 |  | 0 | 0
|  |  | 2630.1177 | 244.3439