## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 21/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-14
Name of the builder group |  |  |  | Veda Infra Projects
Name of the builder company |  |  |  | Veda Infra Projects
Name of the Project |  |  |  | Raghav Paradise
Provided Contact Details ( Name & Contact No.) |  |  |  | 8657055000
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Pratap 8657029000
Name / No of the Building |  |  |  | 1 Building (Sale Wing)
ccc |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51800045345
Project location details |  | Raghav Paradise, CTS No.180(Pt) & 183(Pt), near Late Anantrao Bhosale Playground, Sai Mandir Road, Jay Maharashtra Nagar, Magathane, Borivali East, Borivali, Mumbai - 400066.
CTS No |  | 180(Pt) & 183(Pt)
Locality |  | Jay Maharashtra Nagar
Road |  | Sai Mandir Road |  | Locality/Village |  | Magathane
City |  | Borivali East |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400066
Nearby Landmark |  | Late Anantrao Bhosale Playground |  | Distance from city centre: |  | 2.2 KM from Borivali Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Chawl
West | NA | NA |  |  | Sai Mandir Road
North | NA | NA |  |  | Late Anantrao Bhosale Playground
South | NA | NA |  |  | Chawl
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude |  | 19.2189 |  | Longitude |  | 72.8686
Location Link |  | https://goo.gl/maps/i49Pf9u9gwuFCZ5ZA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1900.58
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 2.2411
Total FSI availaible for the project |  |  |  | 6.2411
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 11861.62
Total number of Buildings |  |  |  | 1 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Slum Rehabilitation Authority (SRA)
Layout Approval No |  | RC/MHL & STGL/0001/20201203/AP/C |  |  | Dated | 2023-11-09
Approved Floor plan No. |  | RC/MHL & STGL/0001/20201203/AP/C |  |  | Dated | 2023-11-09
Commencement-CC No Valid Up to: |  | RC/MHL/STGL/0001/20201203/AP/C |  |  | Dated | 2023-11-09
This CC is re-endorsed as per amended plan dtd.09/11/2023.
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 11861.62
Approved no of units |  |  | Flats - 192, Shop - 5
Approved no of Floors |  |  | Sale Wing = 2B + Gr/Stilt + 1st to 23rd Floor
Proposed no of Floors |  |  | Sale Wing = 2B + Gr/Stilt + 1st to 23rd Floor |  |  |  |  | visitor
Expected Completion |  |  | As per RERA - 30/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Sale Wing = 2B + Gr/Stilt + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 21 Floor, Painting upto 15 Floor Completed | , Flooring upto 21 Floor, Painting upto 15 Floor
Basement | 2 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 21 Floor, Painting upto 15 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 87.39% |  | 94.57% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 17.25
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0 | Extra % stage is given on dtd 29/06/24 |  |  | shailesh
Flooring & Fitting | Flooring & Fitting | 21 | 91.3% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 15 | 65.22% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 17000 |  |  |  | mis | online | visitor
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 30000
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 1100000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1000000 |  |  |  | 17-18 | 16 | 16
Distressed valuation of the Property |  |  |  |  | 13600 |  |  |  | 15500 to 16500 | 2023-08-09 | nikhil
Commercial Area Details : shop
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | 11L | 2024-03-18 | Other charges | Nikhil
Sale Wing |  | 5 |  | 1024.0062 |  | 1638.41
Residential Area Details : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Sale Wing |  | 192 |  | 99806.8219 |  | 154700.574
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Sale Wing
Lower Basement Floor for Parking & Pump Room
Upper Basement Floor for Parking
Ground Floor For Part Commercial & Part Parking
1 |  | Shop | 248.7883 | 0 | 398.0613 | Ground Floor For Part Commercial & Part Parking
2 |  | Shop | 244.4989 | 0 | 391.1982
3 |  | Shop | 190.7811 | 0 | 305.2498
4 |  | Shop | 166.7128 | 0 | 266.7405
5 |  | Shop | 173.2251 | 0 | 277.1601
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Sale Wing
1st Floor For Part Residential & Parking Area
6 |  | 3BHK | 713.6532 | 0 | 1106.1625 | 1st Floor For Part Residential & Parking Area |  | 63.8525 | 24.8369
7 |  | 3BHK | 681.7918 | 0 | 1056.7772
2nd to 7th, 9th to 14th, 16th to 22nd Floor
1 |  | 1 | 407.7403 | 0 | 631.9975 | 2nd to 7th, 9th to 14th, 16th to 22nd Floor
2 |  | 1 | 462.0985 | 0 | 716.2527
3 |  | 1 | 465.6506 | 0 | 721.7585 |  |  | 56.0925 | 17457.363 |  | 11187256.626
4 |  | 2BHK | 558.544 | 0 | 865.7431 |  |  | 14438.4627 | 14553.9704 |  | 13419018.639
5 |  | 2BHK | 558.544 | 0 | 865.7431
6 |  | 3BHK | 713.6532 | 0 | 1106.1625
7 |  | 3BHK | 681.7918 | 0 | 1056.7772
8 |  | 1 | 411.723 | 0 | 638.1706
9 |  | 1 | 411.723 | 0 | 638.1706
8th Floor (Part Refuge Area)
1 |  | 1 | 407.7403 | 0 | 631.9975 | 8th Floor (Part Refuge Area)
2 |  | 1 | 462.0985 | 0 | 716.2527
3 |  | 1 | 465.6506 | 0 | 721.7585 |  |  | 56.0925 | 17457.363 |  | 11187256.626
4 |  | 2BHK | 558.544 | 0 | 865.7431 |  |  | 14438.4627 | 14553.9704 |  | 13419018.639
5 |  | Refuge Area
6
7 |  | 3BHK | 681.7918 | 0 | 1056.7772
8 |  | 1 | 411.723 | 0 | 638.1706
9 |  | 1 | 411.723 | 0 | 638.1706
15th Floor (Part Refuge Area)
1 |  | 1 | 407.7403 | 0 | 631.9975 | 15th Floor (Part Refuge Area)
2 |  | 1 | 462.0985 | 0 | 716.2527
3 |  | 1 | 465.6506 | 0 | 721.7585 |  |  | 56.0925 | 17457.363 |  | 11187256.626
4 |  | 2BHK | 558.544 | 0 | 865.7431 |  |  | 14438.4627 | 14553.9704 |  | 13419018.639
5 |  | 2BHK | 558.544 | 0 | 865.7431 |  |  | 14438.4627 | 14553.9704 |  | 13419018.639
6 |  | Refuge Area
7
8
9 |  | 1 | 411.723 | 0 | 638.1706
23rd Floor for Residential & Fitness Center & Other Amenities (Part Terrace Area)
1 |  | Fitness Center |  |  |  | 23rd Floor for Residential & Fitness Center & Other Amenities (Part Terrace Area)
2
3 |  | 1 | 465.6506 | 0 | 721.7585
4 |  | 2BHK | 558.544 | 0 | 865.7431
5 |  | 2BHK | 558.544 | 0 | 865.7431
6 |  | 3BHK | 713.6532 | 0 | 1106.1625
7 |  | 3BHK | 681.7918 | 0 | 1056.7772
8 |  | 1 | 411.723 | 0 | 638.1706
9 |  | Swimming Pool
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Construction work is in process at the time of visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
9 | In approved plans, commercial shops on the ground floor and 1st floor of the sale wing do not have shop numbering. So please provide a sale plan for the ground floor and 1st floor of the sale wing, which consists of shop numbering.
* | Please Provide latest CC.
* | We have updated revised approved floor plan (on 14/07/2023).
* | We have updated revised approved floor plans & CC (On 20/12/2023).
* | Other Charges of the Property have been revised on 18/03/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Roshan Kudalkar |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Raghav Paradise
Layout Plan :
Google Map :
Formulas:
Magathane = [Magathane, row above]
Sale Wing
Rehab Wing
1 Building (Sale Wing)
(Sale Wing)
(Sale Wing)
Sale Wing
Sale Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted