## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 20/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-13
Name of the builder group |  |  |  |  | M/s. Bhoomi Anand Developers.
Name of the builder company |  |  |  |  | M/s. S.S Engineering Builder & Developers.
Name of the Project |  |  |  |  | Siddhagiri Residency
Contect Details ( Name & Contect No.) |  |  |  |  | Mr. Anand - 9833176072
Docouments Provided |  |  |  |  | 1. Copy of Plans. 2. Copy of CC.
RERA No |  |  |  |  | P52000014294
Approved Layout Plan : |  | CIDCO/BP-15422/TPO/(NM & K)/2017 |  |  |  |  | Dated | 20/09/2017.
Project location details |  | Siddhagiri Residency, Plot No. 223, Sector No. 17, Ulwe Panvel, Navi Mumbai., Raigad.
Sector No | 17 |  |  | Plot No. | 223 | Locality | Ulwe
Road | Sector No. 17 Internal Road |  |  |  | District | Raigad
City | Navi Mumbai |  |  |  | Pin Code | 400 706
Near by Landmark |  | Near RS International Stadium |  |  | Distance from city centre: |  | 2.3Km from Baman Dongri Railway Station
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Building |  | Building |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | Latitude |  | 18.9617 |  | Longitude |  | 73.0172
Location Link |  | https://goo.gl/maps/W78LpsmAX2uadSzM9?coh=178572&entry=tt
Approval details:
Approved usage of the Property: Residential (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 299.41
Permissible FSI |  |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1.5
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 449.11
Total number of Buildings |  |  |  |  | 1 Building
Approval Detail : Plan approval
Layout Approval No |  | CIDCO/BP-15422/TPO/(NM & K)/2017 |  |  |  | Dated | 20/09/2017.
Building plan approval No |  | CIDCO/BP-15422/TPO/(NM & K)/2017 |  |  |  | Dated | 20/09/2017. | Expiry date:NA
C.certificate No |  | CIDCO/BP/-15422/TPO/(NM & K)/2017/1963 Valid Up to: Gr + 1st to 4th Floor |  |  |  | Dated | 07/09/2017. | Expiry date: One year from date of issue
O. Certificate No.: NA |  |  |  |  | Date of approval: NA |  | Expiry date: NA
Commencement date of construction |  |  | 07/09/2017. |  | Expected Completion |  | 2024-12-31
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 449.11 |  | Approved no of units residential |  |  | 17
Approved no of Floors |  | Gr + 1st to 4th Floor |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | Gr + 1st to 4th Floor | [6 empty] | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 3 Floor completed , Painting upto 2 Floor completed
Basement | 0 | Ground | 1 | Podium | 0 |  | Floors | 4 | All work Completed. Provide OC.
Stage of construction: |  | Excavation work completed, Plinth work completed, RCC upto 5 Slab completed, Brickwork upto 4 Floor completed, Internal Plaster upto 4 Floor completed, External Plaster upto 3 Floor completed , Painting upto 2 Floor completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 75% |  | 88.75% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 75% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 2 | 50% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleble area) | [5 empty] | 5700
Floor rise rate Per Sq. Ft. | [5 empty] | NA
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | 150000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Valuation as per Government reckoners rates | [5 empty] | NA
Distress valuation of the property Per Sq. Ft. | [5 empty] | 4560
Building details floor wise
Details of Flats in Building
Sr. | Flat No. | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Builder Saleable area | PLC Y/N
Ground Floor For Parking
1 | 1 | 1MP Room | 320 | 65 | 385 | 0 | 595 | NA |  | 1.5455
1st & 3rd Floor
2 | 1 | 1RK | 318 | 61 | 379 | 0 | 610 | NA
3 | 2 | 1RK | 314 | 68 | 382 | 0 | 615 | NA
4 | 3 | 1RK | 318 | 65 | 383 | 0 | 620 | NA
5 | 4 | 1RK | 318 | 65 | 383 | 0 | 620 | NA
2nd Floor
6 | 1 | 1RK | 318 | 61 | 379 | 0 | 585 | NA
7 | 2 | 1RK | 314 | 68 | 382 | 0 | 590 | NA
8 | 3 | 1RK | 318 | 65 | 383 | 0 | 595 | NA
9 | 4 | 1RK | 318 | 65 | 383 | 0 | 595 | NA
4th Floor
10 | 1 | 1RK | 318 | 61 | 379 | 0 | 585 | NA
11 | 2 | 1RK | 314 | 68 | 382 | 0 | 590 | NA
12 | 3 | 1RK | 318 | 65 | 383 | 0 | 595 | NA
13 | 4 | 1RK | 318 | 65 | 383 | 0 | 595 | NA
Remarks: 1. Construction work was stopped. Work is same as last visit(12/05/2023). 2. We adopted builder saleable area as per builder saleable area chart. 3. We have considered rate by verifying it from market inquire. 4. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 5. Car parking is subjected to authentic documentation. 6. Since the project has received first CC on 07/09/2017., But construction work of Siddhagiri Residency is under construction. 7. As per RERA, completion period of project Siddhagiri Residency is expired on 31/12/2024 but still project is under construction.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Builder Salable Area Chart.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) FungibleArea= Enclose Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Weather shed Area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : Siddhagiri Residency
Google Map :

## C%
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
| 4 | 4 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 65 | 75

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
commonfloor | Siddhagiri Residency | 1BHK | 279 | 404.55 | 8619.4537 | 3487000
commonfloor | Siddhagiri Residency | 1BHK | 407 | 590.15 | 8619.8424 | 5087000
commonfloor | Siddhagiri Residency | 1RK | 187 | 271.15 | 8618.8457 | 2337000
Average |  |  |  |  | 8619.3806
Valuation Adopted