## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 18/08/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Badlapur | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-08-12 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | S M Hitech Developers | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | S M Hitech Developers | [9 empty] | IBHF Thane
Name of the Project |  |  |  | S M Elite | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Mr.Irfan Patel 9930357927/9920404094
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr.Irfan 9930357927
Name / No of the Building |  |  |  | Wing A & B
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P52000052521 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | S M Elite, Survey No.111/2, near SM Emerald, Internal Road, Ghotkamp Koyana Vele, Taloje Majkur, Taloja Panchnand East, Panvel, Raigad - 410208. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 111/2 | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Ghotkamp Koyana Vele | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Taloje Majkur | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Taloja Panchnand East |  | District |  | Raigad | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Panvel |  | Pin Code |  | 410208 | [13 empty] | Mahad | Daund
Nearby Landmark |  | SM Emerald |  | Distance from city centre: |  | 3.0 KM from Taloja Panchnand Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Other Plot |  |  | Open Plot
West | NA | Other Plot |  |  | Open Plot
North | NA | Proposed Road 15.0 M Wide Road, High Tension Lines Conductor Position |  |  | SM Emerald
South | NA | Road Widening Area (Existing Road 164.30 Sq.Mt) |  |  | Internal Road
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.076325,73.105882
Location Link |  | https://maps.app.goo.gl/RbzxMuvZhQHvitvcA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3266.17
Permissible FSI |  |  |  | 1.0807
Permissible TDR/Paid FSI |  |  |  | 2.8008
Total FSI availaible for the project |  |  |  | 3.8815
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 12677.7
Total number of Buildings |  |  |  | 02 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | PMP/NRV/16663/J.K.807/2023 |  |  | Dated | 2023-03-31 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | PMP/NRV/16663/J.K.807/2023 |  |  | Dated | 2023-03-31 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | PMC/TP/Taloje Majkur/111/2/21-23/ 16663/807/2023 |  |  | Dated | 2023-03-31 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Wing A & B = 1B + Gr + 1st to 12th Floor No. of Residential Unit = 166 Nos. & Commercial Unit = 06 Nos. Total Units = 172 Nos. | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | Wing A & B = 1B + Gr + 1st to 12th Floor No. of Residential Unit = 166 Nos. & Commercial Unit = 06 Nos. Total Units = 172 Nos. |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Site Elevation Height: Permissible Top Elevation |  | NAVI/WEST/B/010923/735999 |  |  | Dated | 2023-03-06 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
|  | 10.61M (AMSL) 109.61M (AMSL) |  |  | Valid upto Date | 2033-03-05 | [11 empty] | Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) |  |  | 12677.7
Approved no of units |  |  | Flats - 166, Shops - 6
Approved no of Floors |  |  | Wing A & B = 1B + Gr + 1st to 12th Floor
Proposed no of Floors |  |  | Wing A = 1B + Gr + 1st to 14th Floor
Wing B = 1B + Gr + 1st to 14th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Swimming Pool, Fitness Center, Indoore Games, Senior Sit-Outs, Elegant and well designed decorative entrance lobby, Reputed automatic high-speed eleevators with ARD, Power backup facility for Lifts, Club House, Waterpumps and lighting for common area, Underground and overhead water tank, Society office for maintenance affairs, Round the clock security etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = 1B + Gr + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 12 Slab, Brickwork upto 9 Floor, Internal Plaster upto 4 Floor, External Plaster upto 3 Floor Completed | , RCC upto 12 Slab, Brickwork upto 9 Floor, Internal Plaster upto 4 Floor, External Plaster upto 3 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 12 Slab, Brickwork upto 9 Floor, Internal Plaster upto 4 Floor, External Plaster upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 51.11% |  | 74.71% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 12 | 80% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 9 | 64.29% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 4 | 28.57% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 21.43% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Wing B = 1B + Gr + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 12 Slab, Brickwork upto 10 Floor, Internal Plaster upto 3 Floor, External Plaster upto 6 Floor Completed | , RCC upto 12 Slab, Brickwork upto 10 Floor, Internal Plaster upto 3 Floor, External Plaster upto 6 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 12 Slab, Brickwork upto 10 Floor, Internal Plaster upto 3 Floor, External Plaster upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 53.25% |  | 75.79% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 12 | 80% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 10 | 71.43% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 3 | 21.43% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 6 | 42.86% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Wing B = 1B + Gr + 1st to 14th Floor | [5 empty] | Excavation Completed, Footing work Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation | , Footing work Completed
Stage of construction: |  | Excavation Completed, Footing work Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 5% |  | 32.5% |  | Excavation in process | 7
Plinth |  | 7 | 50% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5300 | [11 empty] | 800000 | 300000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 7500 | [11 empty] | 900000 | 350000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 400000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 500000 | 250000 | 250000
Development Charges |  |  |  |  | 100000 | [11 empty] | 1200000 | 600000 | 300000 | 300000
Club Charges |  |  |  |  | 125000 | [11 empty] | 1300000 | 700000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 800000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 900000 | 500000
Society Formation Charges |  |  |  |  | 25000 | [11 empty] | 1600000 | 1000000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000
Recommended rate of Parking |  |  |  |  | 300000 | [11 empty] | 1800000
Distressed valuation of the Property |  |  |  |  | 4240
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 6 |  | 2096.3966 |  | 4530
Total |  | 6 |  | 2096.3966 |  | 4530
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 83 |  | 58323.0656 |  | 87365
Wing B |  | 83 |  | 57383.3684 |  | 85525
Total |  | 166 |  | 115706.434 |  | 172890
Grand Total |  | 172 |  | 117802.8306 |  | 177420
Building details Floor Wise
Details of Residential & Commercials in Building | [7 empty] | 10.764
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Builder Area Sheet :
55%
Wing A
Basement Floor For Service Space & Parking
Ground Floor For Commercial, Meter Room & Parking
1 |  | Shop | 348.4307 | 0 | 348.4307 | 0 | 755 | 32.161 | 2.1669 | 2.1669
2 |  | Shop | 348.4307 | 0 | 348.4307 | 0 | 755 |  | 2.1669 | 2.1669
3 |  | Shop | 351.337 | 0 | 351.337 | 0 | 755 |  |  | 2.1489
4 |  | Shop | 351.337 | 0 | 351.337 | 0 | 755 |  |  | 2.1489
5 |  | Shop | 348.4307 | 0 | 348.4307 | 0 | 755 |  |  | 2.1669
6 |  | Shop | 348.4307 | 0 | 348.4307 | 0 | 755 |  |  | 2.1669
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Balcony Area+Chajja Area | Gross Carpet area | Attached Terrace area | Builder Area Sheet :
50%
Wing A
1st Floor For Residential | [8 empty] | 10.764
1 |  | 2BHK | 547.8876 | 87.9957 | 635.8833 | 0 | 940 | 49.0725 |  | 1.4783
2 |  | 3BHK | 755.7404 | 42.7869 | 798.5273 | 234.4399 | 1460 | 67.1175 |  | 1.8284 | 73.545
3 |  | 3BHK | 755.7404 | 42.7869 | 798.5273 | 234.4399 | 1460 |  |  | 1.8284
4 |  | 2BHK | 547.8876 | 87.9957 | 635.8833 | 0 | 940 |  |  | 1.4783
5 |  | 2BHK | 517.856 | 87.9957 | 605.8517 | 0 | 890 |  |  | 1.4799
6 |  | 2BHK | 543.7973 | 87.9957 | 631.793 | 0 | 935
7 |  | 2BHK | 543.7973 | 87.9957 | 631.793 | 0 | 935
2nd, 3rd, 4th, 5th, 6th, 7th, 9th, 10th, 11th & 12th Floor
1 |  | 2BHK | 547.8876 | 87.9957 | 635.8833 | 0 | 940 |  | 6808.5106 | 1.4783 | 1.4783
2 |  | 3BHK | 755.7404 | 138.0483 | 893.7887 | 0 | 1350 |  | 4740.7407 | 1.4601 | 1.5104
3 |  | 3BHK | 755.7404 | 138.0483 | 893.7887 | 0 | 1350 |  | 4740.7407 | 1.4601 | 1.5104
4 |  | 2BHK | 547.8876 | 87.9957 | 635.8833 | 0 | 940 |  | 6808.5106 | 1.4783 | 1.4783
5 |  | 2BHK | 517.856 | 87.9957 | 605.8517 | 0 | 890 |  | 7191.0112 | 1.469 | 1.469
6 |  | 2BHK | 543.7973 | 87.9957 | 631.793 | 0 | 935 |  | 6844.9198 | 1.4799 | 1.4799
7 |  | 2BHK | 543.7973 | 87.9957 | 631.793 | 0 | 935 |  | 6844.9198 | 1.4799 | 1.4799
8th Floor (Part Refuge Area) | [7 empty] | 84
1 |  | 2BHK | 547.8876 | 87.9957 | 635.8833 | 0 | 940
2 |  | 3BHK | 755.7404 | 138.0483 | 893.7887 | 0 | 1350
3 |  | 3BHK | 755.7404 | 138.0483 | 893.7887 | 0 | 1350
4 |  | 2BHK | 547.8876 | 87.9957 | 635.8833 | 0 | 940
5 |  | 2BHK | 517.856 | 87.9957 | 605.8517 | 0 | 890
6 |  | 2BHK | 543.7973 | 87.9957 | 631.793 | 0 | 935
7 |  | Refuge Area
Wing B
Basement Floor For Service Space & Parking
Ground Floor For Meter Room & Parking
1st Floor For Residential | [8 empty] | 5400
1 |  | 2BHK | 547.8876 | 87.9957 | 635.8833 | 0 | 940 |  | 5076000
2 |  | 2BHK | 543.7973 | 87.9957 | 631.793 | 0 | 935 |  | 5049000
3 |  | 2BHK | 543.7973 | 87.9957 | 631.793 | 0 | 935 |  | 5049000
4 |  | 2BHK | 517.856 | 87.9957 | 605.8517 | 0 | 890 |  | 4806000
5 |  | 3BHK | 698.9065 | 110.1964 | 809.103 | 0 | 1190 | 62.715 | 6426000
6 |  | 3BHK | 804.2861 | 111.0037 | 915.2898 | 0 | 1425 |  | 7695000
7 |  | 2BHK | 518.5019 | 86.3811 | 604.883 | 0 | 890 |  | 4806000
2nd, 3rd, 4th, 5th, 6th, 7th, 9th, 10th, 11th & 12th Floor
1 |  | 2BHK | 547.8876 | 87.9957 | 635.8833 | 0 | 940
2 |  | 2BHK | 543.7973 | 87.9957 | 631.793 | 0 | 935
3 |  | 2BHK | 543.7973 | 87.9957 | 631.793 | 0 | 935
4 |  | 2BHK | 517.856 | 87.9957 | 605.8517 | 0 | 890
5 |  | 3BHK | 698.9065 | 110.1964 | 809.103 | 0 | 1190
6 |  | 3BHK | 804.2861 | 111.0037 | 915.2898 | 0 | 1425
7 |  | 2BHK | 518.5019 | 86.3811 | 604.883 | 0 | 890
8th Floor (Part Refuge Area)
1 |  | 2BHK | 547.8876 | 87.9957 | 635.8833 | 0 | 940
- |  | Refuge Area
2 |  | 2BHK | 543.7973 | 87.9957 | 631.793 | 0 | 935
3 |  | 2BHK | 517.856 | 87.9957 | 605.8517 | 0 | 890
4 |  | 3BHK | 698.9065 | 110.1964 | 809.103 | 0 | 1190
5 |  | 3BHK | 804.2861 | 111.0037 | 915.2898 | 0 | 1425
6 |  | 2BHK | 518.5019 | 86.3811 | 604.883 | 0 | 890
Remarks:
* | Wing A & B = Construction work is in process at the time of Visit. (Internal photo was not allowed).
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony Area+ Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | S M Elite
Layout :
Google Map :
Wing B
Wing A
Wing A
Wing A
Wing A
Wing B
Wing B
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on C59: SACHIN: Height from AMSL
Note on D62: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F121: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H154: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14
15
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate