## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/08/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | Deep Laxmi Associates
Name of the builder company |  |  |  | Deep Laxmi Associates
Name of the Project |  |  |  | Shreeji Milestone
Provided Contact Details (Name & Contact No.) |  |  |  | 7719005666
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Girish 9320819178
Name / No of the Building |  |  |  | Building No. A, B, C & D
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51700050320
Project location details |  | Shreeji Milestone, Survey No.48, Plot No. 1, near Precious Harmony, Sidh Swayambhu Shiv Mandir Rd, Katrap, Belavli, Badlapur, Ambernath, Thane - 421503.
Survey No |  | 48, Plot No. 1
Locality |  | Katrap
Road |  | Sidh Swayambhu Shiv Mandir Rd |  | Locality/Village |  | Belavli
City |  | Badlapur |  | District |  | Thane
Taluka |  | Ambernath |  | Pin Code |  | 421503
Nearby Landmark |  | Precious Harmony |  | Distance from city centre: |  | 2.5KM from Badlapur Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Ambar Plaza
West | NA | NA |  |  | Satyam Shivam CHS Limited
North | NA | NA |  |  | Sidh Swayambhu Shiv Mandir Road
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.174490,73.226814
Location Link |  | https://goo.gl/maps/CfFxadLgXzb1K7i66
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 8443.55
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.695
Total FSI availaible for the project |  |  |  | 3.795
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 32043.27
Total number of Buildings |  |  |  | 04 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Kulgaon Badlapur Nagar Parishad
Layout Approval No |  | KBNP/NRV/BD/5777-50 |  |  | Dated | 2022-06-29
Approved Floor plan No. |  | KBNP/NRV/BD/5777-50 |  |  | Dated | 2022-06-29
Commencement-CC No Valid Up to: |  | K.B.N.P/NRV/BP/5777/2022-23 Unique No. 50 |  |  | Dated | 2022-06-29
Building No. A = Gr/Stilt (Pt) + 1st to 14th Floor Building No. B = Stilt + 1st to 14th Floor Building No. C = Stilt + 1st to 13th Floor Building No. D = Stilt + 1st to 14th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 32043.27
Approved no of units |  |  | Flats - 560, Shops - 15
Approved no of Floors |  |  | Building No. A = Gr/Stilt (Pt) + 1st to 14th Floor Building No. B = Stilt + 1st to 14th Floor Building No. C = Stilt + 1st to 13th Floor Building No. D = Stilt + 1st to 14th Floor
Proposed no of Floors |  |  | Building No. B = Stilt + 1st to 14th Floor
Building No. A, C & D = Stilt + 1st to 14th Floor
Expected Completion |  |  | As per RERA - 30/06/2029
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Club House
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. B = Stilt + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 13 Floor, Finishing upto 9 Floor Completed | , Painting upto 13 Floor, Finishing upto 9 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 13 Floor, Finishing upto 9 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 92.86% |  | 95% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 14 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 14 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 13 | 92.86% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 9 | 64.29% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Building No. A = Gr/Stilt (Pt) + 1st to 14th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 3 Floor Completed | , External Plaster upto 12 Floor, Flooring upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 12 Floor, Flooring upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 75.71% |  | 90.36% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 15 | 100% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 14 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 85.71% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 21.43% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Building No. C = Gr/Stilt (Pt) + 1st to 14th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 14 | 100% | 10% |  | 45% |  | Excavation in process | 7
Plinth |  | 14 | 100% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Construction details: |  | Building No. D = Gr/Stilt (Pt) + 1st to 14th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3.5
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 7
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 14
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3.5
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 7
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 14
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4200
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8500
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 3360
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 15 |  | 3317.7877 |  | 5308.4604
Total |  | 15 |  | 3317.7877 |  | 5308.4604
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 124 |  | 75141.9824 |  | 112980.6564
Wing B |  | 166 |  | 90807.7304 |  | 136211.5956
Wing C |  | 102 |  | 56510.7632 |  | 84766.1448
Wing D |  | 168 |  | 79547.9729 |  | 119321.9593
Total |  | 560 |  | 302008.4489 |  | 453280.3561
Grand Total |  | 575 |  | 305326.2366 |  | 458588.8164
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Building No. A
Ground Floor For Commercial, Driver Room & Parking
1 |  | Shop | 243.1588 | 0 | 389.054 | Ground Floor For Commercial, Driver Room & Parking
2 |  | Shop | 221.3078 | 0 | 354.0925
3 |  | Shop | 202.3632 | 0 | 323.7811
4 |  | Shop | 165.9809 | 0 | 265.5694
5 |  | Shop | 280.2946 | 0 | 448.4713
6 |  | Shop | 165.9809 | 0 | 265.5694
7 |  | Shop | 202.3632 | 0 | 323.7811
8 |  | Shop | 221.3078 | 0 | 354.0925
9 |  | Shop | 221.3078 | 0 | 354.0925
10 |  | Shop | 202.3632 | 0 | 323.7811
11 |  | Shop | 165.9809 | 0 | 265.5694
12 |  | Shop | 302.0378 | 0 | 483.2605
13 |  | Shop | 165.9809 | 0 | 265.5694
14 |  | Shop | 202.3632 | 0 | 323.7811
15 |  | Shop | 354.9967 | 0 | 567.9948
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building No. A
1st Floor For Residential
1 |  | 1BHK | 470.3222 | 0 | 705.4833 | 1st Floor For Residential
2 |  | 1BHK | 470.3222 | 0 | 705.4833 | 1st Floor For Residential
3 |  | 1BHK | 475.096 | 0 | 712.6441 | 1st Floor For Residential
4 |  | 3BHK | 831.2768 | 224.8061 | 1321.8506 | 1st Floor For Residential
5 |  | 2BHK | 651.2758 | 48.9762 | 1025.8899 | 1st Floor For Residential
6 |  | 2BHK | 651.2758 | 48.9762 | 1025.8899 | 1st Floor For Residential
7 |  | 2BHK | 649.8765 | 284.3849 | 1069.6097 | 1st Floor For Residential
8 |  | 2BHK | 663.8374 | 0 | 995.7561 | 1st Floor For Residential
9 |  | 1BHK | 472.2597 | 0 | 708.3896 | 1st Floor For Residential
2nd to 7th, 9th to 12th & 14th Floor
1 |  | 1BHK | 470.3222 | 0 | 705.4833 | 2nd to 7th, 9th to 12th & 14th Floor
2 |  | 1BHK | 470.3222 | 0 | 705.4833
3 |  | 1BHK | 475.096 | 0 | 712.6441
4 |  | 3BHK | 862.7615 | 0 | 1294.1423
5 |  | 2BHK | 665.8072 | 0 | 998.7108
6 |  | 2BHK | 665.8072 | 0 | 998.7108
7 |  | 2BHK | 666.4261 | 0 | 999.6392
8 |  | 2BHK | 663.8374 | 0 | 995.7561
9 |  | 1BHK | 472.2597 | 0 | 708.3896
8th & 13th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 8th & 13th Floor (Part Refuge Area)
2 |  | 2BHK | 661.7061 | 0 | 992.5592 | 8th & 13th Floor (Part Refuge Area)
3 |  | 1BHK | 475.096 | 0 | 712.6441 | 8th & 13th Floor (Part Refuge Area)
4 |  | 3BHK | 862.7615 | 0 | 1294.1423 | 8th & 13th Floor (Part Refuge Area)
5 |  | 2BHK | 665.8072 | 0 | 998.7108 | 8th & 13th Floor (Part Refuge Area)
6 |  | 2BHK | 665.8072 | 0 | 998.7108 | 8th & 13th Floor (Part Refuge Area)
7 |  | 2BHK | 666.4261 | 0 | 999.6392 | 8th & 13th Floor (Part Refuge Area)
8 |  | 2BHK | 663.8374 | 0 | 995.7561 | 8th & 13th Floor (Part Refuge Area)
9 |  | 1BHK | 472.2597 | 0 | 708.3896 | 8th & 13th Floor (Part Refuge Area)
Building No. B
Stilt Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
1 |  | 2BHK | 624.2474 | 0 | 936.3711 | 1st to 7th, 9th to 12th & 14th Floor For Residential
2 |  | 2BHK | 624.2474 | 0 | 936.3711
3 |  | 2BHK | 624.7856 | 0 | 937.1784
4 |  | 1BHK | 470.1069 | 0 | 705.1604
5 |  | 1BHK | 470.1069 | 0 | 705.1604
6 |  | 2BHK | 624.7856 | 0 | 937.1784
7 |  | 2BHK | 617.3585 | 0 | 926.0377
8 |  | 2BHK | 617.3585 | 0 | 926.0377
9 |  | 1BHK | 470.1069 | 0 | 705.1604
10 |  | 1BHK | 470.1069 | 0 | 705.1604
11 |  | 1BHK | 470.1069 | 0 | 705.1604
12 |  | 1BHK | 470.1069 | 0 | 705.1604
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 624.2474 | 0 | 936.3711 | 8th & 13th Floor (Part Refuge Area)
2 |  | 2BHK | 624.2474 | 0 | 936.3711
3 |  | 2BHK | 624.7856 | 0 | 937.1784
4 |  | Refuge Area
5 |  | 1BHK | 470.1069 | 0 | 705.1604
6 |  | 2BHK | 624.7856 | 0 | 937.1784
7 |  | 2BHK | 617.3585 | 0 | 926.0377
8 |  | 2BHK | 617.3585 | 0 | 926.0377
9 |  | 1BHK | 470.1069 | 0 | 705.1604
10 |  | 1BHK | 470.1069 | 0 | 705.1604
11 |  | 1BHK | 470.1069 | 0 | 705.1604
12 |  | 1BHK | 470.1069 | 0 | 705.1604
Building No. C
Stilt Floor For Parking
1st to 7th, 9th to 12th Floor For Residential
1 |  | 2BHK | 630.3829 | 0 | 945.5743 | 1st to 7th, 9th to 12th Floor For Residential
2 |  | 2BHK | 610.8032 | 0 | 916.2048
3 |  | 1BHK | 485.9408 | 0 | 728.9112
4 |  | 1BHK | 482.281 | 0 | 723.4215
5 |  | 2BHK | 610.8032 | 0 | 916.2048
6 |  | 2BHK | 630.3829 | 0 | 945.5743
7 |  | 1BHK | 470.1069 | 0 | 705.1604
8 |  | 1BHK | 470.1069 | 0 | 705.1604
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 630.3829 | 0 | 945.5743 | 8th & 13th Floor (Part Refuge Area)
2 |  | 2BHK | 610.8032 | 0 | 916.2048
3 |  | Refuge Area
4 |  | 2BHK | 683.3525 | 0 | 1025.0288
5 |  | 2BHK | 610.8032 | 0 | 916.2048
6 |  | 2BHK | 630.3829 | 0 | 945.5743
7 |  | 1BHK | 470.1069 | 0 | 705.1604
8 |  | 1BHK | 470.1069 | 0 | 705.1604
Building No. D
Stilt Floor For Parking
1st to 7th, 9th to 12th & 14th Floor For Residential
1 |  | 1BHK | 423.1113 | 0 | 634.667 | 1st to 7th, 9th to 12th & 14th Floor For Residential
2 |  | 1BHK | 423.1113 | 0 | 634.667
3 |  | 2BHK | 624.2474 | 0 | 936.3711
4 |  | 2BHK | 604.6677 | 0 | 907.0015
5 |  | 1BHK | 403.6231 | 0 | 605.4346
6 |  | 1BHK | 403.6231 | 0 | 605.4346
7 |  | 1BHK | 403.6231 | 0 | 605.4346
8 |  | 1BHK | 403.6231 | 0 | 605.4346
9 |  | 2BHK | 604.6677 | 0 | 907.0015
10 |  | 2BHK | 604.6677 | 0 | 907.0015
11 |  | 1BHK | 403.6231 | 0 | 605.4346
12 |  | 1BHK | 423.1113 | 0 | 634.667
8th & 13th Floor (Part Refuge Area)
1 |  | 1BHK | 423.1113 | 0 | 634.667 | 8th & 13th Floor (Part Refuge Area)
2 |  | 1BHK | 423.1113 | 0 | 634.667
3 |  | 2BHK | 624.2474 | 0 | 936.3711
4 |  | 2BHK | 604.6677 | 0 | 907.0015
5 |  | 1BHK | 403.6231 | 0 | 605.4346
6 |  | 1BHK | 403.6231 | 0 | 605.4346
7 |  | 1RK | 250.6666 | 0 | 376
- |  | Refuge Area
8 |  | 1RK | 250.6666 | 0 | 376
9 |  | 2BHK | 604.6677 | 0 | 907.0015
10 |  | 2BHK | 604.6677 | 0 | 907.0015
11 |  | 1BHK | 403.6231 | 0 | 605.4346
12 |  | 1BHK | 423.1113 | 0 | 634.667
Remarks:
* | Wing A & C - Construction work is in process at the time of Visit. (labour found). Wing B - Finishing work is in the process. Wing D - Work not yet started.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Chajja Area + A.P Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Since Wing D have received CC on 29/06/2022, but as of construction work is not started.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Shreeji Milestone
Layout :
Google Map :
Formulas:
Belavli = [Belavli, row above]
Building = A
Building = B
Building = C
Building = D
Bldg B
Bldg A
Wing A
Wing B
Wing A
Wing B
Wing C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted