## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/08/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-12 | [8 empty] | ;
Name of the builder |  |  |  | Gopal Ghanshyamdas Goyal
Name of the builder company |  |  |  | Siddhi Buildcon | [6 empty] | s
Name of the Project |  |  |  | Siddhivinayak Gaurav
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Raju Kamath 9920363167
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Raju Kamath 9920363167
Name / No of the Building |  |  |  | Wing A, B & C
Name / No of the Existing Building |  |  |  | NA
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | P52000034552
Project location details |  | Siddhivinayak Gaurav, Survey No.01, Hissa No. 10, near Abhang Durge Sidhivinayak Ridhima, Internal Road, Ghot, Koyanavele, Taloja East, Panvel, Raigad - 410208.
Survey No |  | 01, Hissa No. 10
Locality |  | Ghot
Road |  | Internal Road |  | Locality/Village |  | Koyanavele
City |  | Taloja East |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410208
Nearby Landmark |  | Abhang Durge Sidhivinayak Ridhima |  | Distance from city centre: |  | 3.7 KM from Taloja Panchnand Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Open Plot/Building |  |  | Siddhivinayak Sales Pavilion
West | NA | Internal Road |  |  | Building |  |  | Unknown Building
North | NA | Internal Road |  |  | Internal Road/Sidhivinayak Ridhima |  |  | Internal Road
South | NA | Plot No. 02 |  |  | Open Plot |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.076236,73.110487
Location Link |  | https://goo.gl/maps/oQ3ip4Pj9QJsCSp69
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3990
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 1.4596
Total FSI availaible for the project |  |  |  | 2.5596
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10212.774
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Muncipal Corporation
Layout Approval No |  | PMP/NRV/16241/JK/515/2022 |  |  | Dated | 2022-03-04 |  | PMC/NRV/16241/515/2022 |  |  | Dated | 2022-03-04
Approved Floor plan No. |  | PMP/NRV/16241/JK/515/2022 |  |  | Dated | 2022-03-04 |  | PMC/NRV/16241/515/2022 |  |  | Dated | 2022-03-04
Commencement-CC No |  | PMP/TP/Koynavele/1/10/21-22/16241/515/2022 |  |  | Dated | 2022-03-04 |  | PMC/TP/Koynavele/1/10/21-22/16241/515/2022 |  |  | Dated | 2022-03-04
Valid Up to: |  | Building No.1 A, B & C Wing = G + 1st to 10th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 10212.774
Approved no of units |  |  | Flats - 173
Approved no of Floors |  |  | Building No.1 A & C Wing = G + 1st to 9th Floor Building No.1 B Wing = G + 1st to 10th Floor
Proposed no of Floors |  |  | Building No.1 (A Wing) = G + 1st to 9th Floor
Building No.1 (B Wing) = G + 1st to 10th Floor
Building No.1 (C Wing) = G + 1st to 9th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Play Area, Seat-Out Area, Gymnasium, Multipurpose Play Turf, Part Lawn. |  |  |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative
Violations Observed if any : |  |  | NA |  |  |  |  | Enternace etc.
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 (A Wing) = G + 1st to 9th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 8 Floor, Finishing upto 5 Floor Completed | , Painting upto 8 Floor, Finishing upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 9 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 8 Floor, Finishing upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.25
Excavation |  | 9 | 100% | 92.22% |  | 95% |  | Excavation in process | 4.5
Plinth |  | 9 | 100% |  |  |  |  | Excavation Completed | 9
RCC (Including podiums) |  | 10 | 100% |  |  |  |  | Footing in Process | 2.25
Brickwork | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Footing Completed | 4.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 9 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 8 | 88.89% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 55.56% |  |  |  |  | Plinth in process | 6.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 9
Construction details: |  | Building No.1 (B Wing) = G + 1st to 10th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 4 Floor Completed | , Finishing upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 10 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.5
Excavation |  | 10 | 100% | 92% |  | 95% |  | Excavation in process | 5
Plinth |  | 10 | 100% |  |  |  |  | Excavation Completed | 10
RCC (Including podiums) |  | 11 | 100% |  |  |  |  | Footing in Process | 2.5
Brickwork | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Footing Completed | 5
Internal Plaster | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 40% |  |  |  |  | Plinth in process | 7.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 10
Construction details: |  | Building No.1 (C Wing) = G + 1st to 9th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 2 Floor Completed | , Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 9 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting Completed, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.25
Excavation |  | 9 | 100% | 91.11% |  | 95% |  | Excavation in process | 4.5
Plinth |  | 9 | 100% |  |  |  |  | Excavation Completed | 9
RCC (Including podiums) |  | 10 | 100% |  |  |  |  | Footing in Process | 2.25
Brickwork | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Footing Completed | 4.5
Internal Plaster | Brickwork & Internal Plaster | 9 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 9 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 9 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 9 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 22.22% |  |  |  |  | Plinth in process | 6.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 9
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5700 |  |  | 5200 to 5700 | Smith & Sanket |  | 2023-09-05
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate from Floor
Development Charges |  |  |  |  | 200000
Club Charges |  |  |  |  | 100000
Legal Charges |  |  |  |  | 11000
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges + Maintenance Charges |  |  |  |  | 50000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 300000
Distressed valuation of the Property |  |  |  |  | 4560
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 71 |  | 31523.881 |  | 47285.8214
B Wing |  | 67 |  | 29393.4701 |  | 44368.8313
C Wing |  | 35 |  | 17012.3405 |  | 25518.5108
Grand Total |  | 173 |  | 77929.6916 |  | 117173.1635
Building details Floor Wise
Details of Residential in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Bulding No. 1
A Wing
Ground Floor For Parking | [10 empty] | NET | MIS
1st to 7th & 9th Floor
1 |  | 1BHK | 399.6673 | 0 | 599.501 | 1st to 7th & 9th Floor |  | 37.13 | 38.54 |  | 5054.2036 | 4300
2 |  | 1BHK | 399.6673 | 0 | 599.501 |  |  | 37.475 |  |  | 5054.2036 | 4700
3 |  | 1BHK | 399.6673 | 0 | 599.501 | [5 empty] | 5054.2036 | 5000
4 |  | 2BHK | 574.5285 | 0 | 861.7928 |  |  | 53.375 | 56.03 | 489.9773 | 5039.4947 | 5700
5 |  | 2BHK | 574.5285 | 0 | 861.7928 |  |  |  |  | 489.9773 | 5039.4947
6 |  | 1BHK | 399.6673 | 0 | 599.501 | [5 empty] | 5054.2036
7 |  | 1BHK | 399.6673 | 0 | 599.501 | [5 empty] | 5054.2036
8 |  | 1BHK | 399.6673 | 0 | 599.501 | [5 empty] | 5054.2036
8th Floor (Part Refuge area)
- |  | Refuge Area |  |  |  | 8th Floor (Part Refuge area) |  | 1BHK | 399.6673
1 |  | 1BHK | 399.6673 | 0 | 599.501 |  |  | 1BHK | 399.6673
2 |  | 1BHK | 399.6673 | 0 | 599.501 |  |  | 1BHK | 399.6673
3 |  | 2BHK | 574.5285 | 0 | 861.7928 |  |  | 1BHK | 399.6673
4 |  | 2BHK | 574.5285 | 0 | 861.7928 |  |  | 2BHK | 574.5285
5 |  | 1BHK | 399.6673 | 0 | 599.501 |  |  | 2BHK | 574.5285
6 |  | 1BHK | 399.6673 | 0 | 599.501 |  |  | 1BHK | 399.6673
7 |  | 1BHK | 399.6673 | 0 | 599.501 |  |  | 1BHK | 399.6673
10th Floor ( Terrace area )
B Wing
Ground Floor For Parking
1st to 7th & 9th Floor
1 |  | 1BHK | 399.6673 | 0 | 599.501 | 1st to 7th & 9th Floor |  | 395.3348 |  | 38.54 | 38.54
2 |  | 1BHK | 399.6673 | 0 | 599.501 |  |  | 395.3348
3 |  | 1BHK | 399.6673 | 0 | 599.501 |  |  | 395.3348
4 |  | 2BHK | 679.6659 | 0 | 1019.4988 |  |  | 685.3708
5 |  | 1BHK | 398.1604 | 0 | 597.2405 |  |  | 407.848
6 |  | 1BHK | 398.1604 | 0 | 597.2405 |  |  | 407.848
7 |  | 1BHK | 398.1604 | 0 | 597.2405 |  |  | 407.848
8th Floor (Part Refuge area)
1 |  | 1BHK | 399.6673 | 0 | 599.501 | 8th Floor (Part Refuge area)
2 |  | 1BHK | 399.6673 | 0 | 599.501
3 |  | 1BHK | 399.6673 | 0 | 599.501
4 |  | 2BHK | 679.6659 | 0 | 1019.4988
5 |  | 1BHK | 398.1604 | 0 | 597.2405
- |  | Refuge Area | [5 empty] | 1BHK | 399.6673
6 |  | 1BHK | 398.1604 | 0 | 597.2405
10th Floor ( Part Society Office, Drivers Room )
1 |  | 1BHK | 399.6673 | 414.8446 | 703.2121 | 10th Floor ( Part Society Office, Drivers Room )
2 |  | 1BHK | 399.6673 | 414.8446 | 703.2121 |  |  | 568.5545
3 |  | 2BHK | 679.6659 | 0 | 1019.4988
4 |  | 1BHK | 398.1604 | 0 | 597.2405
5 |  | 1RK | 256.1294 | 142.4077 | 455.3979
6 |  | Society Office, Drivers Room
C Wing
Ground Floor For Parking
1st to 7th & 9th Floor
1 |  | 2BHK | 567.6665 | 0 | 851.4997 | 1st to 7th & 9th Floor
2 |  | 2BHK | 567.6665 | 0 | 851.4997
3 |  | 1BHK | 399.6673 | 0 | 599.501
4 |  | 1BHK | 399.6673 | 0 | 599.501
8th Floor (Part Refuge area)
1 |  | 2BHK | 567.6665 | 0 | 851.4997 | 8th Floor (Part Refuge area)
2 |  | 2BHK | 567.6665 | 0 | 851.4997
- |  | Refuge Area | [5 empty] | 1BHK | 399.6673
3 |  | 1BHK | 399.6673 | 0 | 599.501
10th Floor ( Terrace area )
Remarks:
* | Finishing work is in process at the time of Visit.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We Received Upper floor CC for Wing A & C upto 10th floor. Please provide revised approved floor plans.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Siddhivinayak Gaurav
Layout :
Google Map :
Formulas:
Koyanavele = [Koyanavele, row above]
C
A Wing
A
A
B
B
C
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D55: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted