## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 19/08/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
CPC Name: |  |  |  | Axis Sanpada | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
Date Of Property Visit |  |  |  | 2025-08-11 | [6 empty] | Axis Sanpada |  |  | IBHF Vashi
Name of the builder group |  |  |  | Trio Infrastructure Private Limited | [6 empty] | Axis Badlapur |  |  | IBHF Vashi
Name of the builder company |  |  |  | Trio Infrastructure Private Limited | [9 empty] | IBHF Thane
Name of the Project |  |  |  | Sereno | [9 empty] | IBHF Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | NA
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Shiv Pandey 7398255197
Name / No of the Building |  |  |  | Sector III - Building No.3 (Wing E & H)
Name / No of the Existing Building |  |  |  | NA | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Floor Plans & CC | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P99000053269 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Sereno, Survey No (As per approved CC).81, H.No.18, S.No.82, H.No.1, 2, 3/3, 8/1, 10, S.No.76, Group Housing Scheme, near Gladiolus Tower, Internal Road, Rajavali, Gohkiware, Vasai Road East, Vasai, Palghar - 401208. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No (As per approved CC) |  | 81, H.No.18, S.No.82, H.No.1, 2, 3/3, 8/1, 10, S.No.76, Group Housing Scheme | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Rajavali | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Internal Road |  | Locality/Village |  | Gohkiware | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Vasai Road East |  | District |  | Palghar | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Vasai |  | Pin Code |  | 401208 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Gladiolus Tower |  | Distance from city centre: |  | 4.1 KM from Vasai Road Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Building No.3 (Wing A to D) |  |  | Building No.3 (Wing A to D)
West | NA | Other Plot |  |  | Open Plot
North | NA | 12.00 M/W Internal Road |  |  | Internal Road
South | NA | Building No.2 (Wing D) |  |  | Building No.2 (Wing D)
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.395583,72.847778
Location Link |  | https://maps.app.goo.gl/QzNXDCUksjrUv9SX8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | Not Provided |  |  |  | 0
Permissible FSI |  |  |  | Not Provided |  |  |  | 0
Permissible TDR/Paid FSI |  |  |  | Not Provided |  |  |  | #DIV/0!
Total FSI availaible for the project |  |  |  | Not Provided |  |  |  | #DIV/0!
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | Not Provided |  |  |  | 0
Total number of Buildings |  |  |  | 02 Wing
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Vasai-Virar City Municipal Corporation | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | Not Provided |  |  | Dated | NA | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. (For Wing E) |  | VVCMC/TP/AMEND/VP/0329, 0815 & 0509/246/2023-24 |  |  | Dated | 2024-01-31 | [12 empty] | Vasai-Virar City Municipal Corporation
Approved Floor plan No. (For Wing H) |  | VVCMC/TP/AMEND/VP/0329, 0815 & 0509/246/2023-24 |  |  | Dated | 2024-01-31 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | VVCMC/TP/RDP/VP-0329, 0815 & 0509/246/2023-24 |  |  | Dated | 2024-01-31 | [10 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Sector III - Building No.3 (Wing E) = Gr + P1 & P2 + 1st to 22nd Floor (Residential) Sector III - Building No.3 (Wing H) = Gr + P1 & P2 + 1st to 22nd Floor (Residential with Shop) | [14 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA)
Fire Noc No Valid Up to: |  | Sector III - Building No.3 (Wing E) = Gr + P1 & P2 + 1st to 22nd Floor (Residential) Sector III - Building No.3 (Wing H) = Gr + P1 & P2 + 1st to 22nd Floor (Residential with Shop) |  |  | Dated | [11 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up to: |  | 0 |  |  | Dated | 0 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved Builtup Area of Wing E & H (Sq.Mt) |  |  | 26031.67
Approved no of units |  |  | Flats - 432, Shops - 17
Approved no of Floors |  |  | Building No.3 (Wing E) = Gr + P1 & P2 + 1st to 22nd Floor Building No.3 (Wing H) = Gr + P1 & P2 + 1st to 22nd Floor
Proposed no of Floors |  |  | Building No.3 (Wing E) = Gr + P1 & P2 + 1st to 28th Floor
Building No.3 (Wing H) = Gr + P1 & P2 + 1st to 28th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Jogging Track, Sauna Bath, Multipurpose Hall, Entrance Lobby, Barbecue Area, Children's Play Area, Yoga/Meditation Area, Indoor Games, Amphitheater, Steam Room, Party Lawn, Gazebo, Partial Power Backup, Car Parking, CCTV, Conference Room, Cafeteria, Library, Gymnasium, Swimming Pool, Lift(s), 24x7 Security, Kid's Pool etc. |  |  |  |  | https://housing.com/in/buy/projects/page/309186-ava-sereno-by-ava-lifespaces-in-vasai-east
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.3 (Wing E) = Gr + P1 & P2 + 1st to 28th Floor | [5 empty] | Excavation Completed, Plinth work is process
Basement | 0 | Ground | 1 | Podium | 2 | Floors | 28 | Excavation | , Plinth work is process
Stage of construction: |  | Excavation Completed, Plinth work is process | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% | 7.5% |  | 38.75% |  | Excavation in process | 14
Plinth |  | 21 | 75% |  |  |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 28
Construction details: |  | Building No.3 (Wing H) = Gr + P1 & P2 + 1st to 28th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 1 Floor Completed | , RCC upto 7 Slab, Brickwork upto 1 Floor
Basement | 0 | Ground | 1 | Podium | 2 | Floors | 28 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 7 Slab, Brickwork upto 1 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7
Excavation |  | 28 | 100% | 19.3% |  | 51.95% |  | Excavation in process | 14
Plinth |  | 28 | 100% |  |  |  |  | Excavation Completed | 28
RCC (Including podiums) |  | 7 | 22.58% |  |  |  |  | Footing in Process | 7
Brickwork | Brickwork & Internal Plaster | 1 | 3.571% |  |  |  |  | Footing Completed | 14
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 21
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 28
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5600 |  |  | 5200 to 5600 & OC 2L by trupti on 26/06/2025. cost sheet case no. 1805 | [8 empty] | 800000 | 300000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 9000 | [11 empty] | 900000 | 350000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 400000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 500000 | 250000 | 250000
Other Charges |  |  |  |  | 250000 | [11 empty] | 1200000 | 600000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 700000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 800000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 900000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 1000000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000
Recommended rate of Parking |  |  |  |  | 250000 | [11 empty] | 1800000
Distressed valuation of the Property |  |  |  |  | 4480
Sector III (Building No.3)
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing H |  | 17 |  | 2619.6078 |  | 4060.392
Total |  | 17 |  | 2619.6078 |  | 4060.392
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing E |  | 216 |  | 114362.5216 |  | 171872.7303
Wing H |  | 216 |  | 114669.188 |  | 172316.2609
Total |  | 432 |  | 229031.7097 |  | 344188.9912
Grand Total |  | 449 |  | 231651.3174 |  | 348249.3833
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | RERA Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
55%
Sector III (Building No.3)
Wing H | [7 empty] | 10.764
Ground Floor For Commercial, Entrance Lobby & Meter Room
1 |  | Shop | 167.2995 | 0 | 167.2995 | 0 | 259.3142 | 15.5425
2 |  | Shop | 139.2862 | 0 | 139.2862 | 0 | 215.8935
3 |  | Shop | 175.6954 | 0 | 175.6954 | 0 | 272.3279
4 |  | Shop | 220.3122 | 0 | 220.3122 | 0 | 341.4839 | 20.4775
5 |  | Shop | 185.7059 | 0 | 185.7059 | 0 | 287.8442
6 |  | Shop | 103.7381 | 0 | 103.7381 | 0 | 160.794
7 |  | Shop | 115.0402 | 0 | 115.0402 | 0 | 178.3124
8 |  | Shop | 115.0402 | 0 | 115.0402 | 0 | 178.3124
9 |  | Shop | 105.5948 | 0 | 105.5948 | 0 | 163.672
10 |  | Shop | 185.7059 | 0 | 185.7059 | 0 | 287.8442
11 |  | Shop | 183.1225 | 0 | 183.1225 | 0 | 283.84
12 |  | Shop | 96.876 | 0 | 96.876 | 0 | 150.1578 | 40.795
13 |  | Shop | 170.5018 | 0 | 170.5018 | 0 | 264.2777
14 |  | Shop | 117.22 | 0 | 117.22 | 0 | 181.6909 | 27.4975
15 |  | Shop | 231.8835 | 0 | 231.8835 | 0 | 359.4194
16 |  | Shop | 139.2862 | 0 | 139.2862 | 0 | 215.8935
17 |  | Shop | 167.2995 | 0 | 167.2995 | 0 | 259.3142
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | RERA Carpet area | AP Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
[7 empty] | 50% | 230
Sector III (Building No.3)
Wing E
Ground Floor For Entrance Lobby, Meter Room & Parking
1st & 2nd Podium Floor For Parking
1st Floor For Residential
1 |  | 1BHK | 389.5492 | 60.9512 | 450.5003 | 0 | 675.7505 | 25.3525 | 7.75 | 33.1025
2 |  | 1BHK | 389.5492 | 60.9512 | 450.5003 | 0 | 675.7505
3 |  | 2BHK | 545.9501 | 86.3811 | 632.3312 | 0 | 948.4968 | 43.4375
4 |  | 2BHK | 548.7487 | 0 | 548.7487 | 136.2722 | 891.2592
5 |  | 1BHK | 391.0561 | 0 | 391.0561 | 123.0325 | 648.1004
6 |  | 1BHK | 386.9658 | 0 | 386.9658 | 123.0325 | 641.965
7 |  | 1BHK | 391.083 | 0 | 391.083 | 123.0325 | 648.1408
8 |  | 2BHK | 564.8947 | 0 | 564.8947 | 152.5259 | 923.605
9 |  | 2BHK | 562.9572 | 86.3811 | 649.3383 | 0 | 974.0074
10 |  | 1BHK | 389.0648 | 61.7585 | 450.8232 | 0 | 676.2348
2nd to 4th, 6th to 9th, 11th to 14th, 16th to 19th, 21st & 22nd Floor
1 |  | 1BHK | 389.5492 | 60.9512 | 450.5003 | 0 | 675.7505
2 |  | 1BHK | 389.5492 | 60.9512 | 450.5003 | 0 | 675.7505
3 |  | 2BHK | 545.9501 | 86.3811 | 632.3312 | 0 | 948.4968
4 |  | 2BHK | 548.7487 | 86.3811 | 635.1298 | 0 | 952.6947
5 |  | 1BHK | 391.0561 | 62.1621 | 453.2182 | 0 | 679.8273 | 4007033.048 | -7033.048
6 |  | 1BHK | 386.9658 | 62.1621 | 449.1279 | 0 | 673.6919
7 |  | 1BHK | 391.083 | 61.7585 | 452.8415 | 0 | 679.2622
8 |  | 2BHK | 564.8947 | 86.3811 | 651.2758 | 0 | 976.9137
9 |  | 2BHK | 562.9572 | 86.3811 | 649.3383 | 0 | 974.0074
10 |  | 1BHK | 389.0648 | 61.7585 | 450.8232 | 0 | 676.2348
5th, 10th, 15th & 20th Floor (Part Refuge Area)
1 |  | 1BHK | 389.5492 | 60.9512 | 450.5003 | 0 | 675.7505
2 |  | 1BHK | 389.5492 | 60.9512 | 450.5003 | 0 | 675.7505
3 |  | 2BHK | 545.9501 | 86.3811 | 632.3312 | 0 | 948.4968
4 |  | 2BHK | 548.7487 | 86.3811 | 635.1298 | 0 | 952.6947
5 |  | Refuge Area
6 |  | 2BHK | 485.3488 | 84.3628 | 569.7116 | 0 | 854.5674
7 |  | 1BHK | 391.083 | 61.7585 | 452.8415 | 0 | 679.2622
8 |  | 2BHK | 564.8947 | 86.3811 | 651.2758 | 0 | 976.9137
9 |  | 2BHK | 562.9572 | 86.3811 | 649.3383 | 0 | 974.0074
10 |  | 1BHK | 389.0648 | 61.7585 | 450.8232 | 0 | 676.2348
Wing H
1st & 2nd Podium Floor For Parking
1st Floor For Residential
1 |  | 1BHK | 389.0648 | 61.7585 | 450.8232 | 0 | 676.2348
2 |  | 2BHK | 562.9572 | 86.3811 | 649.3383 | 0 | 974.0074
3 |  | 2BHK | 564.8947 | 0 | 564.8947 | 152.5259 | 923.605
4 |  | 1BHK | 391.083 | 0 | 391.083 | 123.0325 | 648.1408
5 |  | 1BHK | 393.0206 | 0 | 393.0206 | 107.2094 | 643.1355
6 |  | 1BHK | 391.5136 | 0 | 391.5136 | 105.9178 | 640.2293
7 |  | 2BHK | 548.7487 | 0 | 548.7487 | 136.2722 | 891.2592
8 |  | 2BHK | 545.9501 | 86.3811 | 632.3312 | 0 | 948.4968
9 |  | 1BHK | 391.702 | 62.5657 | 454.2677 | 0 | 681.4016
10 |  | 1BHK | 391.702 | 62.5657 | 454.2677 | 0 | 681.4016
2nd to 4th, 6th to 9th, 11th to 14th, 16th to 19th, 21st & 22nd Floor
1 |  | 1BHK | 389.0648 | 61.7585 | 450.8232 | 0 | 676.2348 |  | 5100.2991
2 |  | 2BHK | 564.8947 | 86.3811 | 651.2758 | 0 | 976.9137 |  | 5060.8358
3 |  | 2BHK | 562.9572 | 86.3811 | 649.3383 | 0 | 974.0074
4 |  | 1BHK | 391.083 | 61.7585 | 452.8415 | 0 | 679.2622
5 |  | 1BHK | 393.0206 | 62.1621 | 455.1827 | 0 | 682.774
6 |  | 1BHK | 391.5136 | 62.1621 | 453.6757 | 0 | 680.5135
7 |  | 2BHK | 548.7487 | 86.3811 | 635.1298 | 0 | 952.6947
8 |  | 2BHK | 545.9501 | 86.3811 | 632.3312 | 0 | 948.4968
9 |  | 1BHK | 391.702 | 62.5657 | 454.2677 | 0 | 681.4016
10 |  | 1BHK | 391.702 | 62.5657 | 454.2677 | 0 | 681.4016
5th, 10th, 15th & 20th Floor (Part Refuge Area)
1 |  | 1BHK | 389.0648 | 61.7585 | 450.8232 | 0 | 676.2348
2 |  | 2BHK | 562.9572 | 86.3811 | 649.3383 | 0 | 974.0074
3 |  | 2BHK | 564.8947 | 86.3811 | 651.2758 | 0 | 976.9137
4 |  | 1BHK | 391.083 | 61.7585 | 452.8415 | 0 | 679.2622
5 |  | 2BHK | 491.269 | 84.3628 | 575.6318 | 0 | 863.4477
6 |  | Refuge Area
7 |  | 2BHK | 548.7487 | 86.3811 | 635.1298 | 0 | 952.6947
8 |  | 2BHK | 545.9501 | 86.3811 | 632.3312 | 0 | 948.4968
9 |  | 1BHK | 391.702 | 62.5657 | 454.2677 | 0 | 681.4016
10 |  | 1BHK | 391.702 | 62.5657 | 454.2677 | 0 | 681.4016
Remarks:
* | Wing E & H = Construction work is in process at the time of Visit. (Slow Speed)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net Carpet + Enclose Balcony + A.P Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate.
* | Provide approved layout plan with area statement sheet.
* | Recommended Rates/Other Charges of the Property have been revised on 26/06/2025.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Shruti Tathare
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sereno
Layout :
Google Map :
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C56: SACHIN: Floor with height
Note on C58: SACHIN: Survey Nos.
Note on C60: SACHIN: Height from AMSL
Note on D63: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F108: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H153: SACHIN: Give loading of 50% for A Category
Wing H
Wing E
Wing H
Wing E
Sector III Building No.3 (Wing H)
Sector III Building No.3 (Wing E)
Wing E
Wing H

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14
15
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate