## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com | [8 empty] | Building No 2 Construction detaile changes.
Valuation Report | [8 empty] | Due to Site engineer not identified Building No 2 on previous visit construction stage given zero
Date: |  |  |  | 13/08/2025
CPC Name: |  |  |  | Axis Sanpada |  |  |  |  | Construction percentage completed given on date 08/08/2024
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | M/s. Space Edge Projects Pvt Ltd
Name of the builder company |  |  |  | M/s. Space Edge Projects Pvt Ltd
Name of the Project (As Per Builder) |  |  |  | Tulip Heights
Name of the Project (As per RERA) |  |  |  | Tulip Apartment
Contact Details ( Name & Contact No.) |  |  |  | Sharmila Shashi Kedar - 9820280813/9372790343
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Nikita 9136403727 |  |  |  | Mr. Francis 8530122727
Name / No of the Building |  |  |  | Building No.1 & Building No.2(Wing A & B)
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. & Name |  |  |  | P51700022565 - Tulip Apartment
Project location details |  | Tulip Heights, Survey No.43, H.No.2/1, near Rajbhar Arcade, Church Road, Katemanevali, Kalyan East, Kalyan, Thane - 421306.
Survey No |  | 43, H.No.2/1
Road |  | Church Road |  | Locality/Village |  | Katemanevali
City |  | Kalyan East |  | District |  | Thane
Taluka |  | Kalyan |  | Pin Code |  | 421306
Nearby Landmark |  | Rajbhar Arcade |  | Distance from city centre: |  | 3.2Km from Vitthalwadi Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Chruch Road
West | NA | NA |  |  | Rajbhar Arcade
North | NA | NA |  |  | Seven Stars CHS
South | NA | NA |  |  | Shashank CHS Ltd
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.2213564593,73.1398613
Location Link |  | https://goo.gl/maps/QwYuScKkZB5ydtbk8?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 4450.52
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | -4.4939e-07
Total FSI availaible for the project |  |  |  | 1.1
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 4895.57
Total number of Buildings |  |  |  | 3 Wings
Approval Detail : Plan approval
Layout Approval No |  | KDMC/TPD/BP/KD/2019-20/0041/158 |  |  | Dated | 2021-03-22
Approved Floor plan No. |  | KDMC/TPD/BP/KD/2019-20/0041/158 |  |  | Dated | 2021-03-22
Commencement Certificate No. Valid Up to: |  | KDMC/TPD/BP/KD/2019-20/0041/208 |  |  | Dated | 2023-09-22
Building No.1 = Natural Stilt + Gr/St + 1st to 23rd Floor (Resi. + Comm.) + 24th Floor (pt) (Recreational Floor) (2nd + 3rd Floor (Pt) for Mhada) Building No.2(Wing A) = Gr + 1st to 7th Floor (Residential) Building No.2(Wing B) = Gr + 1st to 11th Floor (Residential)
O. Certificate No.: |  | NA Approved upto : NA |  | Date of approval: | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 4895.57
Approved no of units |  |  | Sale Flats - 228, Shops - 18, Mhada Flats - 24
Approved no of Floors |  |  | Building No.1 = B + Gr + 1st to 22nd Floor (2nd, 3rd Floor for Mhada) Building No.2(Wing A) = Gr + 1st to 7th Floor Building No.2(Wing B) = Gr + 1st to 11th Floor
Proposed no of Floors |  |  | Building No.1 = B+ Gr/St + 1st to 24th Floor
Building No.2(Wing A) = Gr + 1st to 7th Floor
Building No.2(Wing B) = Gr + 1st to 11th Floor
Expected Completion |  |  | As per RERA - 30/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Construction details: Building No.1 |  | Part 1(Flat No. 4 to 9) - Building No.1= B+ Gr/St + 1st to 24th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 22 Floor, External Plaster upto 15 Floor, Flooring upto 1 Floor Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 24
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 22 Floor, External Plaster upto 15 Floor, Flooring upto 1 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 71.04% |  | 87.92% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 25 | 100% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 24 | 100% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 22 | 91.67% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 62.5% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 1 | 4.167% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 24
Construction details: Building No.1 |  | Part 2 (Flat No. 1, 2, 3, 10, 11 & 12) - Building No.1 = B+ Gr/St + 1st to 24th Floor | [5 empty] | Excavation work Completed. Plinth work completed, RCC upto 24 Slab, Brickwork upto 19 Floor, Internal Plaster upto 12 Floor Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 24
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 24 Slab, Brickwork upto 19 Floor, Internal Plaster upto 12 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% | 58.09% |  | 80.26% |  | Excavation in process | 12
Plinth |  | 24 | 100% |  |  |  |  | Excavation Completed | 24
RCC (Including podiums) |  | 24 | 96% |  |  |  |  | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 19 | 79.17% |  |  |  |  | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 12 | 50% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 18
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 24
Progress % |  | 64.56% |  | Disbursement % |  | 84.09%
Construction details: |  | Building No.2(Wing A) = Gr + 1st to 7th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75 | Due to Site engineer not identified Building No 2 on previous visit construction stage given zero
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0 | Construction percentage completed given on date 08/08/2024
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Possession |  | 7 | 100% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.2(Wing B) = Gr + 1st to 11th Floor | [5 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 11
Stage of construction: |  | All work completed. Please provide OC. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.75
Excavation |  | 11 | 100% | 100% |  | 100% |  | Excavation in process | 5.5
Plinth |  | 11 | 100% |  |  |  |  | Excavation Completed | 11
RCC (Including podiums) |  | 12 | 100% |  |  |  |  | Footing in Process | 2.75
Brickwork | Brickwork & Internal Plaster | 11 | 100% |  |  |  |  | Footing Completed | 5.5
Internal Plaster | Brickwork & Internal Plaster | 11 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 11 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 11 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 11 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 11 | 100% |  |  |  |  | Plinth in process | 8.25
Possession |  | 11 | 100% |  |  |  |  | Plinth completed | 11
Wheather the construction is as per approved Building plan : |  |  |  |  | Under Construction
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 5700
Recommended rate of the shop Per Sq. Ft. ( on Saleable area) |  |  |  |  | 10000
Recommended rate of the Office Per Sq. Ft. ( on Saleable area)
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Club Charges |  |  |  |  | NA
Legal Services Charges |  |  |  |  | NA
Gas Connection Charges |  |  |  |  | NA
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  |  |  | 150000
Distressed valuation of the Property |  |  |  |  | 4560
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Bldg No.1 | Shop | 18 |  | 3310.0376 |  | 5296.0602 |  |  | 121385.0278
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Bldg No.1 |  | 158 |  | 81284.1307 |  | 121926.1961
Bldg No.2 | Wing A | 47 |  | 18403.5606 |  | 27605.3409
| Wing B | 47 |  | 18387.2988 |  | 27580.9482
Total |  | 252 |  | 118074.9901 |  | 177112.4852
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
60%
Building No.1
Ground Floor for Commercial & Parking
1 |  | Shop | 200.2104 | 0 | 320.3366 | Ground Floor for Commercial & Parking
2 |  | Shop | 150.1578 | 0 | 240.2525
3 |  | Shop | 130.1368 | 0 | 208.2188
4 |  | Shop | 164.7699 | 0 | 263.6319
5 |  | Shop | 190.1191 | 0 | 304.1906
6 |  | Shop | 232.3678 | 0 | 371.7886
7 |  | Shop | 232.3678 | 0 | 371.7886
8 |  | Shop | 190.1191 | 0 | 304.1906
9 |  | Shop | 164.7699 | 0 | 263.6319
10 |  | Shop | 164.7699 | 0 | 263.6319
11 |  | Shop | 190.1191 | 0 | 304.1906
12 |  | Shop | 232.3678 | 0 | 371.7886
13 |  | Shop | 232.3678 | 0 | 371.7886
14 |  | Shop | 190.1191 | 0 | 304.1906
15 |  | Shop | 164.7699 | 0 | 263.6319
16 |  | Shop | 130.1368 | 0 | 208.2188
17 |  | Shop | 150.1578 | 0 | 240.2525
18 |  | Shop | 200.2104 | 0 | 320.3366
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Builiding No.1
Natural Stilt Floor for Parking
1st Floor for Residential
101 |  | 1BHK | 487.7168 | 0 | 731.5753 | 1st Floor for Residential |  | 5686.3596 | 5741.0361
102 |  | 1BHK | 479.6438 | 0 | 719.4658 | 1st Floor for Residential |  | 5782.0681
103 |  | 1BHK | 479.6438 | 0 | 719.4658 | 1st Floor for Residential |  | 5782.0681
104 |  | 1BHK | 479.6438 | 0 | 719.4658 | 1st Floor for Residential |  | 5782.0681
105 |  | 1BHK | 479.6438 | 0 | 719.4658 | 1st Floor for Residential |  | 5782.0681
106 |  | 1BHK | 487.7168 | 0 | 731.5753 | 1st Floor for Residential |  | 5686.3596
107 |  | 2BHK | 746.6987 | 0 | 1120.048 | 1st Floor for Residential |  | 5600.2063 | 5714.0407
108 |  | 1BHK | 479.6438 | 0 | 719.4658 | 1st Floor for Residential
109 |  | 1BHK | 479.6438 | 0 | 719.4658 | 1st Floor for Residential
110 |  | 1BHK | 479.6438 | 0 | 719.4658 | 1st Floor for Residential
111 |  | 1BHK | 479.6438 | 0 | 719.4658 | 1st Floor for Residential
112 |  | 2BHK | 746.6987 | 0 | 1120.048 | 1st Floor for Residential
2nd Floor for MHADA
201 |  | 1BHK | 413.4452 | 0 | 620.1679 | 2nd Floor for MHADA
202 |  | 1BHK | 408.0632 | 0 | 612.0949 | 2nd Floor for MHADA
203 |  | 1BHK | 408.0632 | 0 | 612.0949 | 2nd Floor for MHADA
204 |  | 1BHK | 408.0632 | 0 | 612.0949 | 2nd Floor for MHADA
205 |  | 1BHK | 408.0632 | 0 | 612.0949 | 2nd Floor for MHADA
206 |  | 1BHK | 413.4452 | 0 | 620.1679 | 2nd Floor for MHADA
207 |  | 2BHK | 600.3083 | 0 | 900.4624 | 2nd Floor for MHADA
208 |  | 1BHK | 408.0632 | 0 | 612.0949 | 2nd Floor for MHADA
209 |  | 1BHK | 408.0632 | 0 | 612.0949 | 2nd Floor for MHADA
210 |  | 1BHK | 408.0632 | 0 | 612.0949 | 2nd Floor for MHADA
211 |  | 1BHK | 408.0632 | 0 | 612.0949 | 2nd Floor for MHADA
212 |  | 2BHK | 600.3083 | 0 | 900.4624 | 2nd Floor for MHADA
3rd Floor for MHADA
301 |  | 1BHK | 413.4452 | 0 | 620.1679 | 3rd Floor for MHADA
302 |  | 1BHK | 408.0632 | 0 | 612.0949 | 3rd Floor for MHADA |  | 42.3325 | 44.56
303 |  | 1BHK | 479.6438 | 0 | 719.4658 | 3rd Floor for MHADA
304 |  | 1BHK | 479.6438 | 0 | 719.4658 | 3rd Floor for MHADA
305 |  | 1BHK | 479.6438 | 0 | 719.4658 | 3rd Floor for MHADA
306 |  | 1BHK | 487.7168 | 0 | 731.5753 | 3rd Floor for MHADA
307 |  | 2BHK | 746.6987 | 0 | 1120.048 | 3rd Floor for MHADA
308 |  | 1BHK | 479.6438 | 0 | 719.4658 | 3rd Floor for MHADA
309 |  | 1BHK | 479.6438 | 0 | 719.4658 | 3rd Floor for MHADA
310 |  | 1BHK | 479.6438 | 0 | 719.4658 | 3rd Floor for MHADA
311 |  | 1BHK | 408.0632 | 0 | 612.0949 | 3rd Floor for MHADA
312 |  | 2BHK | 600.3083 | 0 | 900.4624 | 3rd Floor for MHADA
4th Floor
401 |  | 1BHK | 487.7168 | 0 | 731.5753 | 4th Floor |  | 35.6475
402 |  | 1BHK | 479.6438 | 0 | 719.4658 | 4th Floor |  | 42.3325 | 44.56
403 |  | 1BHK | 479.6438 | 0 | 719.4658 | 4th Floor
404 |  | 1BHK | 479.6438 | 0 | 719.4658 | 4th Floor
405 |  | 1BHK | 479.6438 | 0 | 719.4658 | 4th Floor
406 |  | 1BHK | 487.7168 | 0 | 731.5753 | 4th Floor
407 |  | 2BHK | 746.6987 | 0 | 1120.048 | 4th Floor
408 |  | 1BHK | 479.6438 | 0 | 719.4658 | 4th Floor
409 |  | 1BHK | 479.6438 | 0 | 719.4658 | 4th Floor
410 |  | 1BHK | 479.6438 | 0 | 719.4658 | 4th Floor
411 |  | 1BHK | 479.6438 | 0 | 719.4658 | 4th Floor
412 |  | 2BHK | 746.6987 | 0 | 1120.048 | 4th Floor
5th to 7th Floor(Part Refuge Floor)
501,..,701 |  | Refuge Area |  |  |  | 5th to 7th Floor(Part Refuge Floor) |  |  |  |  | #REF! | #REF! | 701
502,..,702 | [10 empty] | #REF! | #REF! | 702
503,..,703 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | #REF! | #REF! | 703
504,..,704 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | #REF! | #REF! | 704
505,..,705 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | #REF! | #REF! | 705
506,..,706 |  | 1BHK | 487.7168 | 0 | 731.5753 | [5 empty] | #REF! | #REF! | 706
506,..,707 |  | 2BHK | 746.6987 | 0 | 1120.048
506,..,708 |  | 1BHK | 479.6438 | 0 | 719.4658
506,..,709 |  | 1BHK | 479.6438 | 0 | 719.4658
506,..,710 |  | 1BHK | 479.6438 | 0 | 719.4658
506,..,711 |  | Refuge Area
506,..,712
8th Floor(Part Refuge Floor)
501,..,701 |  | Refuge Area |  |  |  | 8th Floor(Part Refuge Floor) |  |  |  |  | #REF! | #REF! | 801
502,..,702 | [10 empty] | #REF! | #REF! | 802
503,..,703 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | #REF! | #REF! | 803
504,..,704 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | #REF! | #REF! | 804
505,..,705 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | #REF! | #REF! | 805
506,..,706 |  | 1BHK | 487.7168 | 0 | 731.5753 | [5 empty] | #REF! | #REF! | 806
506,..,707 |  | 2BHK | 746.6987 | 0 | 1120.048
506,..,708 |  | 1BHK | 479.6438 | 0 | 719.4658
506,..,709 |  | 1BHK | 479.6438 | 0 | 719.4658
506,..,710 |  | 1BHK | 479.6438 | 0 | 719.4658
506,..,711 |  | Refuge Area
506,..,712
9th to 13th Floor(Part Refuge Floor)
901 to 1301 |  | Refuge Area |  |  |  | 9th to 13th Floor(Part Refuge Floor) |  |  |  |  | 901 to 1301 | 901 | 1301
902 to 1302 | [10 empty] | 902 to 1302 | 902 | 1302
903 to 1303 | [10 empty] | 903 to 1303 | 903 | 1303
904 to 1304 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | 904 to 1304 | 904 | 1304
905 to 1305 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | 905 to 1305 | 905 | 1305
906 to 1306 |  | 1BHK | 487.7168 | 0 | 731.5753 | [5 empty] | 906 to 1306 | 906 | 1306
907 to 1307 |  | 2BHK | 746.6987 | 0 | 1120.048 | [5 empty] | 907 to 1307 | 907 | 1307
908 to 1308 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | 908 to 1308 | 908 | 1308
909 to 1309 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | 909 to 1309 | 909 | 1309
910 to 1310 |  | Refuge Area | [8 empty] | 910 to 1310 | 910 | 1310
911 to 1311 | [10 empty] | 911 to 1311 | 911 | 1311
912 to 1312 | [10 empty] | 912 to 1312 | 912 | 1312
14th to 21st Floor(Part Refuge Floor)
1401 to 2101 |  | Refuge Area |  |  |  | 14th to 21st Floor(Part Refuge Floor) |  |  |  |  | 1401 to 2101 | 1401 | 2101
1402 to 2102 | [10 empty] | 1402 to 2102 | 1402 | 2102
1403 to 2103 | [10 empty] | 1403 to 2103 | 1403 | 2103
1404 to 2104 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | 1404 to 2104 | 1404 | 2104
1405 to 2105 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | 1405 to 2105 | 1405 | 2105
1406 to 2106 |  | 1BHK | 487.7168 | 0 | 731.5753 | [5 empty] | 1406 to 2106 | 1406 | 2106
1407 to 2107 |  | 2BHK | 746.6987 | 0 | 1120.048 | [5 empty] | 1407 to 2107 | 1407 | 2107
1408 to 2108 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | 1408 to 2108 | 1408 | 2108
1409 to 2109 |  | 1BHK | 479.6438 | 0 | 719.4658 | [5 empty] | 1409 to 2109 | 1409 | 2109
1410 to 2110 |  | Refuge Area | [8 empty] | 1410 to 2110 | 1410 | 2110
1411 to 2111 | [10 empty] | 1411 to 2111 | 1411 | 2111
1412 to 2112 | [10 empty] | 1412 to 2112 | 1412 | 2112
22nd Floor Part Terrace Part Amenities Floor
Building No.2
Wing A
Ground Floor for Residential
1 |  | 2BHK | 466.0812 | 0 | 699.1218 | Ground Floor for Residential
2 |  | 1BHK | 310.649 | 0 | 465.9736 |  |  | 26.75
3 |  | 1BHK | 310.649 | 0 | 465.9736
4 |  | 1BHK | 310.649 | 0 | 465.9736
5 |  | 1BHK | 310.649 | 0 | 465.9736
1st to 3rd Floor
101 to 301 |  | 2BHK | 509.1372 | 0 | 763.7058 | 1st to 3rd Floor |  |  |  |  | 101 to 301 | 101 | 301
102 to 302 |  | 1BHK | 382.122 | 0 | 573.183 | 1st to 3rd Floor |  |  |  |  | 102 to 302 | 102 | 302
103 to 303 |  | 1BHK | 352.7363 | 0 | 529.1044 | 1st to 3rd Floor |  |  |  |  | 103 to 303 | 103 | 303
104 to 304 |  | 1BHK | 310.649 | 0 | 465.9736 | 1st to 3rd Floor |  |  |  |  | 104 to 304 | 104 | 304
105 to 305 |  | 1BHK | 310.649 | 0 | 465.9736 | 1st to 3rd Floor |  |  |  |  | 105 to 305 | 105 | 305
106 to 306 |  | 2BHK | 466.1888 | 0 | 699.2833 | 1st to 3rd Floor |  |  |  |  | 106 to 306 | 106 | 306
4th Floor
401 |  | 2BHK | 509.1372 | 0 | 763.7058 | 4th Floor
402 |  | 1BHK | 382.122 | 0 | 573.183 | 4th Floor
403 |  | 1BHK | 352.7363 | 0 | 529.1044 | 4th Floor
404 |  | 1BHK | 310.649 | 0 | 465.9736 | 4th Floor
405 |  | 1BHK | 310.649 | 0 | 465.9736 | 4th Floor
406 |  | 2BHK | 466.1888 | 0 | 699.2833 | 4th Floor
5th Floor
501 |  | 2BHK | 542.398 | 0 | 813.5969 | 5th Floor
502 |  | 1BHK | 384.2748 | 0 | 576.4122 | 5th Floor
503 |  | 1BHK | 352.7363 | 0 | 529.1044 | 5th Floor
504 |  | 1BHK | 310.649 | 0 | 465.9736 | 5th Floor
505 |  | 1BHK | 310.649 | 0 | 465.9736 | 5th Floor
506 |  | 2BHK | 466.1888 | 0 | 699.2833 | 5th Floor
6th Floor
601 |  | 2BHK | 542.398 | 0 | 813.5969 | 6th Floor
602 |  | 1BHK | 384.2748 | 0 | 576.4122 | 6th Floor
603 |  | 1BHK | 352.7363 | 0 | 529.1044 | 6th Floor
604 |  | 1BHK | 352.7363 | 0 | 529.1044 | 6th Floor
605 |  | 1BHK | 352.7363 | 0 | 529.1044 | 6th Floor
606 |  | 2BHK | 466.1888 | 0 | 699.2833 | 6th Floor
7th Floor
701 | 701 | 1BHK | 484.8106 | 0 | 727.2158 | 7th Floor
701A | 701A | 1BHK | 489.3584 | 0 | 734.0375 | 7th Floor
702 | 703 | 1BHK | 382.122 | 0 | 573.183 | 7th Floor
703 | 704 | 1BHK | 352.7363 | 0 | 529.1044 | 7th Floor
704 | 705 | 1BHK | 352.7363 | 0 | 529.1044 | 7th Floor
705 | 706 | 2BHK | 489.2238 | 0 | 733.8357 | 7th Floor
Wing B
Ground Floor for Residential
1 |  | 2BHK | 466.8347 | 0 | 700.252 | Ground Floor for Residential
2 |  | 1BHK | 310.649 | 0 | 465.9736 | Ground Floor for Residential
3 |  | 2BHK | 437.0184 | 0 | 655.5276 | Ground Floor for Residential
1st to 3rd Floor
101 to 301 |  | 2BHK | 473.2931 | 0 | 709.9396 | 1st to 3rd Floor |  |  |  |  | 101 to 301 | 101 | 301
102 to 302 |  | 1BHK | 310.649 | 0 | 465.9736 | 1st to 3rd Floor |  |  |  |  | 102 to 302 | 102 | 302
103 to 303 |  | 1BHK | 310.649 | 0 | 465.9736 | 1st to 3rd Floor |  |  |  |  | 103 to 303 | 103 | 303
104 to 304 |  | 2BHK | 466.6194 | 0 | 699.9291 | 1st to 3rd Floor |  |  |  |  | 104 to 304 | 104 | 304
4th Floor
401 |  | 2BHK | 473.2931 | 0 | 709.9396 | 4th Floor
402 |  | 1BHK | 310.1296 | 0 | 465.1943 | 4th Floor
403 |  | 1BHK | 310.649 | 0 | 465.9736 | 4th Floor
404 |  | 2BHK | 466.6194 | 0 | 699.9291 | 4th Floor
5th Floor
501 |  | 2BHK | 473.2931 | 0 | 709.9396 | 5th Floor
502 |  | 1BHK | 310.649 | 0 | 465.9736 | 5th Floor
503 |  | 1BHK | 310.649 | 0 | 465.9736 | 5th Floor
504 |  | 2BHK | 466.6194 | 0 | 699.9291 | 5th Floor
6th Floor
601 |  | 2BHK | 473.2931 | 0 | 709.9396 | 6th Floor
602 |  | 1BHK | 310.649 | 0 | 465.9736 | 6th Floor
603 |  | 1BHK | 310.649 | 0 | 465.9736 | 6th Floor
604 |  | 2BHK | 466.6194 | 0 | 699.9291 | 6th Floor
7th Floor
701 |  | 2BHK | 473.2931 | 0 | 709.9396 | 7th Floor
702 |  | 1BHK | 310.649 | 0 | 465.9736 | 7th Floor
703 |  | 1BHK | 310.649 | 0 | 465.9736 | 7th Floor
704 |  | 2BHK | 466.6194 | 0 | 699.9291 | 7th Floor
8th Floor(Part Refuge Floor)
801 |  | 2BHK | 473.2931 | 0 | 709.9396 | 8th Floor(Part Refuge Floor)
802 |  | 1BHK | 310.649 | 0 | 465.9736
803 |  | 1BHK | 310.649 | 0 | 465.9736
804 |  | 2BHK | 466.6194 | 0 | 699.9291
9th to 11th Floor
901 to 1101 |  | 2BHK | 473.2931 | 0 | 709.9396 | 9th to 11th Floor |  |  |  |  | 901 to 1101 | 901 | 1101
902 to 1102 |  | 1BHK | 310.649 | 0 | 465.9736 | 9th to 11th Floor |  |  |  |  | 902 to 1102 | 902 | 1102
903 to 1103 |  | 1BHK | 310.649 | 0 | 465.9736 | 9th to 11th Floor |  |  |  |  | 903 to 1103 | 903 | 1103
904 to 1104 |  | 2BHK | 466.6194 | 0 | 699.9291 | 9th to 11th Floor |  |  |  |  | 904 to 1104 | 904 | 1104
Remarks:
1 | Buildng No.1(Part 1& 2) - Construction work is in process at the time of Visit. Building No.2 - All work completed. Please provide OC.
2 | We considered Saleable area as per our calculation.
3 | We considered Carpet area as per Approved Plan.
4 | We considered Gross carpet area = Net carpet + Enclose balcony.
5 | We have considered rate by verifying it from market inquire.
5 | Car parking is subjected to authentic documentation.
6 | Construction details are taken from Mr. Francis 8530122727.
7 | On Site, we meet Ms. Reshma (8108677384).
7 | We have updated revised approved CC From RERA (on 08/05/2024 & 13/08/2025).
9 | Construction work of Building No.1 (Part 1) goes beyond approved plans. Provide revised plans dtd.22/09/2023
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh Laxman Bapardekar |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Tulip Heights
Layout
Sale Plan
Google Map :
Formulas:
Katemanevali = [Katemanevali, row above]
01
01
01
01
Building No. 1 (Part 1)
Building No. 1 (Part 2)
01
01
Bldg 1
Part 2
Bldg 1
Part 1
Bldg 1
Part 1
Bldg 1
Part 2
Bldg 1
Part 1
Bldg 1
Part 1
Bldg 1
Part 2

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
202 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0