## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 14/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-12
Name of the builder group |  |  |  |  | M/s.Imtiaz Saigara & Ahmedi Delawala
Name of the builder company |  |  |  |  | M/s.Imtiaz Saigara & Ahmedi Delawala
Name of the Project |  |  |  |  | White Pearl
Docouments Provided |  |  |  |  | 1. Copy of Plans. 2. Copy of CC.
RERA No. |  |  |  |  | P51900007731
Project location details |  | White Pearl, CTS No.1027 & 1028, Byculla, Building No.33-35, 226-230 MA Road, Byculla, Mumbai 400008
CTS No |  | 1027 & 1028 |  |  | Locality |  | MA Road, Byculla.
Road |  | MA Road |  |  | District |  | Mumbai
City |  | Byculla |  |  | Pin Code |  | 400008
Near by Landmark |  | Near Ahmed Umar Mills |  |  | Distance from city centre: |  | About 1.4 Km from By Sandhurst Road Railway Station.
Accessibility of the project from the city:(Proximities to civic amenities like school, hospital & market,etc.) |  |  |  |  | all available at 1 to 2 km.
Does the property have electricity/water/Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Residential
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Building/Road |  | Building |  | Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Framed Structure
Latitude & Longitude |  | 18.9629013,72.8280238
Location Link |  | https://maps.app.goo.gl/t8FH48gZLrNwduzW6 |  | 18.9629013,72.8280238
Approval details:
Approved usage of the Property: Residential & Commercial. (Restrictive convenants in regards to land use , if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 1044.3
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 1.85
Total FSI availaible for the project |  |  |  |  | 3.85
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 4023.81
Total number of Buildings |  |  |  |  | 1
Approval Detail : Plan approval
Approved Layout Plan : |  | EEBP/4807/E/4 |  |  |  | Dated | 22/09/2016.
Layout Approval No |  | EEBP/4807/E/4 |  |  |  | Dated | 22/09/2016.
Building plan approval No |  | EEBP/4807/E/4 |  |  |  | Dated | 22/09/2016.
C.certificate No Valid Up to: |  | EB/4807/E/A/FCC/2/Amend This C.C. is further extended upto 5th floor top ie Full C.C. of phase – II as per amended approved plans dt. 22.09.2016 |  |  |  | Dated Expiry date: | 29/08/2022 10/06/2023
Part O. Certificate No.: |  | EB/4807/E/A/OCC/1/New Approved Floor : Rehab tenements only from 6th to 17th floor as marked. |  |  | Date of approval: NA | Dated | 03/01/2020. | Expiry date: NA
Commencement date of construction |  |  | 2017-08-17 |  | Expected Completion |  | 2027-12-31
Building wise Construction details | [10 empty] | DATE Constriction as per RERAS VERUFIED ARECHTITECT CERTIFICATE14/08/2025
Approved area of the building in Sq.Mt |  |  | 4023.81 |  | Approved no of units residential |  |  | 103
Approved no of Floors |  |  | Gr +1st Floor for Amenities and Parking + 2nd to 5th Podium + 6th to 20th floor | [7 empty] | 5
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details:
Construction details: |  | Gr +1st Floor for Amenities and Parking + 2nd to 5th Podium + 6th to 20th floor | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 20
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 5
Excavation |  | 20 | 100% |  | 93.25% |  | 96.75% |  | Excavation in process | 10
Plinth |  | 20 | 100% | [5 empty] | Excavation Completed | 20
RCC (Including podiums) |  | 21 | 100% | [5 empty] | Footing in Process | 5
Brickwork | Brickwork & Internal Plaster | 19 | 95% | [5 empty] | Footing Completed | 10
Internal Plaster | Brickwork & Internal Plaster | 17 | 85% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 17 | 85% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 17 | 85% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 17 | 85% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 17 | 85% | [5 empty] | Plinth in process | 15
Possession |  | 17 | 85% | [5 empty] | Plinth completed | 20
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Carpet Area) | [5 empty] | 31500 |  |  |  | 21724.1379
Floor rise rate Per Sq. Ft. | [5 empty] | NA
Society formation charges | [5 empty] | 2,50,000/-
Recommended rate of Parking | [5 empty] | 5,00,000/-
Development charges | [5 empty] | 3,00,000/-
Valuation as per Government reckoners rates | [5 empty] | NA
Distress valuation of the property Per Sq. Ft. | [5 empty] | 25200
Building details floor wise
Details of Flats in Building
Sr. | Flat No. | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area | PLC Y/N
Ground Floor For Commercial
1st to 5th Floor Parking & REHAB
6th Floor
1 | 1 | 1BHK | 285.8918 | 46.0807 | 331.9725 | 0 | 481.3602 | NA |  | 1.45
7th Floor
2 | 1 | 1BHK | 281.6939 | 0 | 281.6939 | 0 | 408.4561 | NA
3 | 2 | 1BHK | 311.0796 | 68.8175 | 379.8971 | 0 | 550.8508 | NA
4 | 3 | 1BHK | 281.6939 | 76.559 | 358.2528 | 0 | 519.4666 | NA
8th Floor
5 | 1 | 1BHK | 261.2423 | 0 | 261.2423 | 0 | 378.8013 | NA
6 | 2 | 1BHK | 278.2494 | 46.0807 | 324.3301 | 0 | 470.2786 | NA
9th Floor
7 | 1 | 1BHK | 183.3109 | 0 | 183.3109 | 0 | 265.8008 | NA
8 | 2 | 1BHK | 278.2494 | 46.0807 | 324.3301 | 0 | 470.2786 | NA
9 | 3 | 1BHK | 311.0796 | 103.5927 | 414.6723 | 0 | 601.2749 | NA
10th Floor
10 | 1 | 1BHK | 268.6694 | 0 | 268.6694 | 0 | 389.5707 | NA
11 | 2 | 1BHK | 278.2494 | 46.0807 | 324.3301 | 0 | 470.2786 | NA
12 | 3 | 1BHK | 311.0796 | 103.5927 | 414.6723 | 0 | 601.2749 | NA
11th Floor
13 | 1 | 1BHK | 143.8243 | 0 | 143.8243 | 0 | 208.5452 | NA
14 | 2 | 1BHK | 278.2494 | 0 | 278.2494 | 0 | 403.4616 | NA
15 | 3 | 1BHK | 311.0796 | 103.5927 | 414.6723 | 0 | 601.2749 | NA
12th Floor
16 | 1 | 1BHK | 198.5958 | 0 | 198.5958 | 0 | 287.9639 | NA
17 | 2 | 1BHK | 278.2494 | 0 | 278.2494 | 0 | 403.4616 | NA
18 | 3 | 1BHK | 311.0796 | 103.5927 | 414.6723 | 0 | 601.2749 | NA
13th to 14th & 16 to 20th Floor
19 | 1 | 1BHK | 303.2219 | 0 | 303.2219 | 0 | 439.6717 | NA
20 | 2 | 1BHK | 290.9509 | 110.331 | 401.2819 | 0 | 581.8588 | NA
21 | 3 | 1BHK | 278.2494 | 0 | 278.2494 | 0 | 403.4616 | NA
22 | 4 | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 435.1455 | NA
23 | 5 | 1BHK | 300.1003 | 0 | 300.1003 | 0 | 435.1455 | NA
24 | 6 | 1BHK | 311.0796 | 103.5927 | 414.6723 | 0 | 601.2749 | NA
25 | 7 | 1BHK | 311.0796 | 103.5927 | 414.6723 | 0 | 601.2749 | NA
15th Floor
26 | 1 | 1BHK | 290.9509 | 110.331 | 401.2819 | 0 | 581.8588 | NA
27 | 2 | 1BHK | 164.9045 | 0 | 164.9045 | 0 | 239.1115 | NA
28 | 3 | 1BHK | 311.0796 | 103.5927 | 414.6723 | 0 | 601.2749 | NA
29 | 4 | 1BHK | 311.0796 | 103.5927 | 414.6723 | 0 | 601.2749 | NA | 9. As per RERA, completion period of project is expired on 30/12/2023. but still project work is pending.
Remraks: 1. OC received from 6th to 17th floor. Upper floor 18th to 20th floor & Parking floor - Construction Work same as last visit (dtd 06/02/2024) 2. Builder flat sale on carpet area as per given site details. 3. REHAB (Rehabilitation) Flats is not for sale so our valuation report only for sale flats. 4. We considered flat description as per builder sale plan. 5. We have considered rate by verifying it from market inquire. 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. Validity of CC is expired on 10/06/2023. Please provide revised CC.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : White Pearl
s
Google Map :
This construction work is in process.
Pending Work

## C %
Particulars | totaL floor | 20
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 90.4762 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 21 | 19 | 87.5 | Progress |  |  | 10 | 36.1905 | 13.125 | 8.5 | 8.5 | 4.25 | 4.25
Bricks | Total Floor | completed Floor | 85 | Recommended |  |  | 30 | 27.1429 | 13.125 | 8.5 | 4.25 | 4.25 | 4.25
| 20 | 17.5 | 85
plaster | Total Floor | completed Floor | 85
| 20 | 17 | 85
Flooring | Total Floor | completed Floor
| 20 | 17 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 20 | 17 |  | RCC | 36.1905 | 27.1429
Finishing | Total Floor | completed Floor |  | Bricks | 13.125 | 13.125
| 20 | 17 |  | Plaster | 8.5 | 8.5
|  |  |  | Flooring | 8.5 | 4.25
|  |  |  | Wood & painting | 4.25 | 4.25
|  |  |  | Finishing | 4.25 | 4.25
|  |  |  | total | 84.8155 | 91.5179

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0