## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 20/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-15
Name of the builder group |  |  |  | Veena Developers
Name of the builder company |  |  |  | Veena Developers
Name of the Project |  |  |  | Veena Suyog
Provided Contact Details ( Name & Contact No.) |  |  |  | 02261069800/9773761297
Site Person - Contact Details ( Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | Wing A & B
Name / No of the Existing Building |  |  |  | Ram Shyam Co-operative Housing Society Ltd.
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P51800050707
Project location details |  | Veena Suyog, CTS No.544, 544(1 TO 9), Redevlopement of " Ram Shyam Co-operative Housing Society Ltd ", near Nagindas Khandwala College, Swami Vivekananda Road, , Malad, Malad West, Borivali, Mumbai - 400064.
CTS No |  | 544, 544(1 TO 9), Redevlopement of " Ram Shyam Co-operative Housing Society Ltd "
Locality |  | NA
Road |  | Swami Vivekananda Road |  | Locality/Village |  | Malad
City |  | Malad West |  | District |  | Mumbai
Taluka |  | Borivali |  | Pin Code |  | 400064
Nearby Landmark |  | Nagindas Khandwala College |  | Distance from city centre: |  | 0.950KM from Malad Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Swami Vivekananda Road
West | NA | NA |  |  | Kapol CHSL
North | NA | NA |  |  | Rishikesh Apartment
South | NA | NA |  |  | Girnar Apartments
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.192317052,72.84679132
Location Link |  | https://goo.gl/maps/pRE6uhwdFXkELDh26
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1991.3
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.76417
Total FSI availaible for the project |  |  |  | 1.7642
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 3512.99
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai (MCGM)
Layout Approval No |  | CHE/WSII/4153/P/N/337(NEW) |  |  | Dated | 2022-08-04
Approved Floor plan No. |  | CHE/WSII/4153/P/N/337(NEW) |  |  | Dated | 2022-08-04
Commencement-CC No Valid Up to: |  | CHE/WSII/4153/P/N/337(NEW)/FCC/3/Amend |  |  | Dated | 2025-04-25
|  | This CC is granted for the entire work of building comprising of Wing ‘A’ -basement floor (for pump room only) + ground floor (stilt) + 1st to 21st upper floors + 22nd (part) upper floors and staircase core upto top of LMR/OHT and Wing ‘B’ comprising of Pit Type Puzzle Parking System + Ground Floor Commercial Shop and 1st Floor Business Office as per approved amended plans dt 25.10.2023. |  |  | Valid Upto Date | 2026-02-27
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 3512.99
Approved no of units |  |  | Flats - 68, Shops - 2, Office - 1
Approved no of Floors |  |  | Wing A = B + Gr + 1st to 15th Floor Wing B = Gr + 1st Floor
Proposed no of Floors |  |  | Wing A = B + Gr + 1st to 22nd Floor
Wing B = Gr + 1st Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Indoor Games, Amphitheater, Multipurpose Court, Childrens Play Area, Terrace Garden, Senior Citizen Area, Jogging Track, Gymnasium, Yoga, High Speed elevators, Fire Alarm, CCTV, Fire Fighting
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = B + Gr + 1st to 22nd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 16 Floor, Flooring upto 3 Floor Completed | , External Plaster upto 16 Floor, Flooring upto 3 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 22 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 16 Floor, Flooring upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.5
Excavation |  | 22 | 100% | 73.64% |  | 89.32% |  | Excavation in process | 11
Plinth |  | 22 | 100% |  |  |  |  | Excavation Completed | 22
RCC (Including podiums) |  | 23 | 100% |  |  |  |  | Footing in Process | 5.5
Brickwork | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Footing Completed | 11
Internal Plaster | Brickwork & Internal Plaster | 22 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16 | 72.73% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3 | 13.64% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 16.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 22
Construction details: |  | Wing B = Gr + 1st Floor | [5 empty] | Excavation, Plinth Completed
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 1 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 0.25
Excavation |  | 1 | 100% | 10% |  | 45% |  | Excavation in process | 0.5
Plinth |  | 1 | 100% |  |  |  |  | Excavation Completed | 1 | Plinth completed but not sure 14/02/2025
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 0.25
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 0.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 0.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 1
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 19000 |  |  |  | RATE 19000 + OC = 300000 + PARK 10L
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 45000 |  |  |  | By Akash Mote On 22/07/2024
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 35000
Other Charges |  |  |  |  | 300000
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 1000000
Distressed valuation of the Property |  |  |  |  | 15200
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing B | Shops | 2 |  | 1654.2966 |  | 2646.8745
| Office | 1 |  | 1726.7609 |  | 2762.8174
Total |  | 3 |  | 3381.0574 |  | 5409.6919
Residential Area Details : Flats
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 68 |  | 41251.7383 |  | 63940.1944
Total |  | 68 |  | 41251.7383 |  | 63940.1944
Grand Total |  | 71 |  | 44632.7958 |  | 69349.8863
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Wing B
Ground Floor For Commercial & Parking
1 |  | Shop | 1059.2971 | 0 | 1694.8753 | Ground Floor For Commercial & Parking |  |  | 10.764
2 |  | Shop | 594.9995 | 0 | 951.9992
1st Floor
1 |  | Office | 1726.7609 | 0 | 2762.8174 | 1st Floor
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Wing A
Basement Floor For Pump Room & Tanks
Ground Floor For Meter Room & Double Heighted Entrance Lobby
1st Floor For Part Residential
1 |  | Parking |  |  |  | 1st Floor For Part Residential
2
3 |  | 0 | 313.9859 | 0 | 486.6781 |  |  |  | 27.8781
4 |  | 2 | 597.2944 | 0 | 925.8063 |  |  |  | 52.0525
5 |  | 2 | 611.7181 | 0 | 948.1631
2nd Floor For Part Residential &
1 |  | Society Office & Yogalaya |  |  |  | 2nd Floor For Part Residential &
2
3 |  | 0 | 313.9859 | 0 | 486.6781
4 |  | 2 | 597.2944 | 0 | 925.8063
5 |  | 2 | 611.7181 | 0 | 948.1631
3rd Floor
1 |  | 3 | 887.5994 | 0 | 1375.7791 | 3rd Floor
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 3rd Floor
3 |  | 0 | 313.9859 | 0 | 486.6781 | 3rd Floor
4 |  | 2 | 599.3395 | 0 | 928.9763 | 3rd Floor
5 |  | 2 | 612.1487 | 0 | 948.8305 | 3rd Floor
4th Floor
1 |  | 3 | 887.5994 | 0 | 1375.7791 | 4th Floor
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 4th Floor
3 |  | 0 | 313.9859 | 0 | 486.6781 | 4th Floor
4 |  | 2 | 599.3395 | 0 | 928.9763 | 4th Floor
5 |  | 2 | 612.1487 | 0 | 948.8305 | 4th Floor
5th Floor
1 |  | 3 | 887.5994 | 0 | 1375.7791 | 5th Floor
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 5th Floor
3 |  | 0 | 313.9859 | 0 | 486.6781 | 5th Floor
4 |  | 2 | 599.3395 | 0 | 928.9763 | 5th Floor
5 |  | 2 | 672.8576 | 0 | 1042.9293 | 5th Floor
6th Floor
1 |  | 3 | 887.5994 | 0 | 1375.7791 | 6th Floor
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 6th Floor
3 |  | 1 | 457.7929 | 0 | 709.579 | 6th Floor
4 |  | 1 | 420.98 | 0 | 652.5191 | 6th Floor
5 |  | 2 | 672.8576 | 0 | 1042.9293 | 6th Floor
7th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 7th Floor (Part Refuge Area)
3 |  | 1 | 457.7929 | 0 | 709.579 | 7th Floor (Part Refuge Area)
4 |  | 1 | 420.98 | 0 | 652.5191 | 7th Floor (Part Refuge Area)
5 |  | 2 | 672.8576 | 0 | 1042.9293 | 7th Floor (Part Refuge Area)
8th Floor
1 |  | 3 | 887.5994 | 0 | 1375.7791 | 8th Floor
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 8th Floor
3 |  | 1 | 457.7929 | 0 | 709.579 | 8th Floor
4 |  | 1 | 420.98 | 0 | 652.5191 | 8th Floor
5 |  | 2 | 672.8576 | 0 | 1042.9293 | 8th Floor
9th Floor
1 |  | 3 | 922.5824 | 0 | 1430.0028 | 9th Floor
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 9th Floor
3 |  | 1 | 457.7929 | 0 | 709.579 | 9th Floor
4 |  | 1 | 420.98 | 0 | 652.5191 | 9th Floor
5 |  | 2 | 672.8576 | 0 | 1042.9293 | 9th Floor
10th Floor
1 |  | 3 | 922.5824 | 0 | 1430.0028 | 10th Floor
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 10th Floor
3 |  | 1 | 436.1573 | 0 | 676.0438 | 10th Floor
4 |  | 1 | 420.98 | 0 | 652.5191 | 10th Floor
5 |  | 2 | 672.8576 | 0 | 1042.9293 | 10th Floor
11th to 13th Floor
1 |  | 3 | 922.5824 | 0 | 1430.0028 | 11th to 13th Floor
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 11th to 13th Floor
3 |  | 1 | 436.1573 | 0 | 676.0438 | 11th to 13th Floor
4 |  | 1 | 420.98 | 0 | 652.5191 | 11th to 13th Floor
5 |  | 2 | 672.8576 | 0 | 1042.9293 | 11th to 13th Floor
14th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 14th Floor (Part Refuge Area)
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 14th Floor (Part Refuge Area)
3 |  | 1 | 436.1573 | 0 | 676.0438 | 14th Floor (Part Refuge Area)
4 |  | 1 | 420.98 | 0 | 652.5191 | 14th Floor (Part Refuge Area)
5 |  | 2 | 672.8576 | 0 | 1042.9293 | 14th Floor (Part Refuge Area)
15th Floor (Part Terrace Area)
1 |  | 3 | 922.5824 | 0 | 1430.0028 | 15th Floor (Part Terrace Area)
2 |  | 2 | 683.1911 | 0 | 1058.9462 | 15th Floor (Part Terrace Area)
3 |  | 1 | 436.1573 | 0 | 676.0438 | 15th Floor (Part Terrace Area)
4 |  | 1 | 420.98 | 0 | 652.5191 | 15th Floor (Part Terrace Area)
5 |  | Terrace Area |  |  |  | 15th Floor (Part Terrace Area)
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
Remarks:
* | Wing A & B = Construction work is in process at the time of Visit. Internal photos was not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved CC from MCGM site on 14/11/2024.
* | Recommended Rates / Other charges of the Property have been revised on 22/07/2024.
* | We have updated latest CC from MCGM site (On 14/05/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Roshan Kudalkar |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Veena Suyog
Layout :
Google Map :
Formulas:
Malad = [Malad, row above]
Part I
Part II
Wing B
Wing A
Wing A
Wing A
Wing A

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted