## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/08/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | M/s. Macrotech Developers Limited
Name of the builder company |  |  |  | M/s. Macrotech Developers Limited
Old Name of the Project |  |  |  | Upper Thane - Casa Parkville
New Name of the Project |  |  |  | Upper Thane - Casa Eden
Contact Details ( Name & Contact No.) |  |  |  | 9820248856- Rajendra Giri
Name / No of the Building |  |  |  | Wing A, B & C
Docouments Provided |  |  |  | Approved Plans, CC.
RERA No. |  |  |  | Casa Eden = P51700034837
Project location details |  | Upper Thane - Casa Eden, Survey No.55/12 A, 55/12B (P) & 55/7 of Mankoli 27/1 (P), 28/14, 28/14B & 28/15 of Surai, near Casa Tiara - Lodha Upper Thane, Dombivali Link Road, Surai Mankoli Bhiwandi, Surai (Pt), Mankoli(Pt), Dombivali, Bhiwandi, Thane - 421302.
Survey No |  | 55/12 A, 55/12B (P) & 55/7 of Mankoli 27/1 (P), 28/14, 28/14B & 28/15 of Surai
Locality |  | Surai Mankoli Bhiwandi
Road |  | Dombivali Link Road |  | Village |  | Surai (Pt), Mankoli(Pt)
City |  | Dombivali |  | District |  | Thane
Taluka |  | Bhiwandi |  | Pin Code |  | 421302
Nearby Landmark |  | Casa Tiara - Lodha Upper Thane |  | Distance from city centre: |  | 9.8KM from Kalva Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Open Plot
West | NA | NA |  |  | Casa Tiara - Lodha Upper Thane
North | NA | NA |  |  | Upper Thane Sales Gallery by LODHA
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.2344399,73.0498173
Location Link |  | https://goo.gl/maps/Na6YxkonQDK24Zjm7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 506642.89
Permissible FSI |  |  |  | 1.7
Permissible TDR/Paid FSI |  |  |  | 0.13799
Total FSI availaible for the project |  |  |  | 1.838
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 931203.11
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | MMRDA
Layout Approval No |  | SROT/BSNA/2501/BP/Amended/ITP-Anjur Mankoli,Surai,Sarang & Vehele/966/2022 |  |  | Dated | 2022-07-14
Approved Floor plan No. |  | SROT/BSNA/2501/BP/Amended/ITP-Anjur Mankoli,Surai,Sarang & Vehele/966/2022 |  |  | Dated | 2022-07-14
Commencement-CC No Valid Up to: |  | SROT/BSNA/2501/BP/Amended/ITP-Anjur Mankoli,Surai,Sarang & Vehele/966/2022 |  |  | Dated | 2022-07-14
Wing A, B & C = Gr + 1st to 23rd Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 53530.42
Approved no of units |  |  | Flats - 445
Approved no of Floors |  |  | Wing A, B & C = Gr + 1st to 23rd Floor
Proposed no of Floors |  |  | Wing A, B & C = Gr + 1st to 23rd Floor
B Wing = G + 1st to 20th Floor
C Wing = G + 1st to 20th Floor
Expected Completion |  |  | As per RERA - 31/03/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = Gr + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 22 Floor, Painting upto 20 Floor, Finishing upto 8 Floor Completed | , Flooring upto 22 Floor, Painting upto 20 Floor, Finishing upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 22 Floor, Painting upto 20 Floor, Finishing upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 90.65% |  | 94.78% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 95.65% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 20 | 86.96% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 8 | 34.78% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Wing B = Gr + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 22 Floor, Painting upto 20 Floor, Finishing upto 8 Floor Completed | , Flooring upto 22 Floor, Painting upto 20 Floor, Finishing upto 8 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 22 Floor, Painting upto 20 Floor, Finishing upto 8 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 90.65% |  | 94.78% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 22 | 95.65% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 20 | 86.96% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 8 | 34.78% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Construction details: |  | Wing C = Gr + 1st to 23rd Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 20 Floor, Painting upto 18 Floor, Finishing upto 5 Floor Completed | , Flooring upto 20 Floor, Painting upto 18 Floor, Finishing upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 23 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 20 Floor, Painting upto 18 Floor, Finishing upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 5.75
Excavation |  | 23 | 100% | 88.7% |  | 94.35% |  | Excavation in process | 11.5
Plinth |  | 23 | 100% |  |  |  |  | Excavation Completed | 23
RCC (Including podiums) |  | 24 | 100% |  |  |  |  | Footing in Process | 5.75
Brickwork | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Footing Completed | 11.5
Internal Plaster | Brickwork & Internal Plaster | 23 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 23 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 86.96% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 18 | 78.26% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 5 | 21.74% |  |  |  |  | Plinth in process | 17.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 23
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7500 |  |  | 7200 to 7500 | Sanket | Cost sheet | 2022-11-03
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Utility & Maintenance Charges |  |  |  |  | 110000
Recommended rate of Parking |  |  |  |  | 400000
Distressed valuation of the Property |  |  |  |  | 6000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
A Wing |  | 140 |  | 80302.4539 |  | 120453.6809
B Wing |  | 141 |  | 107383.171 |  | 161074.7564
C Wing |  | 164 |  | 108470.2273 |  | 162705.341
Total |  | 445 |  | 296155.8522 |  | 444233.7783
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor For Residential & Meter Room
1 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
2 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
3 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
4 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
5 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
6 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
7 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
8 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
9 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
10 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
11 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
12 |  |  |  | 0 | 0 | Ground Floor For Residential & Meter Room
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Clustor No. 3.02(B) | [7 empty] | Wing D & E Area is been drafted & checked on dtd 02/08/2022
Wing A
Ground Floor For Residential & Meter Room | [8 empty] | 10.764
1 |  | 2BHK | 542.1827 | 0 | 813.274 | Ground Floor For Residential & Meter Room |  | 45.7619
2 |  | 2BHK | 542.1827 | 0 | 813.274
3 |  | 2BHK | 543.2591 | 0 | 814.8886
4 |  | 2BHK | 543.2591 | 0 | 814.8886
5 |  | 1BHK | 477.7063 | 0 | 716.5595 |  |  |  | 6698.6763
1st & 2nd Floor
1 |  | 2BHK | 573.9365 | 0 | 860.9047 | 1st & 2nd Floor
2 |  | 2BHK | 573.9365 | 0 | 860.9047 |  |  |  | 6737.0986
3 |  | 2BHK | 575.874 | 0 | 863.811
4 |  | 2BHK | 575.874 | 0 | 863.811
5 |  | 2BHK | 575.874 | 0 | 863.811
6 |  | 2BHK | 575.874 | 0 | 863.811
3rd to 7th, 9th to 12th Floor for Residential
1 |  | 2BHK | 573.9365 | 0 | 860.9047 | 3rd to 7th, 9th to 12th Floor for Residential
2 |  | 2BHK | 573.9365 | 0 | 860.9047
3 |  | 2BHK | 575.874 | 0 | 863.811
4 |  | 2BHK | 575.874 | 0 | 863.811
5 |  | 2BHK | 575.874 | 0 | 863.811
6 |  | 2BHK | 575.874 | 0 | 863.811
14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
1 |  | 2BHK | 573.9365 | 0 | 860.9047 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
2 |  | 2BHK | 573.9365 | 0 | 860.9047
3 |  | 2BHK | 575.874 | 0 | 863.811
4 |  | 2BHK | 575.874 | 0 | 863.811
5 |  | 2BHK | 575.874 | 0 | 863.811
6 |  | 2BHK | 575.874 | 0 | 863.811
8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
1 |  | 2BHK | 573.9365 | 0 | 860.9047 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
2 |  | 2BHK | 573.9365 | 0 | 860.9047
3 |  | 2BHK | 575.874 | 0 | 863.811
4 |  | Refuge Area
5 |  | 2BHK | 575.874 | 0 | 863.811
6 |  | 2BHK | 575.874 | 0 | 863.811
Clustor No. 3.02(C)
Wing B
Ground Floor For Residential & Meter Room
1 |  | 3BHK | 728.1846 | 0 | 1092.2769 | Ground Floor For Residential & Meter Room
2 |  | 3BHK | 728.1846 | 0 | 1092.2769
3 |  | 2BHK | 659.0797 | 0 | 988.6196
4 |  | 2BHK | 659.5103 | 0 | 989.2654
5 |  | 1BHK | 563.4954 | 0 | 845.2431
6 |  | 3BHK | 725.1707 | 0 | 1087.756
1st to 7th, 9th to 12th Floor
1 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 1st to 7th, 9th to 12th Floor |  |  | 6792.6292
2 |  | 3BHK | 765.5357 | 0 | 1148.3035
3 |  | 3BHK | 765.5357 | 0 | 1148.3035
4 |  | 3BHK | 764.8898 | 0 | 1147.3348
5 |  | 3BHK | 764.8898 | 0 | 1147.3348
6 |  | 3BHK | 765.5357 | 0 | 1148.3035
14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
1 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
2 |  | 3BHK | 765.5357 | 0 | 1148.3035
3 |  | 3BHK | 765.5357 | 0 | 1148.3035
4 |  | 3BHK | 764.8898 | 0 | 1147.3348
5 |  | 3BHK | 764.8898 | 0 | 1147.3348
6 |  | 3BHK | 765.5357 | 0 | 1148.3035
8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
1 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
2 |  | 3BHK | 765.5357 | 0 | 1148.3035
3 |  | 3BHK | 765.5357 | 0 | 1148.3035
4 |  | Refuge Area
5 |  | 3BHK | 764.8898 | 0 | 1147.3348
6 |  | 3BHK | 765.5357 | 0 | 1148.3035
Clustor No. 3.02(C)
Wing C
Ground Floor For Residential & Meter Room
1 |  | 1BHK | 532.6027 | 0 | 798.9041 | Ground Floor For Residential & Meter Room
2 |  | 2BHK | 629.3711 | 0 | 944.0566
3 |  | 2BHK | 600.3083 | 0 | 900.4624
4 |  | 1BHK | 624.4196 | 0 | 936.6295
6 |  | 2BHK | 624.4196 | 0 | 936.6295
7 |  | 2BHK | 600.3083 | 0 | 900.4624
1st to 7th, 9th to 12th Floor
1 |  | 2BHK | 670.059 | 0 | 1005.0885 | 1st to 7th, 9th to 12th Floor
2 |  | 2BHK | 670.059 | 0 | 1005.0885
3 |  | 2BHK | 660.9096 | 0 | 991.3644
4 |  | 2BHK | 661.1249 | 0 | 991.6873
5 |  | 2BHK | 661.1249 | 0 | 991.6873
6 |  | 2BHK | 661.1249 | 0 | 991.6873
7 |  | 2BHK | 660.9096 | 0 | 991.3644
14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
1 |  | 2BHK | 670.059 | 0 | 1005.0885 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
2 |  | 2BHK | 670.059 | 0 | 1005.0885
3 |  | 2BHK | 660.9096 | 0 | 991.3644
4 |  | 2BHK | 661.1249 | 0 | 991.6873
5 |  | 2BHK | 661.1249 | 0 | 991.6873
6 |  | 2BHK | 661.1249 | 0 | 991.6873
7 |  | 2BHK | 660.9096 | 0 | 991.3644
8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
1 |  | 2BHK | 670.059 | 0 | 1005.0885 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
2 |  | 2BHK | 670.059 | 0 | 1005.0885
3 |  | 2BHK | 660.9096 | 0 | 991.3644
4 |  | 2BHK | 661.1249 | 0 | 991.6873
5 |  | Refuge Area
6 |  | 2BHK | 661.1249 | 0 | 991.6873
7 |  | 2BHK | 660.9096 | 0 | 991.3644
Clustor No. 3.02(C)
Wing D
Ground Floor For Residential & Meter Room
1 |  | 3BHK | 728.1846 | 0 | 1092.2769 | Ground Floor For Residential & Meter Room
2 |  | 3BHK | 728.1846 | 0 | 1092.2769 | Ground Floor For Residential & Meter Room
3 |  | 2BHK | 659.0797 | 0 | 988.6196 | Ground Floor For Residential & Meter Room
5 |  | 1BHK | 563.4954 | 0 | 845.2431 | Ground Floor For Residential & Meter Room
6 |  | 3BHK | 725.1707 | 0 | 1087.756 | Ground Floor For Residential & Meter Room
1st to 7th, 9th to 12th Floor
1 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 1st to 7th, 9th to 12th Floor
2 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 1st to 7th, 9th to 12th Floor
3 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 1st to 7th, 9th to 12th Floor
4 |  | 3BHK | 764.8898 | 0 | 1147.3348 | 1st to 7th, 9th to 12th Floor
5 |  | 3BHK | 764.8898 | 0 | 1147.3348 | 1st to 7th, 9th to 12th Floor
6 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 1st to 7th, 9th to 12th Floor
14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
1 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
2 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
3 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
4 |  | 3BHK | 764.8898 | 0 | 1147.3348 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
5 |  | 3BHK | 764.8898 | 0 | 1147.3348 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
6 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
1 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
2 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
3 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
4 |  | Refuge Area |  |  |  | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
5 |  | 3BHK | 764.8898 | 0 | 1147.3348 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
6 |  | 3BHK | 765.5357 | 0 | 1148.3035 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
Clustor No. 3.02(B)
Wing E
Ground Floor For Residential & Meter Room | [8 empty] | 10.764
1 |  | 2BHK | 542.1827 | 0 | 813.274 | Ground Floor For Residential & Meter Room |  | 45.7619
2 |  | 2BHK | 542.1827 | 0 | 813.274 | Ground Floor For Residential & Meter Room
3 |  | 2BHK | 543.2591 | 0 | 814.8886 | Ground Floor For Residential & Meter Room
4 |  | 2BHK | 543.2591 | 0 | 814.8886 | Ground Floor For Residential & Meter Room
5 |  | 1BHK | 477.7063 | 0 | 716.5595 | Ground Floor For Residential & Meter Room
1st & 2nd Floor
1 |  | 2BHK | 573.9365 | 0 | 860.9047 | 1st & 2nd Floor
2 |  | 2BHK | 573.9365 | 0 | 860.9047 | 1st & 2nd Floor
3 |  | 2BHK | 575.874 | 0 | 863.811 | 1st & 2nd Floor
4 |  | 2BHK | 575.874 | 0 | 863.811 | 1st & 2nd Floor
5 |  | 2BHK | 575.874 | 0 | 863.811 | 1st & 2nd Floor
6 |  | 2BHK | 575.874 | 0 | 863.811 | 1st & 2nd Floor
3rd to 7th, 9th to 12th Floor for Residential
1 |  | 2BHK | 573.9365 | 0 | 860.9047 | 3rd to 7th, 9th to 12th Floor for Residential
2 |  | 2BHK | 573.9365 | 0 | 860.9047 | 3rd to 7th, 9th to 12th Floor for Residential
3 |  | 2BHK | 575.874 | 0 | 863.811 | 3rd to 7th, 9th to 12th Floor for Residential
4 |  | 2BHK | 575.874 | 0 | 863.811 | 3rd to 7th, 9th to 12th Floor for Residential
5 |  | 2BHK | 575.874 | 0 | 863.811 | 3rd to 7th, 9th to 12th Floor for Residential
6 |  | 2BHK | 575.874 | 0 | 863.811 | 3rd to 7th, 9th to 12th Floor for Residential
14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
1 |  | 2BHK | 573.9365 | 0 | 860.9047 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
2 |  | 2BHK | 573.9365 | 0 | 860.9047 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
3 |  | 2BHK | 575.874 | 0 | 863.811 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
4 |  | 2BHK | 575.874 | 0 | 863.811 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
5 |  | 2BHK | 575.874 | 0 | 863.811 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
6 |  | 2BHK | 575.874 | 0 | 863.811 | 14th to 17th Floor (15th to 18th Floor as per Builder) 19th to 23rd Floor (20th to 24th Floor as per Builder)
8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
1 |  | 2BHK | 573.9365 | 0 | 860.9047 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
2 |  | 2BHK | 573.9365 | 0 | 860.9047 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
3 |  | 2BHK | 575.874 | 0 | 863.811 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
4 |  | Refuge Area |  |  |  | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
5 |  | 2BHK | 575.874 | 0 | 863.811 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
6 |  | 2BHK | 575.874 | 0 | 863.811 | 8th Floor 13th Floor (14th Floor as per Builder) 18th Floor (19th Floor as per Builder) (Part Refuge Area)
Remarks:
* | Finishing work is in process at the time of Visit. (Internal photographs not allowed.)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, we meet Mr. Lalit Joshi (9323076851)
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Mangesh |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Upper Thane - Casa Eden
Google Map :
Layout Plan:
A
B
E
C
D
C Wing
C Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted