## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 15/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-13
Name of the builder group |  |  |  | Sanskruti Builder And Developer
Name of the builder company |  |  |  | Sanskruti Builder And Developer
Name of the Project |  |  |  | Sanskruti Rose
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Adarsh 7420029890
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Dinesh : 7420029890
Name / No of the Building |  |  |  | Building No.1 (Wing A to E)
Name / No of the Existing Building |  |  |  | Nad Brahma Asavari CHSL
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans
RERA No. |  |  |  | P99000049176
Project location details |  | Sanskruti Rose, Survey No.76, H.No.6, Plot No.4, Redevlopement of "Nad Brahma Asavari CHSL", near Nadbrahma Madhuvanti CHS, Internal Road, Shiv Chaya Chawl, Achole, Nalla Sopara (East), Vasai, Palghar - 401209.
Survey No |  | 76, H.No.6, Plot No.4, Redevlopement of "Nad Brahma Asavari CHSL"
Locality |  | Shiv Chaya Chawl
Road |  | Internal Road |  | Locality/Village |  | Achole
City |  | Nalla Sopara (East) |  | District |  | Palghar
Taluka |  | Vasai |  | Pin Code |  | 401209
Nearby Landmark |  | Nadbrahma Madhuvanti CHS |  | Distance from city centre: |  | 1.2 KM from Nalla Sopara Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Shiv Darshan Apartment
West | NA | NA |  |  | Nad Brahma Road
North | NA | NA |  |  | Shiv Krupa Apartment
South | NA | NA |  |  | Bhumi Plaza
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.409932, 72.822689
Location Link |  | https://goo.gl/maps/a4XxEwgNbp9MKcMD9?coh=178572&entry=tt
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 2440.97
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.1267
Total FSI availaible for the project |  |  |  | 3.2267
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7876.33
Total number of Buildings |  |  |  | 05 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Vasai Virar City Municipal Corporation (VVCMC)
Layout Approval No |  | VVCMC/TP/CC/VP/6600/112/2022-23 |  |  | Dated | 2022-07-14
Approved Floor plan No. |  | VVCMC/TP/CC/VP/6600/112/2022-23 |  |  | Dated | 2022-07-14
Commencement-CC No Valid Up to: |  | VVCMC/TP/CC/VP/6600/112/2022-23 |  |  | Dated | 2022-07-14
Building No.1 (A to E Wing) = G + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 7876.33
Approved no of units |  |  | Flats - 147, Shops - 01
Approved no of Floors |  |  | Building No.1 (A to E Wing) = G + 1st to 7th Floor
Proposed no of Floors |  |  | Building No.1 (A Wing) = G + 1st to 7th Floor
Building No.1 (B Wing) = G + 1st to 7th Floor
Building No.1 (C Wing) = G + 1st to 7th Floor
Building No.1 (D & E Wing) = G + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Landscaping & Tree, Fire Fighting System, Footpaths/Pedest etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 (A Wing) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 6 Floor, External Plaster upto 5 Floor Completed | , Internal Plaster upto 6 Floor, External Plaster upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 6 Floor, External Plaster upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 71.07% |  | 87.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.1 (B & C Wing) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 6 Floor, External Plaster upto 5 Floor Completed | , Internal Plaster upto 6 Floor, External Plaster upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 6 Floor, External Plaster upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 71.07% |  | 87.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 6 | 85.71% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.1 (C Wing) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab Completed, Brickwork upto 6 Floor Completed | , Brickwork upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab
Stage of construction: |  | Excavation, Plinth, RCC Slab Completed, Brickwork upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 56.43% |  | 79.29% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 6 | 85.71% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.1 (D & E Wing) = G + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 4 Floor, Painting upto 3 Floor Completed | , Flooring upto 4 Floor, Painting upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 4 Floor, Painting upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 82.86% |  | 92.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 57.14% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 42.86% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5500 |  |  | 5000 to 5150 & Other charges |  | Trupti | Cost sheet | 2024-02-27
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 9000 |  |  | 5000 to 5500 |  | Trupti | Cost sheet | 2024-03-20
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 150000
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges |  |  |  |  | 50000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 4400
Commercial Area Details : Building No.1
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | Shop | 1 |  | 659.1874 |  | 1021.7404
Total |  | 1 |  | 659.1874 |  | 1021.7404
Residential Area Details : Building No.1
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | Flats | 42 |  | 21050.7242 |  | 31576.0864
Wing B |  | 14 |  | 6482.3768 |  | 9723.5652
Wing C |  | 28 |  | 14038.2742 |  | 21057.4114
Wing D |  | 28 |  | 16758.5254 |  | 25137.7881
Wing E |  | 35 |  | 18947.3848 |  | 28421.0772
Total |  | 147 |  | 77277.2855 |  | 115915.9283
Grand Total |  | 148 |  | 77936.4729 |  | 116937.6687
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Building No.1
Wing A
Ground Floor For Entrance Lobby, Meter Room, Society Office, Commercial & Parking
1 |  | Shop | 659.1874 | 0 | 1021.7404 | Ground Floor For Entrance Lobby, Meter Room, Society Office, Commercial & Parking |  | 60.581
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Building No.1
Wing A
1st to 7th Floor For Residential
1 |  | 2BHK | 536.7469 | 0 | 805.1203 | 1st to 7th Floor For Residential |  | 35.4175 |  | 5126.3719
2 |  | 1BHK | 525.4177 | 0 | 788.1266 |  |  | 10.764 | 39.4325 | 6081.5824
3 |  | 1BHK | 405.6144 | 0 | 608.4216 |  |  |  |  | 5162.3459
4 |  | 2BHK | 744.9495 | 0 | 1117.4243
5 |  | 1BHK | 381.9874 | 0 | 572.9812 |  |  | 27.8925 |  | 5354.9054
6 |  | 1BHK | 412.5303 | 0 | 618.7955
Wing B
Ground Floor For Entrance Lobby, Meter Room & Parking
1st to 7th Floor For Residential
1 |  | 1BHK | 457.1202 | 0 | 685.6803 | 1st to 7th Floor For Residential
2 |  | 1BHK | 468.9337 | 0 | 703.4005
Wing C
Ground Floor For Entrance Lobby, Meter Room & Parking
1st to 7th Floor For Residential
1 |  | 1BHK | 463.4171 | 0 | 695.1257 | 1st to 7th Floor For Residential
2 |  | 1BHK | 492.1839 | 0 | 738.2758
3 |  | 1BHK | 479.6707 | 0 | 719.5061
4 |  | 1BHK | 570.196 | 0 | 855.294
Wing D
Ground Floor For Entrance Lobby, Meter Room & Parking
1st to 7th Floor For Residential
1 |  | 1BHK | 519.1208 | 0 | 778.6812 | 1st to 7th Floor For Residential
2 |  | 1BHK | 480.8279 | 0 | 721.2418
3 |  | 2BHK | 696.4577 | 0 | 1044.6866
4 |  | 2BHK | 697.6687 | 0 | 1046.503
Wing E
Ground Floor For Entrance Lobby, Meter Room & Parking
1st to 7th Floor For Residential
1 |  | 1BHK | 530.8536 | 0 | 796.2804 | 1st to 7th Floor For Residential |  |  | 29.8975
2 |  | 1BHK | 546.6497 | 0 | 819.9746
3 |  | 1BHK | 482.0119 | 0 | 723.0179
4 |  | 2BHK | 657.492 | 0 | 986.238
5 |  | 1BHK | 489.762 | 0 | 734.643
Remarks:
* | Wing A, B & C = Construction work is in process at the time of Visit (Slow Speed). Wing D & E = Construction stage is same as last visit dtd. 23/05/2025 but work is in process at the time of visit. (Slow Speed) Labour found
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Chajja Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates / Other charges of the Property have been revised on 20/03/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Navnath Bhatkar |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Sanskruti Rose
Layout :
Google Map :
Formulas:
Achole = [Achole, row above]
Wing A
Wing B
Wing C
Wing D
Wing E
A Wing
B Wing
C Wing
D Wing
E Wing
A Wing
B Wing
C Wing
D Wing
E Wing

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted