## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 13/08/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | H B Realty
Name of the builder company |  |  |  | H B Realty
Name of the Project |  |  |  | Nandanvan
Contact Details ( Name & Contact No.) |  |  |  | 9867133720
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  | 9867133720
Name / No of the Building |  |  |  | Buildng No.1 & 2
Docouments Provided |  |  |  | Approved Plans, CC, Builder Saleable Area
RERA No. |  |  |  | P52000045672
Project location details |  | Nandanvan, Survey No.116/2B, near TSP Tara Apartment, Ghot Road, Taloja Phase 2, Taloje Majkur, Taloja, Panvel, Raigad - 410208.
Survey No |  | 116/2B
Locality |  | Taloja Phase 2
Road |  | Ghot Road |  | Village |  | Taloje Majkur
City |  | Taloja |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410208
Nearby Landmark |  | TSP Tara Apartment |  | Distance from city centre: |  | 2.5KM from Taloja Panchanand Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Internal Road
West | NA | NA |  |  | Open Plot
North | NA | NA |  |  | Internal Road
South | NA | NA |  |  | Open Plot
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.074446,73.1013328
Location Link |  | https://goo.gl/maps/p6kgbZc3u41Ktu428
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 6060
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.60498
Total FSI availaible for the project |  |  |  | 1.605
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 9726.197
Total number of Buildings |  |  |  | 02 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation
Layout Approval No |  | JK/PMP/NRV/16269/NK-947-1/2022 |  |  | Dated | 31/03/2022.
Approved Floor plan No. |  | JK/PMP/NRV/16269/NK-947-1/2022 |  |  | Dated | 31/03/2022.
Commencement-CC No Valid Up to: |  | PMC/TP/Taloje Majkur/116/2B/21-22/16269/947/1/2022 |  |  | Dated | 31/03/2022.
Building 1 & 2 = G + 1st to 10th Floor
O. Certificate No.: Approved upto : |  | NA |  |  | Dated | NA
NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 9726.197
Approved no of units |  |  | Flats -187, Shops -14
Approved no of Floors |  |  | Building 1 & 2 = G + 1st to 10th Floor
Proposed no of Floors |  |  | Building 1 = G + 1st to 10th Floor
Building 2 = G + 1st to 10th Floor
Expected Completion |  |  | As per RERA - 31/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Vitrified tiles flooring, Kitchen Platform, Decorative
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building 1 = G + 1st to 10th Floor | [5 empty] | All work Completed. Possession granted to the Building.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 10 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Stage of construction: |  | All work completed. Provide OC. | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.5
Excavation |  | 10 | 100% | 100% |  | 100% |  | Excavation in process | 5
Plinth |  | 10 | 100% |  |  |  |  | Excavation Completed | 10
RCC (Including podiums) |  | 11 | 100% |  |  |  |  | Footing in Process | 2.5
Brickwork | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Footing Completed | 5
Internal Plaster | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 10 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 100% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 10 | 100% |  |  |  |  | Plinth in process | 7.5
Possession |  | 10 | 100% |  |  |  |  | Plinth completed | 10
Construction details: |  | Building 2 = G + 1st to 10th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor, Painting upto 4 Floor Completed | , Flooring upto 7 Floor, Painting upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 10 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor, Painting upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 2.5
Excavation |  | 10 | 100% | 84% |  | 93.5% |  | Excavation in process | 5
Plinth |  | 10 | 100% |  |  |  |  | Excavation Completed | 10
RCC (Including podiums) |  | 11 | 100% |  |  |  |  | Footing in Process | 2.5
Brickwork | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Footing Completed | 5
Internal Plaster | Brickwork & Internal Plaster | 10 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 10 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 70% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 4 | 40% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 7.5
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 10
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 6000 |  |  | 5500 to 6000 | Smith | Cost sheet | 2023-01-28
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 12000
Floor Rise Rate |  |  |  |  | 50/- from 3rd floor
Development Charges |  |  |  |  | 250000
Club house Charges |  |  |  |  | 150000
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation & transfer Charges |  |  |  |  | 50000
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 250000
Distressed valuation of the Property |  |  |  |  | 4800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 |  | 10 |  | 2137.7842 |  | 4297
Building No.2 |  | 4 |  | 789.647 |  | 1598
Total |  | 14 |  | 2927.4313 |  | 5895 |  |  | 80905.9241
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 |  | 108 |  | 50050.6759 |  | 82184
Building No.2 |  | 79 |  | 27927.8169 |  | 46036
Total |  | 187 |  | 77978.4929 |  | 128220
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable Area | Floor
Building No.1
Ground Floor For Commercial & Parking
1 |  | Shop | 229.4347 | 0 | 464 | Ground Floor For Commercial & Parking |  |  |  | 2.0224
2 |  | Shop | 190.7381 | 0 | 386 | Ground Floor For Commercial & Parking |  |  |  | 2.0237
3 |  | Shop | 191.1686 | 0 | 387 | Ground Floor For Commercial & Parking |  |  |  | 2.0244
4 |  | Shop | 181.1581 | 0 | 367 | Ground Floor For Commercial & Parking |  |  |  | 2.0259
5 |  | Shop | 176.7449 | 0 | 358 | Ground Floor For Commercial & Parking |  |  |  | 2.0255
6 |  | Shop | 218.7245 | 0 | 442 | Ground Floor For Commercial & Parking |  |  |  | 2.0208
7 |  | Shop | 176.7449 | 0 | 358 | Ground Floor For Commercial & Parking |  |  |  | 2.0255
8 |  | Shop | 181.1581 | 0 | 367 | Ground Floor For Commercial & Parking |  |  |  | 2.0259
9 |  | Shop | 189.554 | 0 | 387 | Ground Floor For Commercial & Parking |  |  |  | 2.0416
10 |  | Shop | 402.3583 | 0 | 781 | Ground Floor For Commercial & Parking |  |  |  | 1.9411
Building No.2
Ground Floor
1 |  | Shop | 211.1897 | 0 | 427 | Ground Floor |  |  |  | 2.0219
2 |  | Shop | 183.6338 | 0 | 372 | Ground Floor |  |  |  | 2.0258
3 |  | Shop | 183.6338 | 0 | 372 | Ground Floor |  |  |  | 2.0258
4 |  | Shop | 211.1897 | 0 | 427 | Ground Floor |  |  |  | 2.0219
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Building No. 1
1st Floor for Residential
101 |  | 1 | 415.625 | 0 | 681 | 1st Floor for Residential |  |  |  | 1.6385
102 |  | 2 | 523.7224 | 0 | 858 | 1st Floor for Residential |  |  |  | 1.6383
103 |  | 2 | 523.7224 | 0 | 858 | 1st Floor for Residential |  |  |  | 1.6383
104 |  | 1 | 410.9964 | 0 | 674 | 1st Floor for Residential |  |  |  | 1.6399
105 |  | 1 | 422.0026 | 0 | 689 | 1st Floor for Residential |  |  |  | 1.6327
106 |  | 2 | 533.0333 | 81.3758 | 1017 | 1st Floor for Residential |  |  |  | 1.7553
107 |  | 1 | 400.1382 | 78.4696 | 800 | 1st Floor for Residential |  |  |  | 1.8032
108 |  | 1 | 400.1382 | 78.4696 | 800 | 1st Floor for Residential |  |  |  | 1.8032
109 |  | 2 | 530.6114 | 128.7374 | 1125 | 1st Floor for Residential |  |  |  | 1.8776
110 |  | 1 | 413.2569 | 0 | 678 | 1st Floor for Residential |  |  |  | 1.6406
111 |  | 1 | 410.2699 | 0 | 672 | 1st Floor for Residential |  |  |  | 1.6379
2nd to 3rd, 5th to 6th & 8th to 10th Floor
201 ,.., 1001 |  | 1 | 415.625 | 0 | 681 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6385
202 ,.., 1002 |  | 2 | 523.7224 | 0 | 858 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6383
203 ,.., 1003 |  | 2 | 523.7224 | 0 | 858 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6383
204 ,.., 1004 |  | 1 | 410.9964 | 0 | 674 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6399
205 ,.., 1005 |  | 1 | 422.0026 | 0 | 689 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6327
206 ,.., 1006 |  | 2 | 562.7016 | 0 | 905 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6083
207 ,.., 1007 |  | 1 | 430.4524 | 0 | 693 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6099
208 ,.., 1008 |  | 1 | 430.4524 | 0 | 693 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6099
209 ,.., 1009 |  | 2 | 559.9164 | 0 | 901 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6092
210 ,.., 1010 |  | 1 | 413.2569 | 0 | 678 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6406
211 ,.., 1011 |  | 1 | 410.2699 | 0 | 672 | 2nd to 3rd, 5th to 6th & 8th to 10th Floor |  |  |  | 1.6379
4th Floor
401 |  | 1 | 415.625 | 0 | 681 | 4th Floor |  |  |  | 1.6385
402 |  | 2 | 523.7224 | 0 | 858 | 4th Floor |  |  |  | 1.6383
403 |  | 2 | 523.7224 | 0 | 858 | 4th Floor |  |  |  | 1.6383
404 |  | 1 | 410.9964 | 0 | 674 | 4th Floor |  |  |  | 1.6399
405 |  | 1 | 422.0026 | 0 | 689 | 4th Floor |  |  |  | 1.6327
406 |  | 2 | 562.7016 | 0 | 905 | 4th Floor |  |  |  | 1.6083
407 |  | 1 | 430.4524 | 0 | 710 | 4th Floor |  | Sale Area chaged by smith for 65% LTV on 29/06/2024
408 |  | 1 | 430.4524 | 0 | 693 | 4th Floor |  |  |  | 1.6099
409 |  | 2 | 559.9164 | 0 | 901 | 4th Floor |  |  |  | 1.6092
410 |  | 1 | 413.2569 | 0 | 678 | 4th Floor |  |  |  | 1.6406
411 |  | 1 | 410.2699 | 0 | 672 | 4th Floor |  |  |  | 1.6379
7th Floor (Part Refuge Area)
701 |  | 1 | 415.625 | 0 | 681 | 7th Floor (Part Refuge Area) |  |  |  | 1.6385
702 |  | 2 | 523.7224 | 0 | 858 | 7th Floor (Part Refuge Area) |  |  |  | 1.6383
703 |  | 2 | 523.7224 | 0 | 858 | 7th Floor (Part Refuge Area) |  |  |  | 1.6383
704 |  | 1 | 410.9964 | 0 | 674 | 7th Floor (Part Refuge Area) |  |  |  | 1.6399
705 |  | 1 | 422.0026 | 0 | 689 | 7th Floor (Part Refuge Area) |  |  |  | 1.6327
706 |  | 2 | 562.7016 | 0 | 905 | 7th Floor (Part Refuge Area) |  |  |  | 1.6083
707 |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
708 | [5 empty] | 7th Floor (Part Refuge Area)
709 |  | 2 | 559.9164 | 0 | 901 | 7th Floor (Part Refuge Area) |  |  |  | 1.6092
710 |  | 1 | 413.2569 | 0 | 678 | 7th Floor (Part Refuge Area) |  |  |  | 1.6406
711 |  | 1 | 410.2699 | 0 | 672 | 7th Floor (Part Refuge Area) |  |  |  | 1.6379
Building No. 2
1st Floor
101 |  | 1 | 355.1313 | 0 | 580 | 1st Floor |  |  |  | 1.6332
102 |  | 1 | 352.9246 | 0 | 582 | 1st Floor |  |  |  | 1.6491
103 |  | 1 | 352.9246 | 0 | 582 | 1st Floor |  |  |  | 1.6491
104 |  | 1 | 335.487 | 62.0006 | 648 | 1st Floor |  |  |  | 1.7467
105 |  | 1 | 335.487 | 62.0006 | 648 | 1st Floor |  |  |  | 1.7467
106 |  | 1 | 352.9246 | 0 | 582 | 1st Floor |  |  |  | 1.6491
107 |  | 1 | 352.9246 | 0 | 582 | 1st Floor |  |  |  | 1.6491
108 |  | 1 | 355.1313 | 0 | 580 | 1st Floor |  |  |  | 1.6332
2nd to 6th & 8th to 10th Floor
201 ,.., 1001 |  | 1 | 355.1313 | 0 | 580 | 2nd to 6th & 8th to 10th Floor |  |  |  | 1.6332
202 ,.., 1002 |  | 1 | 352.9246 | 0 | 582 | 2nd to 6th & 8th to 10th Floor |  |  |  | 1.6491
203 ,.., 1003 |  | 1 | 352.9246 | 0 | 582 | 2nd to 6th & 8th to 10th Floor |  |  |  | 1.6491
204 ,.., 1004 |  | 1 | 355.1313 | 0 | 580 | 2nd to 6th & 8th to 10th Floor |  |  |  | 1.6332 | 0
205 ,.., 1005 |  | 1 | 355.1313 | 0 | 580 | 2nd to 6th & 8th to 10th Floor |  |  |  | 1.6332
206 ,.., 1006 |  | 1 | 352.9246 | 0 | 582 | 2nd to 6th & 8th to 10th Floor |  |  |  | 1.6491
207 ,.., 1007 |  | 1 | 352.9246 | 0 | 582 | 2nd to 6th & 8th to 10th Floor |  |  |  | 1.6491
208 ,.., 1008 |  | 1 | 355.1313 | 0 | 580 | 2nd to 6th & 8th to 10th Floor |  |  |  | 1.6332
7th Floor (Part Refuge Area)
701 |  | 1 | 355.1313 | 0 | 580 | 7th Floor (Part Refuge Area) |  |  |  | 1.6332
702 |  | 1 | 352.9246 | 0 | 582 | 7th Floor (Part Refuge Area) |  |  |  | 1.6491
703 |  | 1 | 352.9246 | 0 | 582 | 7th Floor (Part Refuge Area) |  |  |  | 1.6491
704 |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
705 |  | 1 | 355.1313 | 0 | 580 | 7th Floor (Part Refuge Area) |  |  |  | 1.6332
706 |  | 1 | 352.9246 | 0 | 582 | 7th Floor (Part Refuge Area) |  |  |  | 1.6491
707 |  | 1 | 352.9246 | 0 | 582 | 7th Floor (Part Refuge Area) |  |  |  | 1.6491
708 |  | 1 | 355.1313 | 0 | 580 | 7th Floor (Part Refuge Area) |  |  |  | 1.6332
Remarks:
* | Building 1 = All work completed. Provide OC. Building 2 = Construction work is in process at the time of Visit.
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + W.S Area
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | Recommended Rates / Other charges of the Property have been revised on 29/06/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Nandanvan
Google Map :
Building No.2
Bldg No. 1
Bldg No. 1
Bldg No. 1
Bldg No. 1
Bldg No. 2

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Note
Sale Area chaged by smith for 65% LTV on 29/06/2024