## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/08/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | Siddhivinayak Group NX
Name of the builder company |  |  |  | Siddhivinayak Group NX
Name of the Project |  |  |  | Mid­Town
Provided Contact Details (Name & Contact No.) |  |  |  | Mr. Sandeep & 9320222959
Site Person - Contact Details (Name & Contact No.) |  |  |  | NA
Name / No of the Building |  |  |  | Wing A1 & Wing D
Name / No of the Existing Building |  |  |  | NA | [5 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Docouments Provided |  |  |  | Approved Plans, CC | [5 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P51700052620 |  |  |  | #N/A |  | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | Mid­Town, Survey No.24, H.No.12/A, near Shree Vitthal Rakhumai Mandir, Ambernath Badlapur Road (Badlapur - Katai Road), Navare Nagar, Chikhloli, Chikhloli West, Ambernath, Thane - 421506. | [7 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 24, H.No.12/A | [7 empty] | Bhiwandi | Vikramgad |  | Karjat | Baramati
Locality |  | Navare Nagar | [7 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Ambernath Badlapur Road (Badlapur - Katai Road) |  | Locality/Village |  | Chikhloli |  |  |  | Ambernath | Dahanu |  | Pen | Shirur
City |  | Chikhloli West |  | District |  | Thane |  |  |  | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Ambernath |  | Pin Code |  | 421506 | [6 empty] | Mahad | Daund
Nearby Landmark |  | Shree Vitthal Rakhumai Mandir |  | Distance from city centre: |  | 5KM from Ambernath Railway Station | [6 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [8 empty] | Mangaon | Ambegaon
[13 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [8 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [8 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [8 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Open Plot
West | NA | Other Plot |  |  | Open Plot
North | NA | Other Plot |  |  | House/Open Plot
South | NA | Future Expansion/Open Space/Buidling/60.00M.W.D.P.Road |  |  | Open Plot/Ambernath Badlapur Road(Badlapur - Katai Road)
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.188112,73.208268
Location Link |  | https://maps.app.goo.gl/sty1HQtu7JSPe5LTA
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 5199.4
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.28477
Total FSI availaible for the project |  |  |  | 1.3848
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7199.97
Total number of Buildings |  |  |  | 02 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Ambernath Municipal Council
Layout Approval No. (Wing D) |  | A.N.P./NRV/BP/21-22/1579/9302/178 |  |  | Dated | 2022-03-31
Layout Approval No. (Wing A1) |  | AMC/TPD/2023-2024/1227 |  |  | Dated | 2023-12-15
Approved Floor plan No. (Wing D) |  | A.N.P./NRV/BP/21-22/1579/9302/178 |  |  | Dated | 2022-03-31
Approved Floor plan No. (Wing A1) |  | AMC/TPD/2023-2024/1227 |  |  | Dated | 2023-12-15
Commencement-CC No Valid Up to: (Wing D) |  | ANP/NRV/B.P/2021-22/1579/9302/178 |  |  | Dated | 2022-03-31
Wing D = Gr(Pt)/Stilt(Pt)+ 1st to 7th Floor (Residential + Commercial)
Commencement-CC No Valid Up to: |  | AMC/TPD/2023-2024/1227 |  |  | Dated | 2023-12-15
A1 (Midtown) = Gr/Mezz.Floor + 1st to 14th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 7199.97
Approved no of units |  |  | Flats - 103, Shops - 17, Offices - 17
Approved no of Floors |  |  | Wing A1 = Gr/Mezz.Floor + 1st to 14th Floor Wing D = Gr/Stilt + 1st to 7th Floor
Proposed no of Floors |  |  | Wing A1 = Gr/Mezz.Floor + 1st to 14th Floor
Wing D = Gr/Stilt + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 01/06/2028
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Sufficient Water supply, Entrance Lobby, Lift, Parking, Compound Wall, Pump Room, Septic Tank, Pump Room, Society Office, Fitness Center, Creche & Driver Room etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Nothing
Wheather the construction is as per approved Building plan : |  |  | Yes |  | Yes |  |  | Excavation, Plinth Completed, RCC upto 11 Slab, Brickwork upto 6 Floor Completed | , RCC upto 11 Slab, Brickwork upto 6 Floor
Construction details: |  | Wing A1 = Gr/Mezz.Floor + 1st to 14th Floor | [5 empty] | Excavation, Plinth
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 14 | Completed | Completed
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 11 Slab, Brickwork upto 6 Floor Completed | [5 empty] | Piling Work in process | 3.5
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation in process | 7
Excavation |  | 14 | 100% | 42.55% |  | 69.14% |  | Excavation Completed | 14
Plinth |  | 14 | 100% |  |  |  |  | Footing in Process | 3.5
RCC (Including podiums) |  | 11 | 73.33% |  |  |  |  | Footing Completed | 7
Brickwork | Brickwork & Internal Plaster | 6 | 42.86% |  |  |  |  | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 4 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Plinth in process | 10.5
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth completed | 14
Possession |  | 0 | 0% |  |  |  |  | All work Completed. Possession granted to the Building.
Construction details: |  | Wing D = Gr/Stilt + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring, Painting, Building common Amenities
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Completed
Stage of construction: |  | All work Completed. Possession granted to the Building. | [5 empty] | Piling Work in process | 1.75
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Excavation in process | 3.5
Excavation |  | 7 | 100% | 100% |  | 100% |  | Excavation Completed | 7
Plinth |  | 7 | 100% |  |  |  |  | Footing in Process | 1.75
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing Completed | 3.5
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 4 | 0
Painting & Wooden |  | 7 | 100% |  |  |  |  | Plinth in process | 5.25
Building Common Amenities | Building Common Amenities | 7 | 100% |  |  |  |  | Plinth completed | 7
Possession |  | 7 | 100% |  |  |  |  | #REF! | #REF!
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  | 4500 to 4900
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4400
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 7000
Floor Rise Rate from Floor
Other Charges |  |  |  |  | 200000 |  |  | by rushikesh 13/06/2024
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 150000
Distressed valuation of the Property |  |  |  |  | 3520
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A1 | Shop | 17 |  | 3044.5974 |  | 6875.8925
| Office | 17 |  | 2630.291 |  | 4801.963
Total |  | 34 |  | 5674.8884 |  | 11677.8555
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A1 |  | 89 |  | 39543.949 |  | 61972.0395 |  |  | 89
Wing D |  | 14 |  | 9829.5233 |  | 14744.285
Total |  | 103 |  | 49373.4723 |  | 76716.3245
Grand Total |  | 137 |  | 55048.3608 |  | 88394.1801
Building details Floor Wise
Details of Residential & Commercials in Building | [7 empty] | 10.764
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Mezzanine area & Arch. Proj. | Saleable area Loading : | Floor
55%
Wing A1
Stilt Floor For Entrance Lobby & Parking | [7 empty] | 10.764
1st Floor For Commercial & Entrance Lobby
1 |  | Shop | 451.3345 | 221.7384 | 1043.263 | 1st Floor For Commercial & Entrance Lobby
2 |  | Shop | 201.5021 | 88.803 | 449.9729 |  |  | 20.325 | 8.25
3 |  | Shop | 181.804 | 90.6329 | 422.2771
4 |  | Shop | 146.7133 | 65.8757 | 329.5129
5 |  | Shop | 160.8142 | 61.0319 | 343.8614
6 |  | Shop | 103.765 | 50.9137 | 239.752
7 |  | Shop | 135.6264 | 52.313 | 291.3061 |  |  | 12.285 | 4.86
8 |  | Shop | 128.0916 | 49.4068 | 275.1225
9 |  | Shop | 125.6159 | 61.0319 | 289.304
10 |  | Shop | 182.1269 | 98.8135 | 435.4576
11 |  | Shop | 178.5748 | 85.2509 | 408.9297
12 |  | Shop | 182.4498 | 77.6084 | 403.0903
13 |  | Shop | 233.2559 | 113.4526 | 537.3981
14 |  | Shop | 167.5955 | 72.657 | 372.3913
15 |  | Shop | 148.8661 | 64.584 | 330.8477
16 |  | Shop | 158.2308 | 68.6743 | 351.7029
17 |  | Shop | 158.2308 | 68.6743 | 351.7029
1st Floor
1 |  | Office | 179.8664 | 24.219 | 316.3324 | 1st Floor |  | 19.38 | 16.595
2 |  | Office | 141.8695 | 19.3752 | 249.9293 |  |  | 13.08
3 |  | Office | 159.5225 | 21.7971 | 281.0453
4 |  | Office | 245.3116 | 38.3468 | 439.6704 |  |  | 22.6925
5 |  | Office | 203.009 | 22.6044 | 349.7008
6 |  | Office | 193.4291 | 46.5812 | 372.0159
7 |  | Office | 92.1398 | 23.4117 | 179.1049
8 |  | Office | 127.2305 | 23.4117 | 233.4954
9 |  | Office | 148.9738 | 17.9221 | 258.6885
10 |  | Office | 292.6732 | 98.4906 | 606.3038 |  |  | 9.225 | 19.7524
11 |  | Office | 104.7337 | 21.7971 | 196.1228
12 |  | Office | 112.2685 | 20.5861 | 205.9247
13 |  | Office | 112.2685 | 20.5861 | 205.9247
14 |  | Office | 105.7025 | 19.3752 | 193.8704
15 |  | Office | 118.8346 | 21.7971 | 217.9791
16 |  | Office | 149.2967 | 27.4482 | 273.9546
17 |  | Office | 143.1612 | 0 | 221.8999
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
50%
Wing A1
2nd Floor For Residential
1 |  | 1BHK | 405.2377 | 0 | 607.8565 | 2nd Floor For Residential |  | 33.8675
2 |  | 1BHK | 391.0561 | 43.5942 | 630.1784 |  |  | 4.9
3 |  | 2BHK | 503.809 | 104.2806 | 807.8538 |  |  | 4.2168
4 |  | 2BHK | 476.307 | 356.1399 | 803.4955 |  |  | 32.97 | 32.9314
5 |  | 2BHK | 531.9569 | 51.2818 | 849.2172 |  |  | 6.3975
6 |  | 1BHK | 363.5003 | 53.7662 | 599.0166
7 |  | 1BHK | 386.7505 | 0 | 580.1258
3rd, 5th, 9th & 11th Floor
1 |  | 1BHK | 385.8625 | 41.9796 | 620.7733 | 3rd, 5th, 9th & 11th Floor
2 |  | 1BHK | 412.8532 | 0 | 619.2798
3 |  | 2BHK | 523.9915 | 42.7869 | 828.7742 |  |  | 4.35 | 10.395
4 |  | 2BHK | 511.0209 | 42.7869 | 809.3182
5 |  | 2BHK | 533.8944 | 41.1723 | 842.0139
6 |  | 1BHK | 365.9222 | 40.365 | 589.2483
7 |  | 1BHK | 359.3023 | 58.9329 | 597.8864
4th, 6th, 8th, 10th & 12th Floor
1 |  | 1BHK | 405.2377 | 0 | 607.8565 | 4th, 6th, 8th, 10th & 12th Floor
2 |  | 1BHK | 411.7768 | 46.8234 | 664.4886
3 |  | 2BHK | 545.6541 | 0 | 818.4811
4 |  | 2BHK | 535.2399 | 34.0681 | 836.9279
5 |  | 2BHK | 530.6652 | 45.2088 | 841.2066
6 |  | 1BHK | 363.5003 | 43.5942 | 588.8446
7 |  | 1BHK | 386.7505 | 0 | 580.1258
7th Floor (Part Refuge Area)
- |  | Refuge Area |  |  |  | 7th Floor (Part Refuge Area)
1 |  | 2BHK | 510.2674 | 41.9796 | 807.3807
2 |  | 2BHK | 523.9915 | 42.7869 | 828.7742
3 |  | 2BHK | 511.0209 | 83.9592 | 850.4905
4 |  | 2BHK | 532.6027 | 42.7869 | 841.691 |  |  | 58.26
5 |  | 1BHK | 365.9222 | 40.365 | 589.2483
6 |  | 1BHK | 359.3023 | 58.9329 | 597.8864
13th Floor (Part Refuge Area)
- |  | Refuge Area |  |  |  | 13th Floor (Part Refuge Area)
1 |  | 2BHK | 464.359 | 0 | 696.5384
2 |  | 2BHK | 528.324 | 0 | 792.486
3 |  | 2BHK | 437.422 | 81.8064 | 737.9395
4 |  | 2BHK | 554.346 | 0 | 831.519
5 |  | 1BHK | 373.1341 | 0 | 559.7011
6 |  | 1RK | 257.7978 | 106.2299 | 439.8117
14th Floor
1 |  | 1RK | 303.5448 | 0 | 455.3172 | 14th Floor
2 |  | 1BHK | 365.6531 | 0 | 548.4796
3 |  | 2BHK | 511.9627 | 0 | 767.9441
4 |  | 2BHK | 442.2658 | 0 | 663.3988
5 |  | 2BHK | 554.346 | 0 | 831.519
6 |  | 1BHK | 366.7295 | 0 | 550.0942
7 |  | 1RK | 256.829 | 0 | 385.2436
Wing D
Ground/Stilt Floor For Entrance Lobby & Parking
1st to 7th Floor For Residential
1 |  | 2BHK | 702.1088 | 0 | 1053.1632 | 1st to 7th Floor For Residential
2 |  | 2BHK | 702.1088 | 0 | 1053.1632
Remarks:
1 | Wing A1 = Construction work is in process at the time of Visit. Wing D = All work Completed. Please provide OC.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Cor. Proj Area + Mezzanine Area + Arch Proj. + Balcony Area
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | Wing D = As per the floor plan, the terrace is mentioned in flat No. 1 and 2. but as per the site visit, instead of a terrace area, a balcony is constructed for flat No.1 and 2.
11 | Building Names are changed as per revised approved plans.
12 | As per Approved layout plan dated 31/03/2022 |  | As per Approved layout plan dated 15/12/2023 |  | As per RERA (on 12/06/2024)
| Wing R-1 Wing R-2 |  | Wing A1 Wing D |  | Wing A Wing D
13 | We have updated revised approved plan & CC for wing A1 (on 31/12/2023)
14 | Recommended Rates/Other Charges of the Property have been revised on 15/06/2024.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Mid­Town
Layout :
Remark No. 10
Google Map :
Wing R-1
Wing R- 2
(Wing D)
(Wing A)
Wing A
Wing D
Approved layout plan dated 31/03/2022
Approved layout plan dated 15/12/2023
Wing A1
Wing A
Note on E11: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E12: Sachin: If exisiting Building is provided write it or else NA
Note on D59: Sachin: If multiple building in project or complex just mention builtup of required building

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC