## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 12/08/2025
CPC Name: |  |  |  | Axis Thane
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | V. R. Builders
Name of the builder company |  |  |  | V. R. Builders
Name of the Project |  |  |  | Navsarthak Co-op Hsg Soc Ltd
Provided Contact Details (Name & Contact No.) |  |  |  | 9881136464
Site Person - Contact Details (Name & Contact No.)
Name / No of the Building |  |  |  | 1 Building
Docouments Provided |  |  |  | Approved Plans, CC, Sale Plans, Builder Saleable Area
RERA No. |  |  |  | P51700047946
Project location details |  | Navsarthak Co-op Hsg Soc Ltd, Gut No.53, Plot No.3/P, CTS No.9170, near Namaskar Chsl, Royal Park Road, Shiv Shakti Nagar, Morivali, Ambarnath (West), Ambarnath, Thane - 421501.
Gut No |  | 53, Plot No.3/P, CTS No.9170
Locality |  | Shiv Shakti Nagar
Road |  | Royal Park Road |  | Locality/Village |  | Morivali
City |  | Ambarnath (West) |  | District |  | Thane
Taluka |  | Ambarnath |  | Pin Code |  | 421501
Nearby Landmark |  | Namaskar Chsl |  | Distance from city centre: |  | 2.1 KM from Ambarnath Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Royal Park Road
West | NA | NA |  |  | Raghunath Pooja
North | NA | NA |  |  | Umiya Krupa C.H.S.
South | NA | NA |  |  | Sai Residenvy
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.196680,73.195207
Location Link |  | https://goo.gl/maps/1HYsm5rYW2cbUmKS9
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 556
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 2.6677
Total FSI availaible for the project |  |  |  | 3.7677
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 2094.83
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Ambernath Municipal Council
Layout Approval No |  | ANP/NRV/BP/21-22/1470/9277/153 |  |  | Dated | 2022-03-29
Approved Floor plan No. |  | ANP/NRV/BP/21-22/1470/9277/153 |  |  | Dated | 2022-03-29
Commencement-CC No Valid Up to: |  | ANP/NRV/BP/21-22/1470/9277/153 |  |  | Dated | 2022-03-29
1B + Gr + 1st to 7th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 2094.83
Approved no of units |  |  | Flats - 35, Shops - 7
Approved no of Floors |  |  | 1B + Gr + 1st to 7th Floor
Proposed no of Floors |  |  | 1B + Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/05/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Drivers Room, Store Room, Closed Parking, Fitness Center & Creche
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | 1B + Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 4 Floor Completed | , External Plaster upto 4 Floor
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 70.71% |  | 87.86% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 57.14% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 5000 |  |  |  |  | mis | Visitor | online
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 8500 |  |  |  |  | 4200 | 5500 | 3900
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 200000
Distressed valuation of the Property |  |  |  |  | 4000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 7 |  | 1927.7786 |  | 2931
Total |  | 7 |  | 1927.7786 |  | 2931 |  |  |  |  | 5968.1698
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 35 |  | 17089.0071 |  | 25002.2105
Total |  | 35 |  | 17089.0071 |  | 25002.2105
Grand Total |  | 42 |  | 19016.7857 |  | 27933.2105
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Builder Saleable area | Floor
Basement Floor For Parking & Store Room
Ground Floor For Commercial
1 |  | Shop | 259.9506 | 0 | 365 | Ground Floor For Commercial |  | 20000 | 365 | 1.4041 | 3102500
2 |  | Shop | 354.3509 | 0 | 531 |  |  |  | 531 | 1.4985 | 4513500
3 |  | Shop | 310.972 | 0 | 480 |  |  |  | 480 | 1.5435 | 4080000
4 |  | Shop | 292.0273 | 0 | 450 |  |  |  | 450 | 1.541 | 3825000
5 |  | Shop | 243.5355 | 0 | 375 |  |  | 9333.3333 | 375 | 1.5398 | 3187500
6 |  | Shop | 331.3159 | 0 | 520 |  |  |  | 520 | 1.5695 | 4420000
7 |  | Shop | 135.6264 | 0 | 210 |  |  |  | 210 | 1.5484 | 1785000
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable area | Floor
Ground Floor For Part Residential & Drivers Room | [8 empty] | 10.764
1 |  | 1 | 318.0762 | 0 | 461.2105 | Ground Floor For Part Residential & Drivers Room |  |  |  | 4641.9098
1st to 6th Floor For Residential | [11 empty] | 5968.1698
101 to 601 |  | 2 | 513.4428 | 0 | 754 | 1st to 6th Floor For Residential |  | 5570.2918 | 754 | 1.4685 | 1.4685 | 4376.6578
102 to 602 |  | 1BHK | 518.8786 | 0 | 754 |  |  |  | 754 | 1.4531 | 1.4531
103 to 603 |  | 1BHK | 518.8786 | 0 | 754 |  |  |  | 754 | 1.4531 | 1.4531
104 to 604 |  | 2 | 490.1118 | 0 | 711 |  |  |  | 754 | 1.5384 | 1.4507
105 to 605 |  | 1RK | 388.9841 | 0 | 580 |  |  |  | 580 | 1.4911 | 1.4911 | 3965.5172
7th Floor | [9 empty] | #DIV/0!
701 |  | 2 | 513.4428 | 0 | 754 | 7th Floor |  |  | 754 | 1.4685
702 |  | 1BHK | 518.8786 | 0 | 754 |  |  |  | 754 | 1.4531
703 |  | 1BHK | 518.8786 | 0 | 754 |  |  |  | 754 | 1.4531
704 |  | 3 | 637.9554 | 0 | 961 |  |  | 5285500 | 961 | 1.5064
705 |  | Society Office, Fitness Center & Creche
1 |  |  |  | 0 | #REF!
2 |  |  |  | 0 | #REF!
3 |  |  |  | 0 | #REF!
4 |  |  |  | 0 | #REF!
2nd Floor
201 |  |  |  | 0 | #REF! | 2nd Floor
202 |  |  |  | 0 | #REF! | 2nd Floor
203 |  |  |  | 0 | #REF! | 2nd Floor
204 |  |  |  | 0 | #REF! | 2nd Floor
205 |  |  |  | 0 | #REF! | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | #REF! | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | #REF! | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | #REF! | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | #REF! | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | #REF! | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | #REF! | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | #REF! | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | #REF! | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | #REF! | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | #REF! | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | #REF! | 2nd & 5th Floor
Remarks:
* | Construction work is in process at the time of Visit. Slow Speed (labour found.)
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We considered Saleable area of Commercial as per Builder area Sheet.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Cor. Projection.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As per RERA, completion period of project Navsarthak Co-op Hsg Soc Ltd is expired on 31/05/2025 but still project is under construction.
* | As checked on RERA portal on date 12/08/2025, we have observed that above project " Navsarthak Co-op Hsg Soc Ltd " is kept under abeyance. Please check from your end.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Navsarthak Co-op Hsg Soc Ltd
Layout :
Google Map :
Formulas:
Morivali = [Morivali, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted