## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-12
Name of the builder group |  |  |  | Savvy Infrastructure Private Limited
Name of the builder company |  |  |  | Savvy Infrastructure Private Limited
Name of the Project |  |  |  | Merushikhar
Provided Contact Details ( Name & Contact No.) |  |  |  | 91-22-62396071
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr.Nikhil Shah 9324034825
Name / No of the Building |  |  |  | Wing A & B
Name / No of the Existing Building |  |  |  | Karmayog
Docouments Provided |  |  |  | Approved Plans, CC & Sale Plans
RERA No. |  |  |  | P51800049155
Project location details |  | Merushikhar, CTS No.186, 187, 188, 189 & Redevelopement of " Karmayog ", near Kaatyayni Heights, Parsi Panchayat Road, Jijamata Colony, Mogra, Andheri East, Andheri, Mumbai - 400053.
CTS No |  | 186, 187, 188, 189 & Redevelopement of " Karmayog "
Locality |  | Jijamata Colony
Road |  | Parsi Panchayat Road |  | Locality/Village |  | Mogra
City |  | Andheri East |  | District |  | Mumbai
Taluka |  | Andheri |  | Pin Code |  | 400053
Nearby Landmark |  | Kaatyayni Heights |  | Distance from city centre: |  | 1.1KM from Andheri Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Old Shopline
West | NA | Paved R.G & A.O.S |  |  | Vasudev Mishra Road
North | NA | 18.29 Mt. Wide Parsi Panshayat Road |  |  | Parsi Panchayat Road
South | NA | RG |  |  | Emerald Apartment
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.125614,72.854230
Location Link |  | https://maps.app.goo.gl/7JyDA8vJDniKhcrA6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 3076.23 |  |  |  | 3078.08
Permissible FSI |  |  |  | 1 |  |  |  | 1.7222
Permissible TDR/Paid FSI |  |  |  | 2.3862 |  |  |  | 3.3862
Total FSI availaible for the project |  |  |  | 3.3862
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 10416.72
Total number of Buildings |  |  |  | 2 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai
Layout Approval No |  | P-6691/2021/(186A And Other)/K/E Ward/MOGRA/337/1/NEW |  |  | Dated | 2024-05-03
Approved Floor plan No. |  | P-6691/2021/(186A And Other)/K/E Ward/MOGRA/337/1/NEW |  |  | Dated | 2024-05-03
Commencement-CC No Valid Up to: |  | P-6691/2021/(186A And Other)/K/E Ward/MOGRA/FCC/2/Amend |  |  | Dated | 2025-04-16
|  | Further C.C. up to Top of 12th floor i.e. at 57.00 mts. AGL for Wing A and up to Top of 12th floor i.e. at 57.00 mts. AGL for Wing B, as per approved plan dated 03/05/2024 |  |  | Valid Upto Date | 2025-10-31
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 10416.72
Approved no of units |  |  | Flats - 111 Shops - 7, Offices - 6
Approved no of Floors |  |  | Wing A & B = Gr + P1 to P3 + 1st to 12th Floor |  |  |  |  | Wing A = St + 3P + Gr + 1st to 11th Upper Floor Wing B = St + 3P + Gr + 1st to 7th(Pt) Upper Floor
Proposed no of Floors |  |  | Wing A & B = Gr + P1 to P3 + 1st to 12th Floor |  |  |  |  | Wing A & B = St + 3P + R.G + 1st to 13th Upper Floor
Expected Completion |  |  | As per RERA - 31/03/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | High Speed Elevators, Open Space, Rain Water Harvesting System, Solar Panel Lamp, Parking, Garden, Childern Play Area, Gym, Swimming Pool etc. |  |  |  |  | https://www.99acres.com/savvy-merushikhar-andheri-east-mumbai-andheri-dahisar-npxid-r405239#showModal
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing A = Gr + P1 to P3 + 1st to 12th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor Completed | , Flooring upto 7 Floor
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 12 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 7 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 80.83% |  | 92.92% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 58.33% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Construction details: |  | Wing B = Gr + P1 to P3 + 1st to 12th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 5 Floor Completed | , Flooring upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 12 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 3
Excavation |  | 12 | 100% | 79.17% |  | 92.08% |  | Excavation in process | 6
Plinth |  | 12 | 100% |  |  |  |  | Excavation Completed | 12
RCC (Including podiums) |  | 16 | 100% |  |  |  |  | Footing in Process | 3
Brickwork | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Footing Completed | 6
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 5 | 41.67% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 9
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 12
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 21000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 35000
Recommended rate of the Office Per Sq. Ft. |  |  |  |  | 25000
Floor Rise Rate
Development Charges
Club Charges
Legal Charges
Gas Connection Charges
Water, Electricity, Drainages, Sewerage Connection
Society Formation Charges
Advance Maintenance Charges
Recommended rate of Parking |  |  |  |  | 800000
Distressed valuation of the Property |  |  |  |  | 16800
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A | Shop | 7 |  | 2579.9155 |  | 4127.8648
| Office | 6 |  | 3591.0857 |  | 5745.7371
Total |  | 13 |  | 6171.0012 |  | 9873.6019
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 58 |  | 49041.1069 |  | 76013.7157 |  | 58
Wing B |  | 53 |  | 44994.5964 |  | 69741.6244 |  | 53
Total |  | 111 |  | 94035.7033 |  | 145755.3401
Grand Total |  | 124 |  | 100206.7045 |  | 155628.9421
Building Details Floor Wise
Details of Residential & Commercial in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Wing A | [9 empty] | 10.764
Ground Floor For Commercial, Entrance Lobby, Meter Room & Parking
1 |  | Shop | 268.6694 | 0 | 429.8711 | Ground Floor For Commercial, Entrance Lobby, Meter Room & Parking |  | 24.955
2 |  | Shop | 310.3261 | 0 | 496.5218 |  |  | 28.819
3 |  | Shop | 277.3883 | 0 | 443.8212
4 |  | Shop | 360.594 | 0 | 576.9504
5 |  | Shop | 264.4715 | 0 | 423.1544
6 |  | Shop | 427.7614 | 0 | 684.4182
7 |  | Shop | 670.7048 | 0 | 1073.1277
1st Podium Floor For Commercial & Parking
1 |  | Office | 579.4261 | 0 | 927.0818 | 1st Podium Floor For Commercial & Parking |  | 53.6501
2 |  | Office | 592.6658 | 0 | 948.2653
3 |  | Office | 745.0841 | 0 | 1192.1345
4 |  | Office | 633.1385 | 0 | 1013.0216
5 |  | Office | 626.8954 | 0 | 1003.0326
6 |  | Office | 413.8758 | 0 | 662.2013
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Wing A
2nd Podium Floor For Meter Room, L.M.R & Parking
3rd Podium Floor For Parking
1st Floor For Residential, R.G Area, Swimming Pool & Part Fitness Center | [8 empty] | 10.764
1 |  | Fitness Center |  |  |  | 1st Floor For Residential, R.G Area, Swimming Pool & Part Fitness Center |  |  | 62.8861
2 |  | 3.5BHK | 1106.9698 | 0 | 1715.8031
3 |  | 3BHK | 971.9892 | 0 | 1506.5833
4 |  | 2.5BHK | 761.0148 | 0 | 1179.5729 |  |  | 65.514
5 |  | 2.5BHK | 761.0148 | 0 | 1179.5729
2nd, 4th to 9th, 11th & 12th Floor For Residential
1 |  | 2BHK | 685.9897 | 0 | 1063.2841 | 2nd, 4th to 9th, 11th & 12th Floor For Residential
2 |  | 3.5BHK | 1106.9698 | 0 | 1715.8031 | 2nd, 4th to 9th, 11th & 12th Floor For Residential
3 |  | 3BHK | 971.9892 | 0 | 1506.5833 | 2nd, 4th to 9th, 11th & 12th Floor For Residential
4 |  | 2.5BHK | 761.0148 | 0 | 1179.5729 | 2nd, 4th to 9th, 11th & 12th Floor For Residential
5 |  | 2.5BHK | 761.0148 | 0 | 1179.5729 | 2nd, 4th to 9th, 11th & 12th Floor For Residential
3rd Floor (Part Refuge Area)
1 |  | 2BHK | 685.9897 | 0 | 1063.2841 | 3rd Floor (Part Refuge Area)
2 |  | 2.5BHK | 844.0052 | 0 | 1308.2081 | 3rd Floor (Part Refuge Area)
3 |  | Refuge Area |  |  |  | 3rd Floor (Part Refuge Area)
4 |  | 2.5BHK | 761.0148 | 0 | 1179.5729 | 3rd Floor (Part Refuge Area)
5 |  | 2.5BHK | 761.0148 | 0 | 1179.5729 | 3rd Floor (Part Refuge Area)
10th Floor (Part Refuge Area)
1 |  | 2BHK | 685.9897 | 0 | 1063.2841 | 10th Floor (Part Refuge Area)
2 |  | 3.5BHK | 1106.9698 | 0 | 1715.8031 | 10th Floor (Part Refuge Area)
3 |  | 1BHK | 490.3002 | 0 | 759.9653
- |  | Refuge Area |  |  |  | 10th Floor (Part Refuge Area)
4 |  | 2.5BHK | 761.0148 | 0 | 1179.5729 | 10th Floor (Part Refuge Area)
5 |  | 2.5BHK | 761.0148 | 0 | 1179.5729 | 10th Floor (Part Refuge Area)
Wing B
Ground Floor Parking & Space For D.G Set
1st to 3rd Podium Floor For Parking
1st Floor For Fitness Center, R.G Area, Swimming Pool & Parking
2nd, 4th to 9th, 11th & 12th Floor For Residential
1 |  | 2.5BHK | 758.0009 | 0 | 1174.9014 | 2nd, 4th to 9th, 11th & 12th Floor For Residential
2 |  | 2.5BHK | 754.987 | 0 | 1170.2298 | 2nd, 4th to 9th, 11th & 12th Floor For Residential
3 |  | 3BHK | 954.0133 | 0 | 1478.7206 | 2nd, 4th to 9th, 11th & 12th Floor For Residential
4 |  | 3.5BHK | 1099.9732 | 0 | 1704.9584 | 2nd, 4th to 9th, 11th & 12th Floor For Residential
5 |  | 2BHK | 685.9897 | 0 | 1063.2841 | 2nd, 4th to 9th, 11th & 12th Floor For Residential
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
2nd Floor
201 |  |  |  | 0 | 0 | 2nd Floor
202 |  |  |  | 0 | 0 | 2nd Floor
203 |  |  |  | 0 | 0 | 2nd Floor
204 |  |  |  | 0 | 0 | 2nd Floor
205 |  |  |  | 0 | 0 | 2nd Floor
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
302 ,.., 1502 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
303 ,.., 1503 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
304 ,.., 1504 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
305 ,.., 1505 |  |  |  | 0 | 0 | 3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 2nd to 5th Floor
202 to 502 |  |  |  | 0 | 0 | 2nd to 5th Floor
203 to 503 |  |  |  | 0 | 0 | 2nd to 5th Floor
204 to 504 |  |  |  | 0 | 0 | 2nd to 5th Floor
205 to 505 |  |  |  | 0 | 0 | 2nd to 5th Floor
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 2nd & 5th Floor
202 & 502 |  |  |  | 0 | 0 | 2nd & 5th Floor
203 & 503 |  |  |  | 0 | 0 | 2nd & 5th Floor
204 & 504 |  |  |  | 0 | 0 | 2nd & 5th Floor
205 & 505 |  |  |  | 0 | 0 | 2nd & 5th Floor
3rd Floor (Part Refuge Area)
1 |  | 2.5BHK | 758.0009 | 0 | 1174.9014 | 3rd Floor (Part Refuge Area)
2 |  | Refuge Area |  |  |  | 3rd Floor (Part Refuge Area)
3 |  | 1BHK | 544.4431 | 0 | 843.8868 | 3rd Floor (Part Refuge Area)
4 |  | 3.5BHK | 1099.9732 | 0 | 1704.9584 | 3rd Floor (Part Refuge Area)
5 |  | 2BHK | 685.9897 | 0 | 1063.2841 | 3rd Floor (Part Refuge Area)
10th Floor (Part Refuge Area)
1 |  | Refuge Area |  |  |  | 10th Floor (Part Refuge Area)
2 |  | 3.5BHK | 889.537 | 0 | 1378.7823 | 10th Floor (Part Refuge Area)
3 |  | 3BHK | 954.0133 | 0 | 1478.7206 | 10th Floor (Part Refuge Area)
4 |  | 3.5BHK | 1099.9732 | 0 | 1704.9584 | 10th Floor (Part Refuge Area)
5 |  | 2BHK | 685.9897 | 0 | 1063.2841 | 10th Floor (Part Refuge Area)
Remarks:
* | Construction work is in process at the time of Visit. (Internal Visit was not Allowed.)
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved CC on 20/06/2024.
* | Validity of CC is expired on 31/10/2023. Please provide latest CC.
* | As per plan dtd 10/08/2023, the wing A is reduced from the 13th floor to the 11th floor.
* | We have updated revised approved plan on 06/05/2024
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | We have updated latest CC from MCGM site. (On 14/05/2025)
* | On site we met Ms. Sejal 6354913540.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ganesh Wadkar |  | Report By : |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Merushikhar
Layout :
Google Map :
Formulas:
Mogra = [Mogra, row above]
Wing A
Wing B
Merushikhar
Kaatyayni Heights
Wing A
Wing B
Wing B
Wing B
Wing A
Wing A
Wing A
Wing B
Wing A
Wing B
Wing A

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted