## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/8 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 12/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-12
Name of the builder group |  |  |  |  | M/s.Charms Global
Name of the builder company |  |  |  |  | M/s.Charms Global
Name of the Project |  |  |  |  | Charms Global City
Contact Details ( Name & Contact No.) |  |  |  |  | 02225797935/02225451000
Name / No of the Building |  |  |  |  | Type A1 - Liberty Type B1 - Merlion Type B2 - Eiffel
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
Name as per RERA & RERA No. |  |  |  |  | Type A1 - Liberty = P51700021983 Type B1- Merlion = P51700024398 Type B2 - Eiffel = P51700046249
Project location details |  | Charms Global City, Gut No.42, 43PT, Royal Park Road, near Panvelkar Greencity, Morivali, Ambarnath, Thane.
Gut No |  | 42, 43PT
Road |  | Royal Park Road |  |  | Village |  | Morivali
City |  | Ambarnath |  |  | District |  | Thane
Taluka |  | Ambernath |  |  | Pin Code |  | 421501
Near by Landmark |  | Panvelkar Greencity |  |  | Distance from city centre: |  | About 3.1Km from Ambarnath Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | North |  | South
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open Plot |  | Open Plot |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.1916323, 73.1978312
Location Link |  | https://goo.gl/maps/T2zCrc82Pf97Rzb36
Approval details:
Approved usage of the Property: |  |  |  |  | Residential + Commercial
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 24942.4
Permissible FSI |  |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  |  | 1.4008
Total FSI availaible for the project |  |  |  |  | 2.5008
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 62376.89
Total number of Buildings |  |  |  |  | 3 Buildings
Approval Detail : Plan approval
Layout Approval No |  | ANP/NRV/BP/21-22/953/9229/105 |  |  |  | Dated | 2021-11-02
Approved Floor plan No. (Type A1 & B1) |  | ANP/NRV/BP/19-20/1522/9035/124 |  |  |  | Dated | 05/02/2020.
Approved Floor plan No. (Type B2) |  | ANP/NRV/BP/21-22/953/9229/105 |  |  |  | Dated | 2021-11-02
Commencement Certificate No. (Type A1 & B1) |  | ANP/NRV/BP/19-20/1522/9035/124 |  |  |  | Dated | 05/02/2020.
Valid Up to: Building Type A1 = Lower Gr. + Upper Gr. + 13th Floor Building Type B1 = Gr. + 1st to 12th Floor
Commencement Certificate No. (Type B2) |  | ANP/NRV/BP/21-22/953/9229/105 |  |  |  | Dated | 2021-11-02
Valid Up to: Building Type B2 = Gr/St + 1st to 16th Floor
O. Certificate No.: Approved upto : |  | AMC/NRV/2024-25/21 Bldg A1 = LG + UG + 1st to 13th Floor |  |  | Date of approval: | Dated | 2024-04-04 | NA
Commencement date of construction |  |  | 05/02/2020. |  | Expected Completion |  | Type A1 - Liberty = Completed Type B1- Merlion = Completed Type B2 - Eiffel = 31/03/2026
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 62376.89 |  | Approved no of units |  | Flats = 532 & shop = 25
Approved no of Floors |  | Type A1 = Lower Gr. + Upper Gr. + 1st to 13th Floor Type B1 = Gr. + 1st to 12th Floor Type B2 = Gr/St + 1st to 16th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: Cement, Aggregate, Steel, etc | [8 empty] | All work completed. Please provide OC.
Construction details: |  | Type A1 = Lower Gr. + Upper Gr. + 1st to 13th Floor
Basement | 0 | Ground | 2 | Podium |  | 0 | Floors | 13 | All work Completed. OC Received.
Stage of construction: |  | All work Completed. OC Received.
Progress % |  | 100% |  |  | Disbursement % |  | 100%
[9 empty] | Piling Work in process | 3.25
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Excavation in process | 6.5
Excavation |  | 13 | 100% |  | 100% |  | 100% |  | Excavation Completed | 13
Plinth |  | 13 | 100% | [5 empty] | Footing in Process | 3.25
RCC(Including podiums) |  | 15 | 100% | [5 empty] | Footing Completed | 6.5
Brickwork | Brickwork & Internal Plaster | 13 | 100% | [5 empty] | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 13 | 100% | [5 empty] | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 13 | 100% | [5 empty] | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 13 | 100% | [5 empty] | Basement 4 | 0
Painting & Wooden |  | 13 | 100% | [5 empty] | Plinth in process | 9.75
Building Common Amenities | Building Common Amenities | 13 | 100% | [5 empty] | Plinth completed | 13
Possession |  | 13 | 100% | [5 empty] | All work completed. Please provide OC.
Construction details: |  | Type B1 = Gr. + 1st to 12th Floor
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 12 | All work Completed. OC Received.
Stage of construction: |  | All work completed. Please provide OC. | [6 empty] | Piling Work in process | 3
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Excavation in process | 6
Excavation |  | 12 | 100% |  | 100% |  | 100% |  | Excavation Completed | 12
Plinth |  | 12 | 100% | [5 empty] | Footing in Process | 3
RCC(Including podiums) |  | 13 | 100% | [5 empty] | Footing Completed | 6
Brickwork | Brickwork & Internal Plaster | 12 | 100% | [5 empty] | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 12 | 100% | [5 empty] | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 12 | 100% | [5 empty] | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 100% | [5 empty] | Basement 4 | 0
Painting & Wooden |  | 12 | 100% | [5 empty] | Plinth in process | 9
Building Common Amenities | Building Common Amenities | 12 | 100% | [5 empty] | Plinth completed | 12
Possession |  | 12 | 100%
Progress % |  | 100% |  |  | Disbursement % |  | 100%
Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 15 Floor, Flooring upto 4 Floor, Painting upto 3 Floor Completed
Construction details: |  | Type B2 = Gr./St + 1st to 16th Floor
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 16 | All work Completed. OC Received.
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster upto 15 Floor, Flooring upto 4 Floor, Painting upto 3 Floor Completed | [6 empty] | Piling Work in process | 4
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Excavation in process | 8
Excavation |  | 16 | 100% |  | 77.81% |  | 90.94% |  | Excavation Completed | 16
Plinth |  | 16 | 100% | [5 empty] | Footing in Process | 4
RCC(Including podiums) |  | 17 | 100% | [5 empty] | Footing Completed | 8
Brickwork | Brickwork & Internal Plaster | 16 | 100% | [5 empty] | Basement 1 | 0
Internal Plaster | Brickwork & Internal Plaster | 16 | 100% | [5 empty] | Basement 2 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 15 | 93.75% | [5 empty] | Basement 3 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 25% | [5 empty] | Basement 4 | 0
Painting & Wooden |  | 3 | 18.75% | [5 empty] | Plinth in process | 12
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth completed | 16
Possession |  | 0 | 0%
Wheather the construction is as per approved Building plan : Under Construction.
Violations Observed if any : NA
Proposed Amenities : |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property : | [8 empty] | 4500 to 4700 | Smith | Igr | 2022-12-21
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 4700
Recommended rate of the Shop Per Sq. Ft. ( on Saleable area) | [5 empty] | 8000/- |  |  | charges added by cost sheet |  |  | 2022-07-28 | Abhishek Manjrekar
Development Charges | [5 empty] | 3,00,000/-
ClubHouse Infra Charges | [5 empty] | 1,50,000/-
Grill Charges | [5 empty] | 50,000/-
Recommended rate of Parking | [5 empty] | 100000/-
Development charges Per Sq. Ft. | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 3760
Commercial Area Details :
Building & Wing |  | No. of Shops | Total Carpet Area |  |  | Total Saleable Area
Type A1 |  | 25 | 13230.0948 |  |  | 19845.1422
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
Type A1 |  | 199 | 90436.1141 |  |  | 132401.9092
Type B1 |  | 143 | 66533.1236 |  |  | 99799.6854
Type B2 |  | 190 | 97666.928 |  |  | 146500.3919 |  |  |  | 398547.1288 | 267866.2605
Total |  | 532 | 254636.1656 |  |  | 378701.9866
Grand Total |  | 557 | 267866.2605 |  |  | 398547.1288
Building details Floor Wisg
Details of Flats in Building
Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Building Type A1 (Liberty)
Lower Ground Floor is for Parking & Commercial
1 |  | Shop | 4185.6944 |  | 0 | 6278.5416 | N | Lower Ground Floor
2 |  | Shop | 594.3504 |  | 0 | 891.5256 | N
3 |  | Shop | 297.6515 |  | 0 | 446.4773 | N
4 |  | Shop | 297.2156 |  | 0 | 445.8234 | N
5 |  | Shop | 450.0428 |  | 0 | 675.0643 | N
6 |  | Shop | 241.1437 |  | 0 | 361.7156 | N
7 |  | Shop | 442.0344 |  | 0 | 663.0516 | N
8 |  | Shop | 297.2156 |  | 0 | 445.8234 | N
9 |  | Shop | 299.2123 |  | 0 | 448.8184 | N
10 |  | Shop | 299.2123 |  | 0 | 448.8184 | N
11 |  | Shop | 200.5333 |  | 0 | 300.8 | N
12 |  | Shop | 442.0344 |  | 0 | 663.0516 | N
13 |  | Shop | 435.7375 |  | 0 | 653.6062 | N
Upper Ground Floor is for Residential & Commercial
14 |  | Shop | 1427.3172 |  | 0 | 2140.9757 | N | Upper Ground Floor
15 |  | Shop | 249.2404 |  | 0 | 373.8606 | N
16 |  | Shop | 229.4185 |  | 0 | 344.1278 | N
17 |  | Shop | 391.5728 |  | 0 | 587.3592 | N
18 |  | Shop | 400.776 |  | 0 | 601.164 | N
19 |  | Shop | 229.4185 |  | 0 | 344.1278 | N
20 |  | Shop | 261.3499 |  | 0 | 392.0249 | N
21 |  | Shop | 261.3499 |  | 0 | 392.0249 | N
22 |  | Shop | 229.4185 |  | 0 | 344.1278 | N
23 |  | Shop | 400.776 |  | 0 | 601.164 | N
24 |  | Shop | 398.5694 |  | 0 | 597.8541 | N |  |  | 1.45
25 |  | Shop | 268.8094 |  | 0 | 403.2141 | N
1 |  | 2 BHK | 530.7728 |  | 0 | 769.6206 | N
2 |  | 1 BHK | 438.9559 |  | 0 | 636.4861 | N
3 |  | 1 BHK | 420.4957 |  | 0 | 609.7187 | N
4 |  | 1 BHK | 420.4957 |  | 0 | 609.7187 | N
5 |  | 1 BHK | 433.843 |  | 0 | 629.0724 | N
8 |  | 1 BHK | 426.0929 |  | 655.6352 | 781.7436 | N
9 |  | 1 BHK | 415.7595 |  | 917.9539 | 786.4421 | N
10 |  | 2 BHK | 582.1171 |  | 953.0446 | 1034.6787 | N
1st Floor
1 |  | 2 BHK | 529.3735 |  | 0 | 767.5916 | N | 1st Floor
2 |  | 1 BHK | 430.56 |  | 0 | 624.312 | N
3 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
4 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
5 |  | 1 BHK | 432.5513 |  | 0 | 627.1994 | N |  |  | 3222.439
6 |  | 2 BHK | 519.6321 |  | 0 | 753.4665 | N
7 |  | 2 BHK | 519.6321 |  | 0 | 753.4665 | N
8 |  | 1 BHK | 432.5513 |  | 0 | 627.1994 | N
9 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
10 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
11 |  | 2 BHK | 519.6321 |  | 1077.0458 | 968.8757 | N
12 |  | 1 BHK | 411.9921 |  | 516.0262 | 726.3951 | N
13 |  | 1 BHK | 411.9921 |  | 516.0262 | 726.3951 | N
14 |  | 1 BHK | 411.9921 |  | 516.0262 | 726.3951 | N |  |  | 4164.4004
15 |  | 1 BHK | 411.9921 |  | 516.0262 | 726.3951 | N
2nd to 6th, 8th to 11th, 13th Floors | [8 empty] | 4377.3277 |  | 390.8328
1 |  | 2 BHK | 529.3735 |  | 0 | 767.5916 | N | 2nd to 6th, 8th to 11th, 13th Floors
2 |  | 1 BHK | 430.56 |  | 0 | 624.312 | N
3 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
4 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
5 |  | 1 BHK | 432.5513 |  | 0 | 627.1994 | N
6 |  | 2 BHK | 519.6321 |  | 0 | 753.4665 | N
7 |  | 2 BHK | 519.6321 |  | 0 | 753.4665 | N
8 |  | 1 BHK | 432.5513 |  | 0 | 627.1994 | N
9 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
10 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
11 |  | 2 BHK | 519.6321 |  | 0 | 753.4665 | N
12 |  | 1 BHK | 435.4038 |  | 0 | 631.3355 | N
13 |  | 1 BHK | 435.4038 |  | 0 | 631.3355 | N
14 |  | 1 BHK | 435.4038 |  | 0 | 631.3355 | N
15 |  | 1 BHK | 435.4038 |  | 0 | 631.3355 | N
7th & 12th Floors
1 |  | 2 BHK | 529.3735 |  | 0 | 767.5916 | N | 7th & 12th Floors
2 |  | Refuge Area
3 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
4 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
5 |  | Refuge Area
6 |  | 2 BHK | 519.6321 |  | 0 | 753.4665 | N
7 |  | 2 BHK | 519.6321 |  | 0 | 753.4665 | N
8 |  | 1 BHK | 432.5513 |  | 0 | 627.1994 | N
9 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
10 |  | 1 BHK | 422.2179 |  | 0 | 612.216 | N
11 |  | 2 BHK | 519.6321 |  | 0 | 753.4665 | N
12 |  | 1 BHK | 435.4038 |  | 0 | 631.3355 | N
13 |  | 1 BHK | 435.4038 |  | 0 | 631.3355 | N
14 |  | 1 BHK | 435.4038 |  | 0 | 631.3355 | N
15 |  | 1 BHK | 435.4038 |  | 0 | 631.3355 | N
Building Type B1 (Merlion)
Ground Floor For Parking
1st to 7th & 9th to 12th Floor
1 |  | 1BHK | 399.7481 |  | 0 | 599.6221 | N | 1st to 7th & 9th to 12th Floor
2 |  | 1BHK | 403.5424 |  | 0 | 605.3135 | N
3 |  | 1.5BHK | 591.2235 |  | 0 | 886.8352 | N
4 |  | 1.5BHK | 591.2235 |  | 0 | 886.8352 | N
5 |  | 1BHK | 403.5424 |  | 0 | 605.3135 | N
6 |  | 1BHK | 399.7481 |  | 0 | 599.6221 | N
7 |  | 1BHK | 399.7481 |  | 0 | 599.6221 | N
8 |  | 1BHK | 403.5424 |  | 0 | 605.3135 | N
9 |  | 1.5BHK | 591.2235 |  | 0 | 886.8352 | N
10 |  | 1.5BHK | 591.2235 |  | 0 | 886.8352 | N
11 |  | 1BHK | 403.5424 |  | 0 | 605.3135 | N
12 |  | 1BHK | 399.7481 |  | 0 | 599.6221 | N
8th Floor (Part Refuge Area)
1 |  | 1BHK | 399.7481 |  | 0 | 599.6221 | N | 8th Floor (Part Refuge Area)
2 |  | 1BHK | 403.5424 |  | 0 | 605.3135 | N
3 |  | 1.5BHK | 591.2235 |  | 0 | 886.8352 | N
4 |  | 1.5BHK | 591.2235 |  | 0 | 886.8352 | N
5 |  | 1BHK | 403.5424 |  | 0 | 605.3135 | N
6 |  | 1BHK | 399.7481 |  | 0 | 599.6221 | N
7 |  | 1BHK | 399.7481 |  | 0 | 599.6221 | N
8 |  | Refuge Area
9 |  | 1.5BHK | 591.2235 |  | 0 | 886.8352 | N
10 |  | 1.5BHK | 591.2235 |  | 0 | 886.8352 | N
11 |  | 1BHK | 403.5424 |  | 0 | 605.3135 | N
12 |  | 1BHK | 399.7481 |  | 0 | 599.6221 | N
Building Type B2 (Eiffel)
Ground Floor For Parking, Meter Room & Society Office | [10 empty] | 10.764
1st to 7th, 9th to 12th & 14th to 16th Floor For Residential
1 |  | 2BHK | 599.1727 |  | 0 | 898.759 | N | 1st to 7th, 9th to 12th & 14th to 16th Floor For Residential
2 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
3 |  | 2BHK | 569.3403 |  | 0 | 854.0104 | N
4 |  | 2BHK | 569.3403 |  | 0 | 854.0104 | N
5 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
6 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
7 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
8 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
9 |  | 2BHK | 569.3403 |  | 0 | 854.0104 | N
10 |  | 2BHK | 569.3403 |  | 0 | 854.0104 | N
11 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
12 |  | 2BHK | 599.1727 |  | 0 | 898.759 | N
8th & 13th Floor (Part Refuge Area)
1 |  | 2BHK | 599.1727 |  | 0 | 898.759 | N | 8th & 13th Floor (Part Refuge Area)
2 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
3 |  | 2BHK | 569.3403 |  | 0 | 854.0104 | N
4 |  | 2BHK | 569.3403 |  | 0 | 854.0104 | N
5 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
6 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
7 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
8 |  | Part Refuge Area
9 |  | 2BHK | 569.3403 |  | 0 | 854.0104 | N
10 |  | 2BHK | 569.3403 |  | 0 | 854.0104 | N
11 |  | 1BHK | 447.4003 |  | 0 | 671.1004 | N
12 |  | 2BHK | 599.1727 |  | 0 | 898.759 | N
Remarks: | [8 empty] | In 2025 Please add CC remark.
1. Bldg A1 = All work Completed. OC received. Bldg B1 = All work Completed. Please provide OC. Bldg B2 = Construction work was in process at the time of visit. Internal photos was not allowed. 2. We considered Saleable area as per our calculation 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony + C.B Area + E.P Area. 5.We have considered rate by verifying it from market inquire. 6. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes). 7. We have considered Other charges from cost sheet. 8. Car parking is subjected to authentic documentation. 9. We update revised approved plans. (on 26/06/2021) 10. We update approved plans & CC of Building Type B - 1 Merlion (on 02/05/2022). 11.We have updated Approved layout plan, Floor plan & CC of Building Type B2 (Eiffel) (on 20/06/2023). Layout Plan referred from RERA site. 12. We have updated OC for Bldg A1 from Rera (On 14/02/2025). 13. Since the project has received first CC on 02/11/2021, But construction work of Building Type B2 is under construction. 12. As per RERA, completion period of project Type B1- Merlion is expired on 30/06/2024 but still project is under construction. 12. On site, we meet Mr.Sandeep Sonawane (Sales) - 9930999897.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sudhir Bhosale |  | Report Prepared By : |  |  | Pranita Mhatre
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Charms Global City
Google Map :
Liberty
Merlion
Eiffel
Type B1
Eiffel
Type B2
Type B1
Type A1
Type B2
Type B1
Type A1

## C%
Basement | Podium | Ground | Upper Floor
0 | 1 | 1 | 13
Particulars | total floor | 13
plinth | 10 | 10 | 100%
slab | 15 | 2 | 13.33% |  | Parking |  | Rate
Bricks | 14 | 0 | 0% |  | Palghar |  | 100000/-
plaster | 14 | 0 | 0% |  | Ulwe, karanjade |  | 200000/-
Flooring | 14 | 0 | 0% |  | Panvel |  | 300000/-
Wood & painting | 14 | 0 | 0% |  | Mumbai - G + 15 |  | 500000/-
Finishing | 14 | 0 | 0% |  | Mumbai - G + 25 |  | 800000/-
[5 empty] | Mumbai - G + 35 |  | 1000000/-
| Progress | Recommended |  |  |  | plinth | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
Plinth | 10 | 30 |  | Progress |  | 10 | 5.3333 | 0 | 0 | 0 | 0 | 0
RCC | 5.3333 | 4 |  | Recommended |  | 30 | 4 | 0 | 0 | 0 | 0 | 0
Bricks | 0 | 0
Plaster | 0 | 0
Flooring | 0 | 0
Wood & painting | 0 | 0
Finishing | 0 | 0
total | 15.33% | 34% |  |  | Thane - G + 7 |  | 200000/-
[5 empty] | Thane - G + 15 |  | 400000/-
Excavation in process | 1% | 2% |  |  | Thane - G + 25 |  | 600000/-
Excavation Completed | 1% | 3%
Footing in Process | 3% | 8%
Footing Completed | 5% | 15%
Plinth in process | 7% | 20%
Plinth completed | 10% | 30%

## Note
2020-11-26 | Pratiksha
13/03/2021 | Pratiksha

## Valuation
2020-11-26 | Pratiksha
Market Research Data
| Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
| Makaan | Charms Global City | 1BHK | 364 | 527.8 | 4547.177 | 2400000
| Makaan | Charms Global City | 2BHK | 574 | 832.3 | 5106.3319 | 4250000
| Average |  |  |  |  | 4826.7544
| Valuation Adopted |  |  |  |  | 4900

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0