## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 14/08/2025
CPC Name: |  |  |  | Axis Badlapur
Date Of Property Visit |  |  |  | 2025-08-13
Name of the builder |  |  |  | Mr.Kamlesh Devidas Dhruv
Name of the builder company |  |  |  | Dhruv Builders And Developers
Name of the Project |  |  |  | Dhruv Residency Platinum
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Ankit Zhaveri (9322216100) |  |  |  | Mr. Ankit Zhaveri (9322216100)
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr. Pradip : 8898005777
Name / No of the Building |  |  |  | Building No. 1 (A Wing) Building No. 2 (B, C, D & E Wing)
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet.
RERA No. |  |  |  | P52000047179
Project location details |  | Dhruv Residency Platinum, Survey No.151/3, 151/6, 141/5, near Deep Jyoti City, Pashane Rd, Pashane, Pashane, Vangani West, Karjat, Raigad - 410101.
Survey No |  | 151/3, 151/6, 141/5
Locality |  | Pashane
Road |  | Pashane Rd |  | Locality/Village |  | Pashane
City |  | Vangani West |  | District |  | Raigad
Taluka |  | Karjat |  | Pin Code |  | 410101
Nearby Landmark |  | Deep Jyoti City |  | Distance from city centre: |  | 1.9KM from Vangani Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | NA |  |  | Road
West | NA | NA |  |  | Open Plot/Divine Tower
North | NA | NA |  |  | Pashane Rd
South | NA | NA |  |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.1021291,73.3138875
Location Link |  | https://goo.gl/maps/D6PmsQJ5dD4o2QNf7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 19994.36
Permissible FSI |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  | 0
Total FSI availaible for the project |  |  |  | 0.75
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 14995.77
Total number of Buildings |  |  |  | 05 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Collector Of Raigad
Layout Approval No |  | MS/LNA-1/P.K.158/2018 |  |  | Dated | 2022-02-28
Approved Floor plan No. |  | MS/LNA-1/P.K.158/2018 |  |  | Dated | 2022-02-28
Commencement-CC No Valid Up to: |  | MS/L.N.A.1(A)(B)Tokan No. 14018/P.K. 158/2018 |  |  | Dated | 2022-02-28
Building No. 1 (A Wing) = Gr + 1st to 4th Floor Building No. 2 (B, C, D & E Wing) = Gr +1st to 4th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 3808.05
Approved no of units |  |  | Flats - 104, Shops - 20
Approved no of Floors |  |  | Building No. 1 (A Wing) = Gr + 1st to 4th Floor Building No. 2 (B, C, D & E Wing) = Gr +1st to 4th Floor
Proposed no of Floors |  |  | Building No. 1 (A Wing) = Gr + 1st to 4th Floor
Building No. 2 (B Wing) = Gr +1st to 4th Floor
Building No. 2 (C Wing) = Gr +1st to 4th Floor
Building No. 2 (D & E Wing) = Gr +1st to 4th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No. 1 (A Wing) = Gr + 1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 3.5 Floor, Painting upto 3 Floor Completed | , Flooring upto 3.5 Floor, Painting upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 3.5 Floor, Painting upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 87.5% |  | 94.38% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 3.5 | 87.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 3 | 75% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 2 (B Wing) = Gr +1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 2.5 Floor, Painting upto 2 Floor Completed | , Flooring upto 2.5 Floor, Painting upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 2.5 Floor, Painting upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 83.75% |  | 93.12% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2.5 | 62.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 2 | 50% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 2 (C Wing) = Gr +1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 2 Floor, Painting upto 2 Floor Completed | , Flooring upto 2 Floor, Painting upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 2 Floor, Painting upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 82.5% |  | 92.5% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 2 | 50% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 2 | 50% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 2 (D Wing) = Gr +1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor, External Plaster upto 2 Floor Completed | , Internal Plaster upto 3 Floor, External Plaster upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 3 Floor, External Plaster upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% | 68.12% |  | 86.25% |  | Excavation in process | 2
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 3 | 75% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 2 | 50% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Construction details: |  | Building No. 2 (E Wing) = Gr +1st to 4th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 1 Floor, External Plaster upto 1 Floor, Flooring upto 0.5 Floor Completed | , Internal Plaster upto 1 Floor, External Plaster upto 1 Floor, Flooring upto 0.5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 4 | Excavation, Plinth, RCC Slab, Brickwork |  | Rushikesh | 2023-04-10 | cost sheet
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 1 Floor, External Plaster upto 1 Floor, Flooring upto 0.5 Floor Completed | [5 empty] | Completed | Completed | Rushikesh | 2023-08-08 | cost sheet
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1 | Rushikesh
Excavation |  | 4 | 100% | 63.12% |  | 83.12% |  | Excavation in process | 2 | Rushikesh
Plinth |  | 4 | 100% |  |  |  |  | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% |  |  |  |  | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% |  |  |  |  | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 1 | 25% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 1 | 25% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0.5 | 12.5% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 3
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 4
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 3700 |  |  |  | 3200 to 3500
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 7000 |  |  |  | 3500 to 3700
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 150000
Recommended rate of Parking |  |  |  |  | 100000
Distressed valuation of the Property |  |  |  |  | 2960 |  |  | Legal Charges |  |  |  |  | 25000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 1 (A Wing) |  | 9 |  | 1340.4409 |  | 2077.6834
Building No. 2 (B + C Wing) |  | 11 |  | 2252.9052 |  | 3492.0031 |  |  |  | 10.764
Total |  | 20 |  | 3593.3461 |  | 5569.6865
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No. 1 (A Wing) |  | 12 |  | 2983.5655 |  | 4465.5503
Building No. 2 (B Wing) |  | 32 |  | 8769.2155 |  | 12715.3625
Building No. 2 (C Wing) |  | 16 |  | 4835.1457 |  | 7010.9613
Building No. 2 (D Wing) |  | 32 |  | 7426.9447 |  | 10769.0698
Building No. 2 (E Wing) |  | 12 |  | 2602.3046 |  | 3773.3417
Total |  | 104 |  | 26617.1761 |  | 38734.2858
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
55%
Building No. 1 A Wing (As per Approved Plan)
Building No. 1 (As per Builder)
Ground Floor For Commercial, Meter Room & Parking
1 |  | Shop | 163.8281 | 0 | 253.9335 | Ground Floor For Commercial, Meter Room & Parking |  | 15.2275 | 15.22
2 |  | Shop | 161.0294 | 0 | 249.5956
3 |  | Shop | 200.2104 | 0 | 310.3261
4 |  | Shop | 272.7598 | 0 | 422.7776
5 |  | Shop | 109.2546 | 0 | 169.3446
6 |  | Shop | 108.5011 | 0 | 168.1767
7 |  | Shop | 108.5011 | 0 | 168.1767
8 |  | Shop | 108.1782 | 0 | 167.6762
9 |  | Shop | 108.1782 | 0 | 167.6762
Building No. 2 (B + C Wing) (As per Approved Plan)
Building No. 2 (As per Builder)
Ground Floor For Commercial, Meter Room & Parking
10 |  | Shop | 268.5618 | 0 | 416.2708 | Ground Floor For Commercial, Meter Room & Parking
11 |  | Shop | 260.3812 | 0 | 403.5908
12 |  | Shop | 220.0162 | 0 | 341.025
13 |  | Shop | 158.6614 | 0 | 245.9251 |  |  |  |  | 10.764
14 |  | Shop | 257.152 | 0 | 398.5855
15 |  | Shop | 240.2525 | 0 | 372.3913
16 |  | Shop | 168.8872 | 0 | 261.7751
17 |  | Shop | 169.2101 | 0 | 262.2756 |  |  |  |  | 10.764
18 |  | Shop | 232.7177 | 0 | 360.7124
19 |  | Shop | 154.2481 | 0 | 239.0846
20 |  | Shop | 122.8172 | 0 | 190.3667 |  |  |  |  | 10.764
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
45%
Building No. 1 (A Wing)
1st Floor For Residential (Part Terrace Area)
1 |  | 1BHK | 283.0394 | 0 | 410.4071 | 1st Floor For Residential (Part Terrace Area) |  | 26.295 | 26.305
2 |  | 1RK | 193.9673 | 0 | 281.2526 |  |  | 18.0225
3 |  | 1BHK | 268.8847 | 557.5214 | 529.2632
2nd to 4th Floor For Residential
1 |  | 1BHK | 283.0394 | 0 | 410.4071 | 2nd to 4th Floor For Residential |  | 26.295 | 26.305 | 10.764
2 |  | 1RK | 193.9673 | 0 | 281.2526 | 2nd to 4th Floor For Residential |  | 18.0225
3 |  | 1BHK | 268.8847 | 0 | 389.8828 | 2nd to 4th Floor For Residential
Building No. 2 (B Wing)
1st to 4th Floor For Residential
1 |  | 1BHK | 311.0527 | 0 | 451.0264 | 1st to 4th Floor For Residential
2 |  | 1BHK | 311.0527 | 0 | 451.0264
3 |  | 1BHK | 299.6698 | 0 | 434.5212 |  |  |  |  | 10.764
4 |  | 1RK | 174.3768 | 0 | 252.8464
5 |  | 1RK | 174.3768 | 0 | 252.8464
6 |  | 1BHK | 299.6698 | 0 | 434.5212
7 |  | 1BHK | 311.0527 | 0 | 451.0264
8 |  | 1BHK | 311.0527 | 0 | 451.0264
Building No. 2 (C Wing)
1st to 4th Floor For Residential
1 |  | 1BHK | 310.3261 | 0 | 449.9729 | 1st to 4th Floor For Residential
2 |  | 1BHK | 296.2253 | 0 | 429.5267 |  |  | 27.52
3 |  | 1BHK | 311.0527 | 0 | 451.0264
4 |  | 1BHK | 291.1823 | 0 | 422.2144
Building No. 2 (D Wing)
Ground Floor For Residential, Parking & Meter Room | [7 empty] | 21.9325
1 |  | 1BHK | 236.0545 | 0 | 342.2791 | Ground Floor For Residential, Parking & Meter Room |  | 16.2
2 |  | 1RK | 174.3768 | 0 | 252.8464 | Ground Floor For Residential, Parking & Meter Room |  |  |  | 10.764
3 |  | 1BHK | 236.0545 | 0 | 342.2791 | Ground Floor For Residential, Parking & Meter Room
4 |  | 1RK | 174.3768 | 0 | 252.8464 | Ground Floor For Residential, Parking & Meter Room
1st to 4th Floor For Residential
1 |  | 1BHK | 267.7007 | 0 | 388.166 | 1st to 4th Floor For Residential
2 |  | 1RK | 174.3768 | 0 | 252.8464
3 |  | 1BHK | 257.0443 | 0 | 372.7143
4 |  | 1BHK | 301.8226 | 0 | 437.6427
5 |  | 1BHK | 301.8226 | 0 | 437.6427
6 |  | 1RK | 174.3768 | 0 | 252.8464
7 |  | 1RK | 174.3768 | 0 | 252.8464
Building No. 2 (E Wing)
Ground Floor For Meter Room & Parking
1st to 4th Floor For Residential
1 |  | 1BHK | 301.8226 | 0 | 437.6427 | 1st to 4th Floor For Residential
2 |  | 1RK | 174.3768 | 0 | 252.8464
3 |  | 1RK | 174.3768 | 0 | 252.8464
Remarks:
1 | Wing A to E = Construction work is in process at the time of visit.
2 | We have considered Saleable area of Flats as per our Calculation.
3 | We have considered Saleable area of Commercial as per our Calculation.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Enclose balcony + C.B Area.
6 | We have considered proposed No. of Floor for Stage Calculation.
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | Survey No. mentioned in CC & Rera is 151/3, 151/6, 141/5A Survey No. mentioned in Approved Layout (Sheet No.1) is 151/3, 151/6, 141/5 As per approved layout plan, Building No. 8 is located on survey no. 141/5A. As per discussion with bank officials, report is released for 151/3, 151/6, 141/5.
11 | We have referred shop numbering as per builder nomenclature sheet provided to us on mail by bank officials. Please find the attachment below.
12 | As per visit dtd 13/08/2025, we have observed that construction work of Shop no. 1, 2, 3, 6, 7, 8 from Building No. 1 and Shop no. 11, 12, 13, 16, 17 from Building No. 2 are Completed.Therefore it can be considered as Progress 100% and Disbursement 100%.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Naynesh Sunil Lovanshi |  | Report By : |  | Pooja
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Dhruv Residency Platinum
PHOTOGRAPHS OF PROPERTY : |  |  | Dhruv Residency Platinum
Layout :
Remark No.11 :
Google Map :
Building No. 1 (A Wing)
Building No. 2 (B Wing)
Building No. 2 (C Wing)
Building No. 2 (D Wing)
Building No. 2 (E Wing)
Building No. 2 (B Wing)
Building No. 2 (C Wing)
Building No. 2 (D Wing)
Building No. 2 (E Wing)
141/5A
141/5A
A Wing
Building No. 2 (D Wing)
Building No. 2 (E Wing)
A Wing
A Wing
B Wing
C Wing
D Wing
E Wing
Shop No.17
Shop No.17

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted