## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 18/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-18
Name of the builder group |  |  |  |  | M/s.Royale Urbanspace
Name of the builder company |  |  |  |  | M/s.Royale Urbanspace
Name of the Project |  |  |  |  | Royale City - Tulip
Contect Details ( Name & Contect No.) |  |  |  |  | 2225091011
Site Meet Person Contect Details ( Name & Contect No.) |  |  |  |  | NA
Name / no of the Building |  |  |  |  | Building (N1, O1) Building (N2, N3) Building (N4, N5) Building (P3, P4)
Docouments Provided |  |  |  |  | Approved Plans, CC
Name of the Project as per RERA = Wings on RERA = RERA No. |  |  |  |  | Tulip N = N4, N5 = P51700011791 Tulip P = P3, P4 = P51700011815 Tulip N1 N2 N3 O1 = N1, N2, N3, O1 = P51700019737
Project location details |  | Royale City - Tulip, Gut No.- 44/1, Borsheti, Shahapur, Thane
Plot No | NA |  |  | G. No |  | 44/1 | Locality | Borsheti
Road | Mumbai Nashik National Highway. |  |  |  | District | Thane
City | Shahapur |  |  |  | Pin Code | 421601
Near by Landmark |  | Royale city Orchid |  |  | Distance from city centre: |  | About 3.2 Km from Asangoan Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open Plot. |  | Open Plot |  | Open Plot.
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.4350523, 73.3258298
Location Link |  | https://goo.gl/maps/ZBeo1r76bnRA22UM6
Approval details:
Approved usage of the Property: Residential (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 20000
Permissible FSI |  |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.75
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 15000
Total number of Buildings |  |  |  |  | 04 Building (8 Wings)
Approval Detail : Plan approval
Layout Approval No |  | VS/BP/BORSHETI/SHAHAPUR/SSTN/933 |  |  |  | Dated | 16/04/2013. | Expiry date:NA
Building plan approval No |  | VS/BP/BORSHETI/SHAHAPUR/SSTN/933 |  |  |  | Dated | 16/04/2013. | Expiry date:NA
Date of Commencement of Construction |  | VSP/BP/BORSHETI/SHAHAPUR/SSTN/933 Valid Up to: Building type : N,O, P = G + 1st to 4th Floor |  |  |  | Dated | 16/04/2013.
O. Certificate No.: |  | Mahsul/K-1/T-11/SR-05/19 Approved Upto : Bldg N4 & N5 = Gr/Stilt + 1st to 4th Floor |  |  | Date of approval: NA | Dated | 2019-12-27
|  | Mahsul/K-1/T-11/O.C.P./SR-1/2020 Approved Upto : Bldg P3 & P4 = Gr/Stilt + 1st to 4th Floor |  |  | Date of approval: NA | Dated | 2020-01-28
Commencement date of construction |  |  | 16/04/2013. |  | Expected Completion |  | 30/12/2025
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 15000 |  | Approved no of units |  |  | 205
Approved no of Floors |  | Building type : N,O, P = G + 1st to 4th Floor
Quality of construction: Good |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details: |  | Building N1 & O1 = G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC upto 4.5 Slab, Brickwork upto 2 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 4.5 Slab, Brickwork upto 2 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 49.75% |  | 74.5% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 4.5 | 90% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 2 | 50% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building N2 & N3 = G + 1st to 4th Floor | [6 empty] | Excavation work Completed. Footing work is process
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | Excavation work Completed. Footing work is process | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 2.5% |  | 26.25% |  | Excavation in process | 2
Plinth |  | 1 | 25% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 0 | 0% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 0 | 0% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% | [5 empty] | Plinth in process | 3
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 4
Construction details: |  | Building (P3 & P4) & (N4 & N5) = G + 1st to 4th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 4
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1
Excavation |  | 4 | 100% |  | 100% |  | 100% |  | Excavation in process | 2
Plinth |  | 4 | 100% | [5 empty] | Excavation Completed | 4
RCC (Including podiums) |  | 5 | 100% | [5 empty] | Footing in Process | 1
Brickwork | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Footing Completed | 2
Internal Plaster | Brickwork & Internal Plaster | 4 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 4 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 4 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 4 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 4 | 100% | [5 empty] | Plinth in process | 3
Possession |  | 4 | 100% | [5 empty] | Plinth completed | 4
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities : 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3800
Advance maintainence charges for 24 months | [5 empty] | 40,000/-
Recommended rate of Parking | [5 empty] | 150000/-
Distressed valuation of the Property | [5 empty] | 3040
Residential Area Details :
Building & Wing |  | No. of Flats | Total Gross Carpet Area |  |  | Total Saleable Area
N1 |  | 27 | 9778.2759 |  |  | 14985
N2 |  | 27 | 9572.8988 |  |  | 14985
N3 |  | 27 | 9572.8988 |  |  | 14985
N4 |  | 27 | 9572.8988 |  |  | 14985
N5 |  | 27 | 9572.8988 |  |  | 14985
O1 |  | 18 | 7410.4973 |  |  | 11640
P3 |  | 26 | 6847.8415 |  |  | 10790
P4 |  | 26 | 6847.8415 |  |  | 10790
Total |  | 205 | 69176.0516 |  |  | 108145
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Type - N1
Ground Floor.
1 |  | 1BHK | 315.0838 |  | 0 | 555 | N | Ground Floor.
2 |  | 1BHK | 315.0838 |  | 0 | 555 | N
3 |  | 1BHK | 315.0838 |  | 0 | 555 | N
4 |  | Stilt Area
5
6
1st to 4th Floor.
1 |  | 1BHK | 368.85 |  | 0 | 555 | N | 1st to 4th Floor.
2 |  | 1BHK | 366.9125 |  | 0 | 555 | N
3 |  | 1BHK | 366.9125 |  | 0 | 555 | N
4 |  | 1BHK | 368.85 |  | 0 | 555 | N
5 |  | 1BHK | 368.85 |  | 0 | 555 | N
6 |  | 1BHK | 367.8812 |  | 0 | 555 | N
Type -N2 & N3
Ground Floor.
1 |  | 1BHK | 315.0838 |  | 0 | 555 | N | Ground Floor.
2 |  | 1BHK | 315.0838 |  | 0 | 555 | N
3 |  | 1BHK | 315.0838 |  | 0 | 555 | N
4 |  | Stilt Area
5
6
1st to 4th Floor.
1 |  | 1BHK | 368.85 |  | 0 | 555 | N | 1st to 4th Floor.
2 |  | 1BHK | 341.2403 |  | 0 | 555 | N
3 |  | 1BHK | 341.2403 |  | 0 | 555 | N
4 |  | 1BHK | 368.85 |  | 0 | 555 | N
5 |  | 1BHK | 368.85 |  | 0 | 555 | N
6 |  | 1BHK | 367.8812 |  | 0 | 555 | N
Type - N4 & N5
Ground Floor.
1 |  | 1BHK | 315.0838 |  | 0 | 555 | N | Ground Floor.
2 |  | 1BHK | 315.0838 |  | 0 | 555 | N
3 |  | 1BHK | 315.0838 |  | 0 | 555 | N
4 |  | Stilt Area
5
6
1st to 4th Floor.
1 |  | 1BHK | 368.85 |  | 0 | 555 | N | 1st to 4th Floor.
2 |  | 1BHK | 341.2403 |  | 0 | 555 | N
3 |  | 1BHK | 341.2403 |  | 0 | 555 | N
4 |  | 1BHK | 368.85 |  | 0 | 555 | N
5 |  | 1BHK | 368.85 |  | 0 | 555 | N
6 |  | 1BHK | 367.8812 |  | 0 | 555 | N
Type - O1
Ground Floor.
1 |  | 1BHK | 387.0089 |  | 0 | 800 | N | Ground Floor.
2 |  | 1BHK | 387.0089 |  | 0 | 840 | N
3 |  | Stilt Area
4
1st to 4th Floor.
1 |  | 1BHK | 414.78 |  | 0 | 625 | N | 1st to 4th Floor.
2 |  | 1BHK | 414.78 |  | 0 | 625 | N
3 |  | 1BHK | 414.78 |  | 0 | 625 | N
4 |  | 1BHK | 414.78 |  | 0 | 625 | N
Type - P3 & P4
Ground Floor
1 |  | 1RK | 236.7004 |  | 0 | 475 | N | Ground Floor.
2 |  | 1RK | 236.7004 |  | 0 | 475 | N
3 |  | Stilt Area
4
5
6
1st to 4th Floor.
1 |  | 1RK | 266.2475 |  | 0 | 410 | N | 1st to 4th Floor.
2 |  | 1RK | 265.2788 |  | 0 | 410 | N
3 |  | 1RK | 265.2788 |  | 0 | 410 | N
4 |  | 1RK | 265.2788 |  | 0 | 410 | N
5 |  | 1RK | 265.2788 |  | 0 | 410 | N
6 |  | 1RK | 266.2475 |  | 0 | 410 | N
Remarks: 1. Bldg (N1, O1) - Construction work is same since visit (08/02/2024). & Bldg (N2, N3) - Work is same as visit since visit (04/02/2022). Bldg (N4, N5) & Bldg (P3, P4) - All work Completed. OC Received. 2. We considered Saleable area as per Builder Area sheet. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. We have considered Other charges from cost sheet. 6. Car parking is subjected to authentic documentation. 7. We have updated OC from Rera for Building N4, N5, P3 & P4 (dtd.14/05/2024). 8. As building have received CC on 16/04/2013, still construction work of Building N1 to N3 & O1 is pending. 7. On site, we meet Mr. Bharat - 7875322675.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Builder area Sheet.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Royale City - Tulip
Google Map :
N1
N1
O1
N4
N5
P3
P4

## N1,O1
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 | 0 | Progress |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 4 | 0 | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 4 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 10 | 30

## N2, N3
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 5 |  | 50
slab | total slab | completed slab |  | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 0 |  | 0 | Progress |  |  | 5 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor |  | 0 | Recommended |  |  | 25 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 |  | 0
plaster | Total Floor | completed Floor |  | 0
| 4 | 0 |  | 0
Flooring | Total Floor | completed Floor
| 4 | 0 |  |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  |  | Plinth | 5 | 25
| 4 | 0 |  |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  |  | Bricks | 0 | 0
| 4 | 0 |  |  | Plaster | 0 | 0
[5 empty] | Flooring | 0 | 0
[5 empty] | Wood & painting | 0 | 0
[5 empty] | Finishing | 0 | 0
[5 empty] | total | 5 | 25
Excavation in process |  |  | 1% | 2%
Excavation Completed |  |  | 1% | 3%
Footing in Process |  |  | 3% | 8%
Footing Completed |  |  | 5% | 15%
Plinth in process |  |  | 7% | 20%
Plinth completed |  |  | 10% | 30%

## C% P3 P4
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 5 | 5
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 5 | 5
| 4 | 4 | 100
plaster | Total Floor | completed Floor | 100
| 4 | 4 | 100
Flooring | Total Floor | completed Floor
| 4 | 4 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 4 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 4 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 5 | 5
|  |  |  | Finishing | 5 | 5
|  |  |  | total | 95 | 100

## C% N3& N4
Particulars | totaL floor | 4
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 5 | 5 | 100 | Progress |  |  | 10 | 40 | 15 | 10 | 10 | 5 | 5
Bricks | Total Floor | completed Floor | 100 | Recommended |  |  | 30 | 30 | 15 | 10 | 5 | 5 | 5
| 4 | 4 | 100
plaster | Total Floor | completed Floor | 100
| 4 | 4 | 100
Flooring | Total Floor | completed Floor
| 4 | 4 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 4 | 4 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 4 | 4 |  | Plaster | 10 | 10
|  |  |  | Flooring | 10 | 5
|  |  |  | Wood & painting | 5 | 5
|  |  |  | Finishing | 5 | 5
|  |  |  | total | 95 | 100

## Note
30/09/2020.

## Sheet1
1302-ELLORA FIESTA, PLOT NO. 8, SECTOR 11, OPP. JUINAGAR RAILWAY STATION, SANPADA, NAVI MUMBAI 400 706. TEL: 022-27758396/95. FAX :022-27758394. E mail : axisbank@vsjadon.com. vsjcvaluer@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 03/10/2020.
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 29/09/2020.
Name of the builder group |  |  |  |  | M/s.Royale Urbanspace LLP
Name of the builder company |  |  |  |  | M/s.Royale Urbanspace LLP
Name of the Project |  |  |  |  | Royale City - Tulip
Contect Details ( Name & Contect No.) |  |  |  |  | 2225091011
Name / no of the Building |  |  |  |  | Building (L1) Building (L2, L3) Building (M1, M2) Building (N1, O1) Building (N2, N3) Building (N4, N5) Building (P1, P2) Building (P3, P4)
Docouments Provided |  |  |  |  | Approved Layout, CC
Name of the Project as per RERA = RERA No. |  |  |  |  | Tulip N = P51700011791 Tulip P = P51700011815
Project location details |  | Royale City, Gut No.- 44/1, Borsheti, Shahapur, Thane
Plot No | NA |  |  | G. No |  | 44/1 | Locality | Borsheti
Road | Mumbai Nashik National Highway. |  |  |  | District | Thane
City | Shahapur |  |  |  | Pin Code | 421601
Near by Landmark |  | Royale city Orchid |  |  | Distance from city centre: |  | About 3.2 Km from Asangoan Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open Plot. |  | Open Plot |  | Open Plot.
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 19.4351 |  | Longitude |  | 73.3258
Approval details:
Approved usage of the Property: Residential (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 20000
Permissible FSI |  |  |  |  | 0.75
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 0.75
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 15000
Total number of Buildings |  |  |  |  | 10
Approval Detail : Plan approval
Layout Approval No |  | VS/BP/BORSHETI/SHAHAPUR/SSTN/933 |  |  |  | Dated | 16/04/2013. | Expiry date:NA
Building plan approval No |  | VS/BP/BORSHETI/SHAHAPUR/SSTN/933 |  |  |  | Dated | 16/04/2013. | Expiry date:NA
Date of Commencement of Construction |  | VSP/BP/BORSHETI/SHAHAPUR/SSTN/933 Valid Up to: Building type : L, M, N,O, P = G + 4th Floor |  |  |  | Dated | 16/04/2013. | Expiry date: One year from date of issue
O. Certificate No.: NA |  |  |  |  | Date of approval: NA |  |  | Expiry date: NA
Commencement date of construction |  |  | 16/04/2013. |  | Expected Completion |  | 31/12/2019.
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 15000 |  | Approved no of units |  |  | 257
Approved no of Floors |  | Building type : L, M, N,O, P = G + 4th Floor |  |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  |  |  | Projected life of the structure: 60 Years After Completion
Material laying at Site: :Bricks, Cement & Steel etc.
Construction details:
Stage of construction (L1, L2, L3, M1, M2, N1, N2, N3, O1, P1 & P2): Work not started Yet.
|  | Type of Work |  |  | % Complition
|  | Plinth |  |  | 0
|  | RCC |  |  | 0
|  | Brick |  |  | 0
|  | Plaster |  |  | 0
|  | Flooring |  |  | 0
|  | Painting & Wooden Work |  |  | 0
|  | Finishing |  |  | 0
% Progress |  |  | 0 |  | % Disbursement |  |  | 0
Stage of construction (P3 & P4): Building Construction is completed. Wait for OC.
|  | Type of Work |  |  | % Complition
|  | Plinth |  |  | 100
|  | RCC |  |  | 100
|  | Brick |  |  | 100
|  | Plaster |  |  | 100
|  | Flooring |  |  | 100
|  | Painting & Wooden Work |  |  | 100
|  | Finishing |  |  | 100
% Progress |  |  | 95 |  | % Disbursement |  |  | 100
Stage of construction (P4 & P5): Building Construction is completed. Wait For OC.
|  | Type of Work |  |  | % Complition
|  | Plinth |  |  | 100
|  | RCC |  |  | 100
|  | Brick |  |  | 100
|  | Plaster |  |  | 100
|  | Flooring |  |  | 100
|  | Painting & Wooden Work |  |  | 100
|  | Finishing |  |  | 100
% Progress |  |  | 95 |  | % Disbursement |  |  | 100
Wheather the construction is as per approved Building plan : Under Construction
Violations Observed if any : NA
Proposed Amenities 1. Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3000
Floor rise rate Per Sq. Ft. | [5 empty] | NA
PLC charges | [5 empty] | NA
Club Charges | [5 empty] | NA
Any Other amenities | [5 empty] | NA
Society formation charges | [5 empty] | NA
Recommended rate of Parking | [5 empty] | NA
Development charges Per Sq. Ft. | [5 empty] | NA
Valuation as per Government reckoners rates | [5 empty] | NA
Distressed valuation of the Property | [5 empty] | 2400
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area | PLC Y/N | Floor
Type - N1
Ground Floor.
1 |  | 1BHK | 315.0838 |  | 0 | 456.8715 | N | Ground Floor.
2 |  | 1BHK | 315.0838 |  | 0 | 456.8715 | N
3 |  | 1BHK | 315.0838 |  | 0 | 456.8715 | N
4 |  | Stilt Area
5
6
1st to 4th Floor.
1 |  | 1BHK | 368.85 |  | 0 | 534.8325 | N | 1st to 4th Floor.
2 |  | 1BHK | 366.9125 |  | 0 | 532.0231 | N
3 |  | 1BHK | 366.9125 |  | 0 | 532.0231 | N
4 |  | 1BHK | 368.85 |  | 0 | 534.8325 | N
5 |  | 1BHK | 368.85 |  | 0 | 534.8325 | N
6 |  | 1BHK | 367.8812 |  | 0 | 533.4278 | N
Type -N2 & N3
Ground Floor.
1 |  | 1BHK | 315.0838 |  | 0 | 456.8715 | N | Ground Floor.
2 |  | 1BHK | 315.0838 |  | 0 | 456.8715 | N
3 |  | 1BHK | 315.0838 |  | 0 | 456.8715 | N
4 |  | Stilt Area
5
6
1st to 4th Floor.
1 |  | 1BHK | 368.85 |  | 0 | 534.8325 | N | 1st to 4th Floor.
2 |  | 1BHK | 341.2403 |  | 0 | 494.7985 | N
3 |  | 1BHK | 341.2403 |  | 0 | 494.7985 | N
4 |  | 1BHK | 368.85 |  | 0 | 534.8325 | N
5 |  | 1BHK | 368.85 |  | 0 | 534.8325 | N
6 |  | 1BHK | 367.8812 |  | 0 | 533.4278 | N
Type - N4 & N5
Ground Floor.
1 |  | 1BHK | 315.0838 |  | 0 | 456.8715 | N | Ground Floor.
2 |  | 1BHK | 315.0838 |  | 0 | 456.8715 | N
3 |  | 1BHK | 315.0838 |  | 0 | 456.8715 | N
4 |  | Stilt Area
5
6
1st to 4th Floor.
1 |  | 1BHK | 368.85 |  | 0 | 534.8325 | N | 1st to 4th Floor.
2 |  | 1BHK | 341.2403 |  | 0 | 494.7985 | N
3 |  | 1BHK | 341.2403 |  | 0 | 494.7985 | N
4 |  | 1BHK | 368.85 |  | 0 | 534.8325 | N
5 |  | 1BHK | 368.85 |  | 0 | 534.8325 | N
6 |  | 1BHK | 367.8812 |  | 0 | 533.4278 | N
Type - O1
Ground Floor.
1 |  | 1BHK | 387.0089 |  | 0 | 561.1628 | N | Ground Floor.
2 |  | 1BHK | 387.0089 |  | 0 | 561.1628 | N
3 |  | Stilt Area
4
1st to 4th Floor.
1 |  | 1BHK | 414.78 |  | 0 | 601.431 | N | 1st to 4th Floor.
2 |  | 1BHK | 414.78 |  | 0 | 601.431 | N
3 |  | 1BHK | 414.78 |  | 0 | 601.431 | N
4 |  | 1BHK | 414.78 |  | 0 | 601.431 | N
Type - P1 & P2
Ground Floor
1 |  | 1RK | 236.7004 |  | 0 | 343.2155 | N | Ground Floor.
2 |  | 1RK | 236.7004 |  | 0 | 343.2155 | N
3 |  | Stilt Area
4
5
6
1st to 4th Floor.
1 |  | 1RK | 266.2475 |  | 0 | 386.0589 | N | 1st to 4th Floor.
2 |  | 1RK | 265.2788 |  | 0 | 384.6542 | N
3 |  | 1RK | 265.2788 |  | 0 | 384.6542 | N
4 |  | 1RK | 265.2788 |  | 0 | 384.6542 | N
5 |  | 1RK | 265.2788 |  | 0 | 384.6542 | N
6 |  | 1RK | 266.2475 |  | 0 | 386.0589 | N
Type - P3 & P4
Ground Floor
1 |  | 1RK | 236.7004 |  | 0 | 343.2155 | N | Ground Floor.
2 |  | 1RK | 236.7004 |  | 0 | 343.2155 | N
3 |  | Stilt Area
4
5
6
1st to 4th Floor.
1 |  | 1RK | 266.2475 |  | 0 | 386.0589 | N | 1st to 4th Floor.
2 |  | 1RK | 265.2788 |  | 0 | 384.6542 | N
3 |  | 1RK | 265.2788 |  | 0 | 384.6542 | N
4 |  | 1RK | 265.2788 |  | 0 | 384.6542 | N
5 |  | 1RK | 265.2788 |  | 0 | 384.6542 | N
6 |  | 1RK | 266.2475 |  | 0 | 386.0589 | N
Remarks: 1. Construction work was in process. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered recommended rate as per Market Inquire. 5. Building Type - L & M Approved plans are not provided to us. 6. Building type : (L1, L2, L3, M1, M2, N1, N2, N3, O1, P1 & P2): Work not started Yet.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY OF CUSTOMER: |  |  |  |  | Royale City - Tulip
Google Map :

## Valuation
2020-10-03 | Pratiksha | Market Research Data
|  | Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
|  | Makkan | Royal city Tulip N | 1BHK | 395 | 572.75 | 3491.9319 | 2000004
|  | Makkan | Royal city Tulip N | 1BHK | 575 | 833.75 | 2186.5067 | 1823000
|  | Housing | Royal city Tulip | 1RK | 278 | 444 | 2477.4775 | 1100000
|  | Housing | Royal city Tulip P | 1RK | 282.7586 | 410 | 3048.7805 | 1250000
|  | Housing | Royal city Tulip N | 1RK | 272.4138 | 395 | 3415.1899 | 1349000
|  | Makkan | Royal city | 1BHK | 275 | 398.75 | 2721.0031 | 1085000
|  | Makkan | Royal city Tulip P | 1BHK | 410 | 594.5 | 2102.6072 | 1250000
|  | Average |  |  |  |  | 2777.6424
|  | Valuation Adopted |  |  |  |  | 2800

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 3.85 | 10.5875 | CB | 2.75 | 0.9 | 2.475 |  |  | 0
|  |  |  | 0 | FB | 2.7 | 0.9 | 2.43 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.2 | 2.5 | 5.5 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 2.6 | 2.9 | 7.54 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.2 | 0.92 | 1.104 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.2 | 1.5 | 1.8 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 2 | 0.9 | 1.8 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 304.9603 | 28.3315 |  |  | 52.7974 | 4.905 |  | 0 | 0
33.2365

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 2.75 | 4.4 | 12.1 | CB | 3.5 | 0.9 | 3.15 |  |  | 0
|  |  |  | 0 | FB | 0 | 0 | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch | 2.5 | 2.2 | 5.5 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 0 | 0 | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 1.5 | 1.2 | 1.8 | DB |  |  | 0 |  |  | 0
| toilet2 | 0.9 | 1.2 | 1.08 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1 | 1 | 1 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 231.2107 | 21.48 |  |  | 33.9066 | 3.15 |  | 0 | 0
24.63

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0