## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  | 29/08/2025
Name of Branch : |  |  | IDBI Belapur
Date Of Property Visit |  |  | 2025-08-20
Name of the builder group |  |  | M/s. Konnark Zenith
Name of the builder company |  |  | M/s. Konnark Zenith
Address of Builder/Developer |  |  | 9th Floor, Office No. 908, Plot No. 87, Shelton Cubix, Near Varsha Buildcon, Sector 15, CBD Belapur, Tal. Thane, Dist. Thane 400614. |  |  |  |  | Rera
Contact Details |  |  | Mr. Shubham Shinde 9702461682
Architect Name |  |  | Anurag Chatterjee
Name of the Project |  |  | Konnark Astra
Name / No of the Building |  |  | 01 Building
Name / No of the Existing Building |  |  | NA
Docouments Provided |  |  | Approved Plans & CC. | [12 empty] | Thane | Palghar | Mumbai | Raigad | Pune
RERA No. |  |  | PM1270002500149 | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Address of the Project |  |  | Konnark Astra, Plot No.54 & 58, near Today Group Codename Goldrush Panvel, Mumbai Goa Highway, Giravale, Palaspa, Panvel, Panvel, Raigad - 410221. | [12 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Nearby Landmark |  |  | Today Group Codename Goldrush Panvel | [15 empty] | Mahasala | Bhor
Plot No |  |  | 54 & 58 | [12 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  |  | Mumbai Goa Highway | [12 empty] | Ambernath | Dahanu |  | Pen | Shirur
Locality/Village |  |  | Giravale, Palaspa | [12 empty] | Murbad | Wada |  | Sudhagad | Indapur
City |  |  | Panvel | [5 empty] | Pune City | [9 empty] | Mahad | Daund
Taluka |  |  | Panvel | [15 empty] | Roha | Mawal
District |  |  | Raigad | District | [14 empty] | Mangaon | Ambegaon
Pin Code |  |  | 410221 | Pin Code | [14 empty] | Poladpur | Purandhar
Latitude & Longitude |  |  | 18.945442,73.135881 | Longitude | [11 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Location Link |  |  | https://maps.app.goo.gl/LF1mtxgvcoeb1Fm77 | Longitude | [11 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Distance from city centre: |  |  | 7.4KM from Panvel Railway Station | Distance from city centre: |  | from ……. Railway Station | [12 empty] | Shriwardhan | Mulshi
Class of locality |  |  | Middle Class
Proximity to Civic Amenities |  |  | All available at 1 to 3 km. | [15 empty] | Murud | Velhe
Nature of the locality |  |  | Developing
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  |  | Maharashtra State Road Development Corporation Limited (MSRDC) | [11 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  |  | MSRDC/B/2025/APL/00119 |  |  | Dated | 2025-04-28
Approved Floor plan No. |  |  | MSRDC/B/2025/APL/00119 |  |  | Dated | 2025-04-28
Commencement Certificate No. |  |  | MSRDC/B/2025/APL/00119 |  |  | Dated | 2025-04-28
Valid Up to: |  |  | G + 1st to 24th Floor
O. Certificate No.: |  |  | NA Approved upto : NA | Date of approval: |  | Dated | NA
Building wise Construction details
Approved usage of the Property: |  |  | Residential + Commercial
Total number of Buildings |  |  | 01 Building
Approved no of units |  |  | Flats - 126, Shops - 18
Approved no of Floors |  |  | G + 1st to 24th Floor
Proposed no of Floors |  |  | G + 1st to 31st Floor
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Shops |  | 18 |  | 5693.2088 |  | 8824.4736 |  | OK
Total |  | 18 |  | 5693.2088 |  | 8824.4736
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flats |  | 126 |  | 72689.6472 |  | 109034.4708 |  | OK
Total |  | 126 |  | 72689.6472 |  | 109034.4708
Grand Total |  | 144 |  | 78382.856 |  | 117858.9444
Building Details Floor Wise
Details of Commercial & Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet Area | Attached Loft area | Gross Carpet Area | Attached Otla Area | Saleable area Loading : | 10.764
55%
Ground Floor For Commercial, Entrance Lobby, Society Office, Meter Room, Telecom Room, Driver Room & Parking
1 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485 | 29.3232
2 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
3 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
4 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
5 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
6 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
7 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
8 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
9 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
1st Floor For Commercial & Podium Parking | [7 empty] | 1
10 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
11 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
12 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
13 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
14 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
15 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
16 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
17 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
18 |  | Shop | 316.2894 | 0 | 316.2894 | 0 | 490.2485
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet Area | Balcony + AP Area | Gross Carpet Area | Attached Terrace area | Saleable area Loading : | 10.764
50%
2nd Floor For Podium Parking, Driveway & Ramp Driveway | [7 empty] | 1
3rd to 6th, 8th to 11th, 14th to 16th, 18th to 21st, 23rd to 24th Floor For Residential | [7 empty] | 17
1 |  | 2BHK | 616.3359 | 99.1418 | 715.4777 | 0 | 1073.2165 |  | 54.7887 | 54.8787
2 |  | 2BHK | 616.3359 | 99.1418 | 715.4777 | 0 | 1073.2165
3 |  | 1.5BHK | 535.7028 | 83.8516 | 619.5543 | 0 | 929.3315 |  |  | 47.5437
4 |  | 1BHK | 406.7716 | 65.2298 | 472.0014 | 0 | 708.0021 |  |  | 36.3197
5 |  | 1BHK | 406.7716 | 65.2298 | 472.0014 | 0 | 708.0021
6 |  | 1BHK | 402.2507 | 64.6486 | 466.8993 | 0 | 700.3489
13th Floor as Recreational Floor | [7 empty] | 1
7th, 12th, 17th & 22nd Floor (With Refuge Area) | [7 empty] | 4
1 |  | 2BHK | 616.3359 | 99.1418 | 715.4777 | 0 | 1073.2165 |  | 7100000 | 6615.6267 |  | 701,..,2201 | 701 | 2201
2 |  | 2BHK | 616.3359 | 99.1418 | 715.4777 | 0 | 1073.2165 |  |  |  |  | 702,..,2202 | 702 | 2202
3 |  | 1.5BHK | 535.7028 | 83.8516 | 619.5543 | 0 | 929.3315 |  | 5800000 | 6241.0455 |  | 703,..,2203 | 703 | 2203
4 |  | 1BHK | 406.7716 | 65.2298 | 472.0014 | 0 | 708.0021 |  |  |  |  | 704,..,2204 | 704 | 2204
5 |  | 1BHK | 406.7716 | 65.2298 | 472.0014 | 0 | 708.0021 |  | 4800000 | 6779.6409 |  | 705,..,2205 | 705 | 2205
6 |  | 1BHK | 402.2507 | 64.6486 | 466.8993 | 0 | 700.3489 |  |  |  |  | 706,..,2206 | 706 | 2206
- |  | - | Refuge Area | [8 empty] | 707,..,2207 | 707 | 2207
Type of Structure |  |  | RCC Frame Structure
Quality of infrastructure in vicinity |  |  | Good
Proposed Amenities : |  |  | Swimming Pool, Landscaping & Garden, Vitrified tiles flooring, Granite Kitchen Platform & Decorative Entrance etc.
Realizable Rates of the Property : |  |  | On Saleable Area | [6 empty] | 4663.6938 | 10
Rate of Flat Per Sq. Ft. |  |  | 5500
Rate of Shop Per Sq. Ft.
Rate of Office Per Sq. Ft.
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
Recommended rate of Parking |  |  | 250000
Government Ready Reckoner Rate (in sqft)
For Residential |  |  | 4663.6938
Rate of Shop Per Sq. Ft.
Rate of Office Per Sq. Ft.
Floor Rise Rate Per Sq.ft |  |  |  |  | NA
Development Charges |  |  |  |  | NA
Society Formation Charges |  |  |  |  | NA
Advance Maintenance Charges |  |  |  |  | NA
For Land |  |  | 404.1249
Construction details of the Property :
Building/Wing : |  | G + 1st to 31st Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 31
Stage of construction: |  | Work not yet Started. | [5 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 7.75
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 15.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 31
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 7.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 15.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 23.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 31
Date of commencement |  |  | 2025-04-28
Expected Completion |  |  | As per RERA - 30/12/2033
Future estimated life of the structure |  |  | 60 Years After Completion
Remarks:
* | Work not yet started.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We have considered Saleable area of Flats as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Balcony + AP Area.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | On Site, We meet Mr Deepak Jadhav (Ph no 8928459306)
* | Please check for Fire NOC, Airport NOC.
* | We have given Valuation for Sale Flats and Shops only.
* | NO REMARK FOR CC
Signature
Name of the Valuer |  | Mr. Vishwajeet Singh Jadon
Name of the Site Engineer |  | Mr. Ravindra Vishwakarma
Channel
CERTIFICATE
I, have personally inspected the above said property on29/08/2025 And met Mr Deepak Jadhav (Ph no 8928459306).The value of the property is taken on the area basis. | [9 empty] | 8928459306
I hereby declare that:
1. The information furnished is true and correct to the best of my knowledge and belief.
2. I have no direct or indirect interest in the property valued.
Place : | Navi Mumbai |  |  | Signature of the Valuer.
Date : | 29/08/2025
PHOTOGRAPHS OF PROPERTY : |  |  | Konnark Astra
Layout
Ready Reckoner Rate
Google Map :
Konnark Astra
Note on D12: SACHIN: Building No. Tower No. Wing Bunglow No., etc
Note on D13: SACHIN: If exisiting Building is provided write it or else NA
Note on D134: SACHIN: First CC Date

## Remark
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34 | As per Approved Floor Plan, In C to E wing on Ground floor Shop No. 19 & 20 are merged into single shop.
35 | There are guest houses, villas, resorts, etc. in a range of 200 to 300 meters. There are few residential buildings available in the surrounding areas. (within 500 meters) There are inadequate transportation options to get to the project and the area is not developed
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Valuation
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe