## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-08-18
Branch Name/ID |  | Mahindra Rural Housing Finance - Kalyan |  |  | Date & Time of Site Visit | 20/08/2025 at 05:46PM
Name of the person met at site & Contact No |  | Mr. Abdul 9920155998 |  |  | Date of Report Release | 2025-08-21
Project Details
Name of the project |  | Chandrangan Residency Phase IV
Address |  | Chandrangan Residency Phase IV, Survey No.67/2 & 67/4, near Chandrangan Residency Phase 2, Sabe Road, Diva, Diva, Thane, Thane - 400612. | [9 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 67/2 & 67/4 | [9 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Diva | [9 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Sabe Road | [9 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Diva | [9 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Thane | [9 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Thane | [9 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 400612 | [9 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P51700056036 | [12 empty] | Mahad | Daund
Landmark |  | Chandrangan Residency Phase 2 | [12 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.184124,73.040733 | [9 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/MS1hWkFT32wiRSvw9 | [12 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Ekveera Enterprises | [12 empty] | Mahasala | Bhor
Office address (agreement) |  | Survey No.70/6H, Chandrangan Residency Phase 2, Near Kalpataru Jewellers, Diva Shil Road, Diva East, Thane, Thane-4000612 | [12 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [12 empty] | Murud | Velhe
Builder Bank Details |  | Bharat Co-op Bank Mumbai Ltd IFSC - BCMB0000091
Contact No. |  | Mr. Abdul 9920155998
Location of the project Municipal Limit : |  | Thane Municipal Corporation (TMC)
Project Type (Apartments/Plot/ Combined) |  | Apartments
No of Wings / Buildings |  | Bunglow & Building A |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | Flats = 226, Bunglow = 01 |  |  | Exposure Limit (Proposed) | 34.05 |  |  |  |  | 227
Approved No. of Floor |  | Bunglow = Stilt/Gr + 1st to 2nd Floor Building A = Stilt + 1st to 21st Floor
Proposed No. of Floor |  | Bunglow = Stilt/Gr + 1st to 2nd Floor Building A = Stilt + 1st to 21st Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | S No. 67 H No.5 | S No.74 | S No 69 H No.6 | Other Plot
|  | Physical on site |  | Shiv kutir | Open Plot | Chandrangan Residency Phase 2 | Residential Building
Verification of survey No. (Title document) |  | Survey No. 67 Hissa No. 2 & Survey No. 67 Hissa No. 4 | [5 empty] | As per RERA (On 04/04/2025)
Plot area mentioned in the sale deed (As per 7/12) |  | 3340 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 3283.83
Approach road |  | Yes, Approx 32ft
Connectivity |  | 1. 0.13Km From New Holy Spirit School. 2. 0.35Km From Diva High School & Junior College. 3. 0.4Km From Vivek Memorial Astha Hospital. 4. 0.55Km From Jivdani Hospital. 5. 0.15Km From Sai Mandir. 6. 0.2Km From Vitthal Mandir. 7. 0.22Km From Sirvi Super Bazar 8. 0.082Km From Laxmi Super Market 9. 1Km From Diva Mohatsav Naka Bus Stop. 10. 0.55Km From Diva Junction Railway Station.
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 3283.83
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 2.8686
|  | Total FSI availaible for the project |  |  |  | 3.9686
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 13135.29
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 13032.09
Building plan approvals - Approval No : |  | TMCB/RB/2024/APL/00153 Date - 27/03/2024
Building height / No. of Floors |  | Bunglow = Stilt/Gr + 1st to 2nd Floor (Height = 11.65m) Building A = Stilt + 1st to 21st Floor (Height = 64.50m)
Construction/Building Permission |  | TMCB/RB/2024/APL/00153 Date - 27/03/2024 Bunglow = Stilt/ Gr. + 1st to 2nd Floor Building A = Stilt + 1st to 21st Floor
NA / Land conversion |  | Name of the Authority : |  | Collector Of Thane
|  | Reference No : |  | K Mahsul/K-1/Te-1/Diva-Thane/SND/SR-17/2023 Date - 06/10/2023
|  | Validity & area : mentioned |  | Area - 3340Sq.Mt.
Other statutory permissions (Fire NOC) |  | TMC/CFO/M/HR/114/108 Date - 18/07/2023 Building A = Stilt + 1st to 21st Floor (Height = 64.5m)
CONSTRUCTION PROGRESS
Baseline start date |  | 2024-05-10 |  | Baseline finish date | 2026-12-31
Construction details:
Bunglow = Ground + 1st to 2nd Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
|  |  |  | 0 | 1 | 0 | 2
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 0.5
Excavation |  | 0% |  | 2 | 100% | 23.33% |  | Excavation in process | 1
Plinth |  | 10% |  | 2 | 100% |  |  | Excavation Completed | 2
RCC (Including podiums) |  | 40% |  | 1 | 33.33% |  |  | Footing in Process | 0.5
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 1
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 1.5
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 2
Building A = Stilt + 1st to 21st Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 17 Floor, Internal Plaster upto 11 Floor, External Plaster upto 11 Floor Completed
|  |  |  | 0 | 1 | 0 | 21
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 21 Slab, Brickwork upto 17 Floor, Internal Plaster upto 11 Floor, External Plaster upto 11 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 5.25
Excavation |  | 0% |  | 21 | 100% | 65.56% |  | Excavation in process | 10.5
Plinth |  | 10% |  | 21 | 100% |  |  | Excavation Completed | 21
RCC (Including podiums) |  | 40% |  | 21 | 95.45% |  |  | Footing in Process | 5.25
Brickwork |  | 15% |  | 17 | 80.95% |  |  | Footing Completed | 10.5
Internal Plaster |  | 5% |  | 11 | 52.38% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 11 | 52.38% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 15.75
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 21
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | No
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block |  | Projected Parts Available |  | Yes/No | No
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M25 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE500 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A
Total |  | 0 |  | 0 |  | 0
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Bunglow |  | 1 |  | 2443.5895 |  | 3665.3842
Building A |  | 226 |  | 94187.9063 |  | 141281.8594
Total |  | 227 |  | 96631.4957 |  | 144947.2436
Grand Total |  | 227 |  | 96631.4957 |  | 144947.2436
BUILDING / BLOCK - Configuration Details
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Building No.1
Ground Floor
1 |  | Shop |  |  | 0 |  | 0
2 |  | Shop |  |  | 0 |  | 0
3 |  | Shop |  |  | 0 |  | 0
4 |  | Shop |  |  | 0 |  | 0
5 |  | Shop |  |  | 0 |  | 0
6 |  | Shop |  |  | 0 |  | 0
7 |  | Shop |  |  | 0 |  | 0
8 |  | Shop |  |  | 0 |  | 0
9 |  | Shop |  |  | 0 |  | 0
10 |  | Shop |  |  | 0 |  | 0
11 |  | Shop |  |  | 0 |  | 0
12 |  | Shop |  |  | 0 |  | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Balcony Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading: |  |  | 10.764
50%
Bunglow
Ground Floor For Entrance Lobby & Parking
1st to 2nd For Residential
1 |  | 3BHK | 2118.7858 | 324.8037 | 2443.5895 | 0 | 3665.3842
Building A
Ground Floor For Entrance Lobby, Meter Room & Parking
1st Floor For Residential, Society Office, Driver Room, Fitness Centre & Creche | [7 empty] | 1
1 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425 |  | 8291.1438
2 |  | 2BHK | 511.6129 | 32.292 | 543.9049 | 0 | 815.8574 |  | 74767.9699
3 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
4 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
5 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
6 |  | 2BHK | 511.6129 | 32.292 | 543.9049 | 0 | 815.8574
7 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
8 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
9 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
2nd to 7th, 9th to 12th, 14th to 17th & 19th to 21st Floor | [7 empty] | 17
1 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
2 |  | 2BHK | 511.6129 | 32.292 | 543.9049 | 0 | 815.8574
3 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
4 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
5 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
6 |  | 2BHK | 511.6129 | 32.292 | 543.9049 | 0 | 815.8574
7 |  | 1BHK | 321.3054 | 0 | 321.3054 | 0 | 481.9581
8 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
9 |  | 2BHK | 596.218 | 29.6548 | 625.8728 | 0 | 938.8092
10 |  | 2BHK | 596.218 | 29.6548 | 625.8728 | 0 | 938.8092
11 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
8th, 13th & 18th Floor (Part Refuge Area) | [7 empty] | 3
1 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
2 |  | 2BHK | 511.6129 | 32.292 | 543.9049 | 0 | 815.8574
3 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
4 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
5 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
6 |  | 2BHK | 511.6129 | 32.292 | 543.9049 | 0 | 815.8574
7 |  | Refuge Area
8 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
9 |  | 2BHK | 596.218 | 29.6548 | 625.8728 | 0 | 938.8092
10 |  | 2BHK | 596.218 | 29.6548 | 625.8728 | 0 | 938.8092
11 |  | 1BHK | 321.6283 | 0 | 321.6283 | 0 | 482.4425
2nd Floor
1 |  | 1BHK |  |  | 0 |  | 0
2 |  | 1BHK |  |  | 0 |  | 0
3 |  | 1BHK |  |  | 0 |  | 0
4 |  | 1BHK |  |  | 0 |  | 0
5 |  | 1BHK |  |  | 0 |  | 0
6 |  | 1BHK |  |  | 0 |  | 0
7 |  | 1BHK |  |  | 0 |  | 0
8 |  | 1BHK |  |  | 0 |  | 0
9 |  | 1BHK |  |  | 0 |  | 0
10 |  | 1BHK |  |  | 0 |  | 0
11 |  | 1BHK |  |  | 0 |  | 0
12 |  | 1BHK |  |  | 0 |  | 0
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 7900 |  |  | 7500 to 7900 | Rohan | Cost Sheet | 2025-08-21
Development Charges |  |  |  |  | 175000 |  |  |  | Rohan | Cost Sheet | 2025-08-21
Recommended of Parking ( If Available) |  |  |  |  | 400000
REMARKS ON RECOMMENDATION
1 | Construction work is in process at the time of Visit (labour found)
2 | AAC block, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Few Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Balcony Area
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Mr. Abdul 9920155998
Photographs Of Property : |  | Chandrangan Residency Phase IV
Layout Of Property :
Google Map :
Name of Engineer Visited the property |  | Gangaram parshuram Lambore |  | Authorized Signatory Name & Seal of the agency
Building A
Bunglow
Building A
Building A
Bunglow
Bunglow
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C54: RERA Start date
Note on F54: RERA completion date
Note on H86: if multiple buildings are in project and are connected internally
Note on C88: AAC Block or Brick
Note on H90: If present on slopy area

## C%
Building A = Stilt + 1st to 21st Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 21
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 5.25
Excavation | 21 | 100% | Excavation, Plinth Completed, RCC upto 5 Slab Completed | Excavation, Plinth Completed, RCC upto 5 Slab Completed |  | Excavation in process | 10.5
Plinth | 21 | 100% |  |  |  | Excavation Completed | 21
RCC (Including podiums) | 5 | 22.73% |  |  |  | Footing in Process | 5.25
Brickwork | 0 | 0% |  |  |  | Footing Completed | 10.5
Internal Plaster | 0 | 0% | 19.09% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% | , RCC upto 5 Slab |  |  | Plinth in process | 15.75
Possession | 0 | 0% | Completed |  |  | Plinth completed | 21