## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-21
Project Name |  | Aaradhya Onepark |  | Date & Time of Site Visit |  | 2025-08-22
Name of the person met at site & Contact No. |  | Miss. Payal Pariyani 9130021100 |  | Date of Report Release |  | 26/08/2025
Data from APF Request Form
Branch Name/ID |  | Mumbai-RO Thane |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | MICL Creaters LLP |  | Developer Name |  | MICL Creaters LLP
Developer Office Address |  | 1201, 12th Floor, Krushal Commercial Complex, GM Road, Krushal Tower Amar Mahal, Kurla, Mumbai - 400089
Project Address | As per ARF | Aaradhya Onepark at Ghatkopar, Kurla, Mumbai Suburban, 400077
| As per Legal Documents | Proposed Cluster Redevelopment Scheme (CDS) Under Reg.No 33(9) Of DCPR 2034 On Property Bearing F.P. Nos 353/5/A, 353/7, 353/8, 353/9, 353/17, 353/11, 353/12, 353/13, 353/15,353/16 And 353/46 (Internal Access) Of TPS-III, Village Ghatkopar- Kirol, Abutting 18.30 Mt R.B. Mehta Marg And 9.10mt Wide Tp Road, Ghatkopar East, Mumbai In N Ward.
| As per Actual at site | Aaradhya Onepark, FP No.353/5/A, 353/7, 353/8, 353/9, 353/17, 353/11, 353/12, 353/13, 353/15, 353/16 & 353/46 Redevelopement of " Meenalochani CHSL, Shree Nataraj CHSL, Belvedere CHSL, Honeycomb CHSL, Balaji Prasad CHSL, Neelkanth Chhaya CHSL, Sarvabandhu CHSL, Awadhpuri CHSL, Ashwamedh CHSL, Lalit Prakash CHSL ", near Valmiki CHSL, R B Mehta Marg, Sidhu Wadi , Ghatkopar, Ghatkopar East, Kurla, Mumbai - 400077.
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Municipal Corporation of Greater Mumbai (MCGM)
RERA Registration No. | : | P51800054477 |  | RERA Registration Validity | : | 2028-07-31
Project Launch Date | : | 2024-01-25 |  | Construction Start Date | : | 2024-01-01
Proposed Date of Completion (As per RERA) | : | 2028-07-31 |  | Developer Bank Name (As per RERA) | : | ICICI BANK LIMITED IFSC Code - ICIC0000026
Project Type (Mixed, Residential, Comm.) | : | Residential |  | Plot Area (In Sq.Mt) | : | 13128.52
FSI/FAR Permissible | : | 4 |  | Net Plot Area (In Sq.Mt) | : | 13128.52
Permissible Built up Area (In Sq.Mt) | : | 66070.07 |  | Proposed Built up Area (In Sq.Mt) | : | 66056.05
Total Number of Units Approved | : | Sale Flats = 248, Rehab Flats = 220 |  | Total Number of Units Planned | : | As per RERA Site Flats = 468 |  | 468
Latitude, Longitude | : | 19.0773338,72.907399 |  | Landmark | : | Valmiki CHSL
Location Link | : | https://maps.app.goo.gl/oaRGfGLSLga9LUT6A
Extra Amenities available | : | Fitness Centre, Swimming pool, Sports Bar, Mini Theatre and a rooftop garden, Kids' Play Areas / Sand Pits, Indoor Games, etc.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developed |  | Class of Locality | : | Upper
Type of Road | : | Bitumen |  | Width of the Road | : | 18.30m
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 0.3 KM from Oden Cinema Bus Stop
Distance from the nearest School (Km) | : | About 1KM from PG Garodia (ICSE) School |  | Distance from Hospital (Km) | : | About 1Km from Parakh Hospital
Distance from the Main Market (Km) | : | 1. Approx. 0.5KM from R Oden Mall. 2. Approx. 0.9 KM from Garodia Shopping Center. |  | Distance from Railway Station (Km) | : | 1.7 KM from Ghatkopar Railway Station 1.5KM from Vidyavihar Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North |  | South | East |  | West
East |  | Other Plot |  |  | Swami Narayan Temple
West |  | Road |  |  | R B Mehta Marg
North |  | Residential Building |  |  | PGD Manor Chandini CHS
South |  | Residential Building |  |  | Kailas Niwas
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building No. 1 Tower 1 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 16th Floor
Building No.2 Tower 2 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 18th Floor
Building No.2 Tower 3 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 18th Floor
Building No.2 Tower 4 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 18th Floor
Building No.2 Tower 5 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 18th Floor
Building No.2 Tower 6 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 18th Floor
Building No.2 Tower 7 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 18th Floor
Building No.2 Tower 8 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 18th Floor
Building No.2 Tower 9 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 18th Floor
Building No.2 Tower 10 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 18th Floor
Building No.2 Tower 11 |  | Sale | 3B + G + 1st to 18th Floor |  |  | 3B + G + 1st to 18th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | P-16663/2023)/N WARD/FP/337/1/Amend |  |  |  | Date: | 2024-10-29
Approved Plan Details | : | P-16663/2023)/N WARD/FP/337/1/Amend |  |  |  | Date: | 2024-10-29
CC Details Valid Up to: |  | P-16663/2023)/N Ward/FP/FCC/1/New |  |  |  | Date: | 2025-02-11
|  | Re-endorsement of Plinth C.C upto top of Basement level and Full C.C for Building no. 1 of Tower 1 and Building no. 2 of Tower No 7, 8, 9, 10 & 11 as per approved amended plans dated 29.10.2024. |  |  |  | Valid Upto Date | 2026-02-10
CC Details Valid Up to: |  | P-16663/2023)/N Ward/FP/FCC/1/Amend |  |  |  | Date: | 2025-03-27
|  | Full C.C. to Tower No. 2 & 3 of Building No. 2 as per the approved amended plans dated 29.10.2024. |  |  |  | Valid Upto Date | 2026-03-26
Environmental Clearance Details | : | SIA/MH/INFRA2/443014/2023 Plot Area-13128.52 Sq.M. Net Plot Area-13128.52 Sq.M. Proposed Builtup Area-128661.62 Sq.M. Tower No. 3 = 3B + G + 1st Amenity + 2nd to 18th Floor |  |  |  | Date: | 2024-02-02
Airport Authority Clearance Details |  | SNCR/WEST/B/022823/743990 |  |  |  | Date: | 21/03/2023 | [5 empty] | 7 RCC 3Brick 2 plaster
|  | Site Elevation in mtr (AMSL) = 4.78m Top Elevation in mtr (AMSL) = 57.13m |  |  |  | Valid Upto Date | 2031-03-20
Change of User/Zone Certificate Details | : | NA |  |  |  | Date: | NA
Airport Authority Clearance Details | : |  |  |  |  | Date: | [6 empty] | 7 RCC 3Brick 2 plaster
Fire NOC Details | : | P-16663/2023/N Ward/FP-CFO/1/New Building No.1 ( Tower No.1) = 3B + G + 1st to 16th Floor (Height-62.38mtrs) Building No.2 ( Tower No.2 to 11) = 3B + G + 1st to 18th Floor (Height62.17mtrs) |  |  |  | Date: | 2023-08-22
Construction Status
Building No. 1 Tower 1= 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3.75 Floor Completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 35.33% |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3.75 Floor Completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 6 | 31.58% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 5 | 27.78% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 3.75 | 20.83% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 3.75 | 20.83% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.2 Tower 2 = 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 3 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.5 Floor, External Plaster upto 1.5 Floor Completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 29.92% |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.5 Floor, External Plaster upto 1.5 Floor Completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 3 | 15.79% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 2 | 11.11% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 1.5 | 8.333% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 1.5 | 8.333% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.2 Tower 3 = 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 4 Slab, Brickwork upto 3 Floor, Internal Plaster upto 2.4 Floor, External Plaster upto 2.4 Floor Completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 31.76% |  | Excavation work Completed. Plinth work completed, RCC upto 4 Slab, Brickwork upto 3 Floor, Internal Plaster upto 2.4 Floor, External Plaster upto 2.4 Floor Completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 4 | 21.05% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 3 | 16.67% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 2.4 | 13.33% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 2.4 | 13.33% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.2 Tower 4 = 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 3 Slab, Brickwork upto 2 Floor Completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 29.5% |  | Excavation work Completed. Plinth work completed, RCC upto 3 Slab, Brickwork upto 2 Floor Completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 3 | 15.79% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 2 | 11.11% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.2 Tower 5= 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.2 Tower 6= 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. 1st & 2nd Basement Completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 22% |  | Excavation work Completed. 1st & 2nd Basement Completed |  | Excavation in process | 9
Plinth |  | 14.4 | 80% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.2 Tower 7= 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.2 Tower 8= 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 7 Floor, Internal Plaster upto 5.25 Floor, External Plaster upto 5.25 Floor Completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 38.93% |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 7 Floor, Internal Plaster upto 5.25 Floor, External Plaster upto 5.25 Floor Completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 8 | 42.11% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 7 | 38.89% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 5.25 | 29.17% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 5.25 | 29.17% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.2 Tower 9= 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 8 Floor, Internal Plaster upto 6 Floor, External Plaster upto 6 Floor Completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 40.73% |  | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 8 Floor, Internal Plaster upto 6 Floor, External Plaster upto 6 Floor Completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 9 | 47.37% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 8 | 44.44% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 6 | 33.33% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 6 | 33.33% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.2 Tower 10= 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 8 Floor, Internal Plaster upto 6 Floor, External Plaster upto 6 Floor Completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 40.73% |  | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 8 Floor, Internal Plaster upto 6 Floor, External Plaster upto 6 Floor Completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 9 | 47.37% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 8 | 44.44% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 6 | 33.33% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 6 | 33.33% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building No.2 Tower 11= 3B + G + 1st to 18th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3.75 Floor Completed
|  |  | 3 | 1 |  | 0 | 18 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 4.5
Excavation |  | 18 | 100% | 35.33% |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab, Brickwork upto 5 Floor, Internal Plaster upto 3.75 Floor, External Plaster upto 3.75 Floor Completed |  | Excavation in process | 9
Plinth |  | 18 | 100% |  |  |  |  | Excavation Completed | 18
RCC (Including podiums) |  | 6 | 31.58% |  |  |  |  | Footing in Process | 3.6
Brickwork |  | 5 | 27.78% |  |  |  |  | Footing Completed | 7.2
Internal Plaster |  | 3.75 | 20.83% |  |  |  |  | Basement 1 | 10.8
External Plaster |  | 3.75 | 20.83% |  |  |  |  | Basement 2 | 14.4
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 18
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 32.2%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 39000 to 40000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 1000000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 6740.0595
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 14341.3229
Distress Value (Rs. Per sqft) |  |  |  |  | : | 5392.0476
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Total |  | - |  | 0 |  | 0 | 0
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Tower No.1 (Reserve) |  | Sale |  | 14 |  | 64031.9144
Tower No.2 (Breeze) |  | Sale |  | 18 |  | 21983.8554
Tower No.3 (Crest) |  | Sale |  | 29 |  | 49739.0447 |  |  |  | 39
Tower No.4 (Dove) |  | Sale |  | 24 |  | 36626.2322
Tower No.5 (Evan) |  | Sale |  | 26 |  | 51586.0394
Tower No.6 (Fiona) |  | Sale |  | 14 |  | 19257.6571
Tower No.7 (Glen) |  | Sale |  | 22 |  | 26208.2948
Tower No.8 (Hazel) |  | Sale |  | 35 |  | 42419.5247
Tower No.9 (Iris) |  | Sale |  | 18 |  | 27540.1246
Tower No.10 (Jade) |  | Sale |  | 19 |  | 26197.2079
Tower No.11 (Klara) |  | Sale |  | 29 |  | 47056.7635
Total |  | - |  | 248 |  | 412646.6588
Unit Details, Nomenclature and Area Details (Flats)
Tower No.2 (Breeze) |  | Rehab |  | 34 |  | 28043.5568
Tower No.3 (Crest) |  | Rehab |  | 3 |  | 5319.8917 |  | 39000
Tower No.4 (Dove) |  | Rehab |  | 28 |  | 34288.5067
Tower No.5 (Evan) |  | Rehab |  | 6 |  | 11377.7633
Tower No.6 (Fiona) |  | Rehab |  | 20 |  | 28762.915
Tower No.7 (Glen) |  | Rehab |  | 27 |  | 29613.271
Tower No.8 (Hazel) |  | Rehab |  | 34 |  | 30922.281
Tower No.9 (Iris) |  | Rehab |  | 32 |  | 33001.3476
Tower No.10 (Jade) |  | Rehab |  | 14 |  | 20392.9362
Tower No.11 (Klara) |  | Rehab |  | 22 |  | 23989.2962
Total |  | - |  | 220 |  | 245711.7655
Grand Total |  | - |  | 468 |  | 658358.4244
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Building No.1
Tower No.1 (Sale Flats) : Reserve
1st, 2nd & 3rd Basement For Parking, Pump, Room Fire Tank, Sludge Tank, Domestic Tank & Raw Water Tank
Ground Floor For Entrance Lobby, Meter Room, Parking & Lounge Area
1st Floor For Fitness Centre, Escape Zone, Spa & Lobby
2nd to 5th, 7th, 9th, 11th & 13th Floor For Residential | [7 empty] | 8
1 |  | Sale | 4BHK | 4190.1023 | 225.7211 | 0 | 4415.8234
6th, 8th, 10th & 12th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 4
1 |  | Sale | 4BHK | 4190.1023 | 225.7211 | 0 | 4415.8234
14th Floor | [7 empty] | 1
1 |  | Sale | 2BHK | 3922.1863 | 523.8839 | 0 | 4446.0702
15th Floor | [7 empty] | 1
1 |  | Sale | 3.5BHK Duplex with 16th Floor | 5824.7233 | 771.2406 | 0 | 6595.9639
16th Floor | [7 empty] | 1
1 |  | 3.5BHK Duplex with 15th Floor
Building No.2
Tower No.2 : Breeze
Ground Floor For Society Office, Meter Room, Parking & Lobby
1st Floor For Residential, Amenity, Fitness Center | [7 empty] | 1
1 |  | Sale | 3BHK | 860.3665 | 0 | 0 | 860.3665
2nd to 6th, 8th Floor For Residential | [7 empty] | 6
1 |  | Rehab | 3BHK | 860.3665 | 0 | 0 | 860.3665
2 |  | Sale | 3BHK | 1196.8492 | 96.6607 | 0 | 1293.5099
3 |  | Rehab | 2BHK | 634.9684 | 0 | 0 | 634.9684
7th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Rehab | 3BHK | 860.3665 | 0 | 0 | 860.3665
2 |  | Rehab | 3BHK | 1196.8492 | 96.6607 | 0 | 1293.5099
3 |  | Rehab | 2BHK | 634.9684 | 0 | 0 | 634.9684
9th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Rehab | 3BHK | 860.3665 | 0 | 0 | 860.3665
2 |  | Sale | 3BHK | 1196.8492 | 96.6607 | 0 | 1293.5099
3 |  | Rehab | 2BHK | 634.9684 | 0 | 0 | 634.9684
10th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 860.3665 | 0 | 0 | 860.3665
2 |  | Sale | 3BHK | 1196.8492 | 96.6607 | 0 | 1293.5099
3 |  | Rehab | 2BHK | 634.9684 | 0 | 0 | 634.9684
11th, 13th Floor For Residential (Refuge Area at Midlanding) | [7 empty] | 2
1 |  | Rehab | 3BHK | 860.4742 | 0 | 0 | 860.4742
2 |  | Sale | 3BHK | 1196.8492 | 96.6607 | 0 | 1293.5099
3 |  | Rehab | 3BHK | 854.4463 | 0 | 0 | 854.4463
12th Floor | [7 empty] | 1
1 |  | Rehab | 3BHK | 860.4742 | 0 | 0 | 860.4742
2 |  | Sale | 3BHK | 1196.8492 | 96.6607 | 0 | 1293.5099
3 |  | Rehab | 3BHK | 854.4463 | 0 | 0 | 854.4463
14th Floor | [7 empty] | 1
1 |  | Rehab | 3BHK | 860.4742 | 0 | 0 | 860.4742
2 |  | Rehab | 3BHK | 1196.8492 | 96.6607 | 0 | 1293.5099
3 |  | Rehab | 3BHK | 854.4463 | 0 | 0 | 854.4463
15th Floor (Refuge Area at Midlanding) | [7 empty] | 1
1 |  | Sale | 3BHK | 860.4742 | 0 | 0 | 860.4742
2 |  | Sale | 3BHK | 1196.8492 | 96.6607 | 0 | 1293.5099
3 |  | Rehab | 3BHK | 854.4463 | 0 | 0 | 854.4463
16th, 18th Floor | [7 empty] | 2
1 |  | Rehab | 3BHK | 860.4742 | 0 | 0 | 860.4742
2 |  | Sale | 3BHK | 1196.8492 | 96.6607 | 0 | 1293.5099
3 |  | Rehab | 3BHK | 854.4463 | 0 | 0 | 854.4463
17th Floor (Refuge Area at Midlanding) | [7 empty] | 1
1 |  | Rehab | 3BHK | 860.4742 | 0 | 0 | 860.4742
2 |  | Sale | 3BHK | 1196.8492 | 96.6607 | 0 | 1293.5099
3 |  | Rehab | 3BHK | 854.4463 | 0 | 0 | 854.4463
Tower No.3 : Crest
Ground Floor For Society Office, Meter Room, Parking & Lobby
1st Floor For Fitness Centre & Lobby
2nd to 6th, 8th to 11th, 15th to 18th Floor For Residential | [7 empty] | 13
1 |  | Sale | 4BHK | 1808.0291 | 179.113 | 0 | 1987.142
2 |  | Sale | 3BHK | 1245.3948 | 100.2128 | 0 | 1345.6076 | 33888.0359
12th Floor | [7 empty] | 1
1 |  | Rehab | 4BHK | 1808.0291 | 179.113 | 0 | 1987.142 | 37742.6467
2 |  | Rehab | 3BHK | 1245.3948 | 100.2128 | 0 | 1345.6076
13th Floor
1 |  | Rehab | 4BHK | 1808.0291 | 179.113 | 0 | 1987.142
2 |  | Sale | 3BHK | 1245.3948 | 100.2128 | 0 | 1345.6076
7th Floor for Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Refuge Area
2 |  | Sale | 4BHK | 2255.5962 | 237.6691 | 0 | 2493.2653
14th Floor for Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Refuge Area
2 |  | Sale | 4BHK | 2336.7568 | 237.6691 | 0 | 2574.4259
1st Floor
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 |  |  |  | 0 | 0 | 0 | 0 | [7 empty] | 201,..,901 | 201 | 901
202,..,902 | [6 empty] | 0 | [7 empty] | 202,..,902 | 202 | 902
203,..,903 | [6 empty] | 0 | [7 empty] | 203,..,903 | 203 | 903
204,..,904 | [6 empty] | 0 | [7 empty] | 204,..,904 | 204 | 904
205,..,905 | [6 empty] | 0 | [7 empty] | 205,..,905 | 205 | 905
206,..,906 | [6 empty] | 0 | [7 empty] | 206,..,906 | 206 | 906
207,..,907 | [6 empty] | 0 | [7 empty] | 207,..,907 | 207 | 907
208,..,908 | [6 empty] | 0 | [7 empty] | 208,..,908 | 208 | 908
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0 | [7 empty] | 201 to 501 | 201 | 501
202 to 502 | [6 empty] | 0 | [7 empty] | 202 to 502 | 202 | 502
203 to 503 | [6 empty] | 0 | [7 empty] | 203 to 503 | 203 | 503
204 to 504 | [6 empty] | 0 | [7 empty] | 204 to 504 | 204 | 504
205 to 505 | [6 empty] | 0 | [7 empty] | 205 to 505 | 205 | 505
206 to 506 | [6 empty] | 0 | [7 empty] | 206 to 506 | 206 | 506
207 to 507 | [6 empty] | 0 | [7 empty] | 207 to 507 | 207 | 507
208 to 508 | [6 empty] | 0 | [7 empty] | 208 to 508 | 208 | 508
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0 | [7 empty] | 201 & 501 | 201 | 501
202 & 502 | [6 empty] | 0 | [7 empty] | 202 & 502 | 202 | 502
203 & 503 | [6 empty] | 0 | [7 empty] | 203 & 503 | 203 | 503
204 & 504 | [6 empty] | 0 | [7 empty] | 204 & 504 | 204 | 504
205 & 505 | [6 empty] | 0 | [7 empty] | 205 & 505 | 205 | 505
206 & 506 | [6 empty] | 0 | [7 empty] | 206 & 506 | 206 | 506
207 & 507 | [6 empty] | 0 | [7 empty] | 207 & 507 | 207 | 507
208 & 508 | [6 empty] | 0 | [7 empty] | 208 & 508 | 208 | 508
Tower No.4 : Dove
Ground Floor For Society Office, Meter Room, Drivers Room, Sub Station No.1, Fitness Centre, Parking & Lobby
1st Floor For Residential, Fitness Centre & Lobby | [7 empty] | 1
1 |  | Sale | 2BHK | 923.8741 | 43.1636 | 0 | 967.0378
2nd Floor For Residential | [7 empty] | 1
1 |  | Rehab | 3BHK | 1159.3904 | 43.1636 | 0 | 1202.5541
2 |  | Rehab | 3BHK | 1145.0743 | 56.8339 | 0 | 1201.9082
3 |  | Sale | 4BHK | 1565.1932 | 98.8135 | 0 | 1664.0068
3rd Floor | [7 empty] | 1
1 |  | Rehab | 3BHK | 1185.8699 | 43.1636 | 0 | 1229.0335
2 |  | Rehab | 3BHK | 1145.0743 | 56.8339 | 0 | 1201.9082
3 |  | Sale | 4BHK | 1565.1932 | 98.8135 | 0 | 1664.0068
4th Floor | [7 empty] | 1
1 |  | Rehab | 3BHK | 1185.8699 | 43.1636 | 0 | 1229.0335
2 |  | Rehab | 3BHK | 1169.078 | 56.8339 | 0 | 1225.912
3 |  | Sale | 4BHK | 1565.1932 | 98.8135 | 0 | 1664.0068
5th Floor | [7 empty] | 1
1 |  | Rehab | 3BHK | 1185.8699 | 43.1636 | 0 | 1229.0335
2 |  | Sale | 3BHK | 1169.078 | 56.8339 | 0 | 1225.912
3 |  | Sale | 4BHK | 1565.1932 | 98.8135 | 0 | 1664.0068
6th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 1185.8699 | 43.1636 | 0 | 1229.0335
2 |  | Rehab | 3BHK | 1169.078 | 56.8339 | 0 | 1225.912
3 |  | Sale | 4BHK | 1565.1932 | 98.8135 | 0 | 1664.0068
7th Floor (Refuge Area at Midlanding) | [7 empty] | 1
1 |  | Rehab | 3BHK | 1185.8699 | 43.1636 | 0 | 1229.0335
2 |  | Rehab | 3BHK | 1169.078 | 56.8339 | 0 | 1225.912
3 |  | Sale | 4BHK | 1565.1932 | 98.8135 | 0 | 1664.0068
8th & 10th Floor | [7 empty] | 2
1 |  | Sale | 3BHK | 1185.8699 | 43.1636 | 0 | 1229.0335
2 |  | Rehab | 3BHK | 1169.078 | 56.8339 | 0 | 1225.912
3 |  | Sale | 4BHK | 1565.1932 | 98.8135 | 0 | 1664.0068
9th & 11th Floor (Refuge Area at Midlanding) | [7 empty] | 2
1 |  | Sale | 3BHK | 1185.8699 | 43.1636 | 0 | 1229.0335
2 |  | Rehab | 3BHK | 1169.078 | 56.8339 | 0 | 1225.912
3 |  | Sale | 4BHK | 1565.1932 | 98.8135 | 0 | 1664.0068
12th, 14th, 16th & 18th Floor | [7 empty] | 4
1 |  | Rehab | 3BHK | 1185.8699 | 43.1636 | 0 | 1229.0335
2 |  | Rehab | 3BHK | 1169.078 | 56.8339 | 0 | 1225.912
3 |  | Sale | 4BHK | 1565.1932 | 98.8135 | 0 | 1664.0068
13th, 15th & 17th Floor (Refuge Area At Midlanding) | [7 empty] | 3
1 |  | Rehab | 3BHK | 1185.8699 | 43.1636 | 0 | 1229.0335
2 |  | Rehab | 3BHK | 1169.078 | 56.8339 | 0 | 1225.912
3 |  | Sale | 4BHK | 1565.1932 | 98.8135 | 0 | 1664.0068
Tower No.5 : Evan
Ground Floor For Society Office, Meter Room, BMS Room, Changing Room, Parking & Lobby
1st Floor For Fitness Centre & Lobby
2nd to 4th, 8th, 10th, 11th, 13th, 15th to 18th Floor For Residential | [7 empty] | 11
1 |  | Sale | 4BHK | 1513.526 | 105.3796 | 0 | 1618.9056
2 |  | Sale | 4BHK | 1951.5132 | 222.169 | 0 | 2173.6822
5th & 12th Floor | [7 empty] | 2
1 |  | Rehab | 4BHK | 1513.526 | 105.3796 | 0 | 1618.9056
2 |  | Rehab | 4BHK | 1951.5132 | 222.169 | 0 | 2173.6822
6th Floor | [7 empty] | 1
1 |  | Rehab | 4BHK | 1513.526 | 105.3796 | 0 | 1618.9056
2 |  | Sale | 4BHK | 1951.5132 | 222.169 | 0 | 2173.6822
9th Floor | [7 empty] | 1
1 |  | Sale | 4BHK | 1513.526 | 105.3796 | 0 | 1618.9056
2 |  | Rehab | 4BHK | 1951.5132 | 222.169 | 0 | 2173.6822
7th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Refuge Area
2 |  | Sale | 4BHK | 2626.8466 | 327.5485 | 0 | 2954.3951
14th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Refuge Area
2 |  | Sale | 5BHK | 2793.0427 | 327.5485 | 0 | 3120.5912
Tower No.6 : Fiona
Ground Floor For Society Office, Parking & Lobby
1st Floor For Fitness Centre & Lobby
2nd Floor For Residential | [7 empty] | 1
1 |  | Sale | 3BHK | 1308.7948 | 42.1949 | 0 | 1350.9896
2 |  | Sale | 3BHK | 1260.572 | 86.3273 | 0 | 1346.8993
3rd & 8th Floor | [7 empty] | 2
1 |  | Rehab | 3BHK | 1308.7948 | 42.1949 | 0 | 1350.9896
2 |  | Sale | 3BHK | 1260.572 | 86.3273 | 0 | 1346.8993
4th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 1308.7948 | 42.1949 | 0 | 1350.9896
2 |  | Rehab | 3BHK | 1260.572 | 86.3273 | 0 | 1346.8993
5th & 6th Floor | [7 empty] | 2
1 |  | Rehab | 3BHK | 1308.7948 | 42.1949 | 0 | 1350.9896
2 |  | Rehab | 3BHK | 1260.572 | 86.3273 | 0 | 1346.8993
7th & 9th Floor (Refuge Area at Midlanding) | [7 empty] | 2
1 |  | Rehab | 3BHK | 1308.7948 | 42.1949 | 0 | 1350.9896
2 |  | Rehab | 3BHK | 1260.572 | 86.3273 | 0 | 1346.8993
10th, 12th, 14th & 18th Floor | [7 empty] | 4
1 |  | Rehab | 4BHK | 1527.0887 | 42.1949 | 0 | 1569.2836
2 |  | Sale | 3BHK | 1260.572 | 107.64 | 0 | 1368.212
16th Floor | [7 empty] | 1
1 |  | Rehab | 4BHK | 1527.0887 | 42.1949 | 0 | 1569.2836
2 |  | Rehab | 3BHK | 1260.572 | 107.64 | 0 | 1368.212
11th, 13th & 15th Floor (Refuge Area at Midlanding) | [7 empty] | 3
1 |  | Rehab | 4BHK | 1527.0887 | 42.1949 | 0 | 1569.2836
2 |  | Sale | 3BHK | 1260.572 | 107.64 | 0 | 1368.212
17th Floor (Refuge Area at Midlanding) | [7 empty] | 1
1 |  | Sale | 4BHK | 1527.0887 | 42.1949 | 0 | 1569.2836
2 |  | Sale | 3BHK | 1260.572 | 107.64 | 0 | 1368.212
Tower No.7 : Glen
Ground Floor For Society Office, Parking & Lobby
1st Floor For Fitness Centre & Lobby | [7 empty] | 1
2nd to 6th Floor For Residential | [7 empty] | 5
1 |  | Rehab | 3BHK | 1146.9042 | 58.4485 | 0 | 1205.3527
2 |  | Rehab | 3BHK | 1051.3199 | 0 | 0 | 1051.3199
3 |  | Rehab | 3BHK | 1052.0734 | 0 | 0 | 1052.0734
7th Floor for Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Rehab | 3BHK | 1146.9042 | 58.4485 | 0 | 1205.3527
2 |  | Refuge Area
3 |  | Rehab | 3BHK | 1052.0734 | 0 | 0 | 1052.0734
8th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 1222.898 | 58.5562 | 0 | 1281.4542
2 |  | Rehab | 3BHK | 1051.3199 | 0 | 0 | 1051.3199
3 |  | Rehab | 3BHK | 1052.0734 | 0 | 0 | 1052.0734
9th, 11th to 13th, 15th to 16th Floor | [7 empty] | 6
1 |  | Sale | 3BHK | 1222.898 | 58.5562 | 0 | 1281.4542
2 |  | Rehab | 3BHK | 1051.3199 | 0 | 0 | 1051.3199
3 |  | Sale | 3BHK | 1052.0734 | 0 | 0 | 1052.0734
10th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 1222.898 | 58.5562 | 0 | 1281.4542
2 |  | Sale | 3BHK | 1051.3199 | 0 | 0 | 1051.3199
3 |  | Sale | 3BHK | 1052.0734 | 0 | 0 | 1052.0734
14th Floor For Residential (Part Refuge Area & Society Office) | [7 empty] | 1
1 |  | Sale | 3BHK | 1222.898 | 58.5562 | 0 | 1281.4542
2 |  | Refuge Area & Society Office
3 |  | Sale | 3BHK | 1139.8 | 92.3551 | 0 | 1232.1551
17th & 18th Floor | [7 empty] | 2
1 |  | Sale | 3BHK | 1222.898 | 58.5562 | 0 | 1281.4542
2 |  | Rehab | 3BHK | 1123.9769 | 76.4244 | 0 | 1200.4013
3 |  | Sale | 3BHK | 1139.8 | 92.3551 | 0 | 1232.1551
Tower No.8 : Hazel
Ground Floor For Society Office, Meter Room, Fire Control Room, Changing Room, Parking & Lobby
1st Floor For Fitness Centre & Lobby | [7 empty] | 1
3 |  | Sale | 3BHK | 1043.1392 | 0 | 0 | 1043.1392
2nd to 6th Floor For Residential | [7 empty] | 5
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Rehab | 2BHK | 654.3436 | 0 | 0 | 654.3436
3 |  | Rehab | 3BHK | 1012.1389 | 0 | 0 | 1012.1389
4 |  | Rehab | 3BHK | 1006.1111 | 0 | 0 | 1006.1111
7th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Rehab | 2BHK | 772.4246 | 0 | 0 | 772.4246
3 |  | Rehab | 3BHK | 1012.1389 | 0 | 0 | 1012.1389
4 |  | Rehab | 3BHK | 1006.1111 | 0 | 0 | 1006.1111
8th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Rehab | 2BHK | 772.4246 | 0 | 0 | 772.4246
3 |  | Rehab | 3BHK | 1012.1389 | 0 | 0 | 1012.1389 |  |  | 467
4 |  | Rehab | 3BHK | 1006.1111 | 0 | 0 | 1006.1111
9th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Rehab | 2BHK | 772.4246 | 0 | 0 | 772.4246
3 |  | Rehab | 3BHK | 1012.1389 | 0 | 0 | 1012.1389
4 |  | Sale | 3BHK | 1006.1111 | 44.1324 | 0 | 1050.2435
10th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Rehab | 2BHK | 772.4246 | 0 | 0 | 772.4246
3 |  | Sale | 3BHK | 1018.2744 | 43.7018 | 0 | 1061.9762
4 |  | Sale | 3BHK | 1148.1959 | 44.1324 | 0 | 1192.3283
11th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Rehab | 2BHK | 772.4246 | 0 | 0 | 772.4246
3 |  | Sale | 3BHK | 1018.2744 | 43.7018 | 0 | 1061.9762
4 |  | Rehab | 3BHK | 1148.1959 | 44.1324 | 0 | 1192.3283
12th Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Rehab | 2BHK | 772.4246 | 0 | 0 | 772.4246
3 |  | Sale | 3BHK | 1018.2744 | 43.7018 | 0 | 1061.9762
4 |  | Rehab | 3BHK | 1148.1959 | 44.1324 | 0 | 1192.3283
13th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Rehab | 2.5BHK | 859.8283 | 0 | 0 | 859.8283
3 |  | Sale | 3BHK | 1018.2744 | 43.7018 | 0 | 1061.9762
4 |  | Rehab | 3BHK | 1148.1959 | 44.1324 | 0 | 1192.3283
14th, 16th & 18th Floor | [7 empty] | 3
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Rehab | 2.5BHK | 859.8283 | 0 | 0 | 859.8283
3 |  | Sale | 3BHK | 1018.2744 | 43.7018 | 0 | 1061.9762
4 |  | Sale | 3BHK | 1148.1959 | 44.1324 | 0 | 1192.3283
15th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Rehab | 2.5BHK | 859.8283 | 0 | 0 | 859.8283
3 |  | Sale | 3BHK | 1018.2744 | 43.7018 | 0 | 1061.9762
4 |  | Sale | 3BHK | 1148.1959 | 44.1324 | 0 | 1192.3283
17th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Sale | 3BHK | 1282.3153 | 56.1881 | 0 | 1338.5034
2 |  | Sale | 2.5BHK | 859.8283 | 0 | 0 | 859.8283
3 |  | Sale | 3BHK | 1018.2744 | 43.7018 | 0 | 1061.9762
4 |  | Sale | 3BHK | 1148.1959 | 44.1324 | 0 | 1192.3283
Tower No.9 : Iris
Ground Floor For Society Office, Meter Room, Fire Control Room, Parking & Lobby
1st Floor For Residential, BMS Room & Lobby
2 |  | Sale | 3BHK | 1005.3576 | 0 | 0 | 1005.3576
2nd & 3rd Floor For Residential | [7 empty] | 2
1 |  | Rehab | 4BHK | 1513.3108 | 0 | 0 | 1513.3108
2 |  | Rehab | 3BHK | 1005.5729 | 0 | 0 | 1005.5729
3 |  | Rehab | 2.5BHK | 777.9143 | 0 | 0 | 777.9143
4th Floor | [7 empty] | 1
1 |  | Sale | 4BHK | 1597.1623 | 99.0288 | 0 | 1696.1911
2 |  | Rehab | 3BHK | 1005.5729 | 0 | 0 | 1005.5729
3 |  | Rehab | 2.5BHK | 777.9143 | 0 | 0 | 777.9143
5th Floor | [7 empty] | 1
1 |  | Sale | 4BHK | 1597.1623 | 99.0288 | 0 | 1696.1911
2 |  | Sale | 3BHK | 1005.5729 | 0 | 0 | 1005.5729
3 |  | Rehab | 2.5BHK | 777.9143 | 0 | 0 | 777.9143
6th & 8th Floor | [7 empty] | 2
1 |  | Sale | 4BHK | 1597.1623 | 99.0288 | 0 | 1696.1911
2 |  | Rehab | 3BHK | 1005.5729 | 0 | 0 | 1005.5729
3 |  | Rehab | 2.5BHK | 857.9984 | 0 | 0 | 857.9984
9th Floor | [7 empty] | 1
1 |  | Rehab | 4BHK | 1597.1623 | 99.0288 | 0 | 1696.1911
2 |  | Rehab | 3BHK | 1005.5729 | 0 | 0 | 1005.5729
3 |  | Rehab | 2.5BHK | 857.9984 | 0 | 0 | 857.9984
7th Floor for Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Rehab | 4BHK | 1645.6003 | 99.0288 | 0 | 1744.6291
2 |  | Refuge Area
3 |  | Rehab | 2.5BHK | 857.9984 | 0 | 0 | 857.9984
10th to 12th Floor | [7 empty] | 3
1 |  | Sale | 4BHK | 1583.2768 | 150.5884 | 0 | 1733.8651
2 |  | Rehab | 3BHK | 1005.5729 | 0 | 0 | 1005.5729
3 |  | Rehab | 2.5BHK | 857.9984 | 0 | 0 | 857.9984
13th Floor | [7 empty] | 1
1 |  | Sale | 4BHK | 1583.2768 | 150.5884 | 0 | 1733.8651
2 |  | Rehab | 3BHK | 1105.7857 | 112.5914 | 0 | 1218.3772
3 |  | Rehab | 2.5BHK | 857.9984 | 0 | 0 | 857.9984
15th to 17th Floor | [7 empty] | 3
1 |  | Sale | 4BHK | 1583.2768 | 150.5884 | 0 | 1733.8651
2 |  | Sale | 3BHK | 1105.7857 | 112.5914 | 0 | 1218.3772
3 |  | Rehab | 2.5BHK | 857.9984 | 0 | 0 | 857.9984
14th Floor for Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Rehab | 4BHK | 1796.6192 | 203.1167 | 0 | 1999.7359
2 |  | Refuge Area
3 |  | Rehab | 2.5BHK | 857.9984 | 0 | 0 | 857.9984
18th Floor | [7 empty] | 1
1 |  | Sale | 4BHK | 1583.2768 | 150.5884 | 0 | 1733.8651
2 |  | Sale | 3BHK | 1105.7857 | 112.5914 | 0 | 1218.3772
3 |  | Rehab | 2.5BHK | 857.9984 | 0 | 0 | 857.9984
Tower No.10 : Jade
Ground Floor For Society Office, Meter Room, Parking & Lobby
1st Floor For Fitness Centre & Lobby
2nd, 4th to 6th Floor For Residential | [7 empty] | 4
1 |  | Rehab | 3BHK | 1260.572 | 89.1259 | 0 | 1349.698
2 |  | Rehab | 3BHK | 1263.586 | 88.803 | 0 | 1352.389
3rd Floor | [7 empty] | 1
1 |  | Rehab | 3BHK | 1260.572 | 89.1259 | 0 | 1349.698
2 |  | Sale | 3BHK | 1263.586 | 88.803 | 0 | 1352.389
7th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Rehab | 3BHK | 1260.572 | 89.1259 | 0 | 1349.698
2 |  | Rehab | 3BHK | 1263.586 | 88.803 | 0 | 1352.389
9th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Rehab | 3BHK | 1260.572 | 118.404 | 0 | 1378.976
2 |  | Rehab | 3BHK | 1263.586 | 117.9734 | 0 | 1381.5594
8th, 10th, 12th, 14th, 16th Floor | [7 empty] | 5
1 |  | Sale | 3BHK | 1260.572 | 118.404 | 0 | 1378.976
2 |  | Sale | 3BHK | 1263.586 | 117.9734 | 0 | 1381.5594
11th, 13th, 15th, 17th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 4
1 |  | Sale | 3BHK | 1260.572 | 118.404 | 0 | 1378.976
2 |  | Sale | 3BHK | 1263.586 | 117.9734 | 0 | 1381.5594
18th Floor
1 |  | Rehab | 5BHK | 2531.9081 | 240.3601 | 0 | 2772.2682
Tower No.11 : Klara
Ground Floor For Society Office, Meter Room, Sub Station No.2, Parking & Lobby
1st Floor For Fitness Centre, BMS Room & Lobby
2nd Floor For Residential | [7 empty] | 1
1 |  | Sale | 3BHK | 1003.0972 | 0 | 0 | 1003.0972
2 |  | Sale | 3BHK | 1005.7882 | 0 | 0 | 1005.7882
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
3rd to 6th, 10th Floor | [7 empty] | 5
1 |  | Rehab | 3BHK | 1008.0486 | 0 | 0 | 1008.0486
2 |  | Rehab | 3BHK | 1010.7396 | 46.931 | 0 | 1057.6706
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
7th & 9th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 2
1 |  | Rehab | 3BHK | 1008.0486 | 0 | 0 | 1008.0486
2 |  | Rehab | 3BHK | 1010.7396 | 46.931 | 0 | 1057.6706
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
8th Floor | [7 empty] | 1
1 |  | Rehab | 3BHK | 1008.0486 | 0 | 0 | 1008.0486
2 |  | Sale | 3BHK | 1010.7396 | 46.931 | 0 | 1057.6706
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
11th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Rehab | 3BHK | 1128.4978 | 101.1816 | 0 | 1229.6794
2 |  | Sale | 3BHK | 1056.379 | 46.931 | 0 | 1103.31
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
12th Floor | [7 empty] | 1
1 |  | Rehab | 3BHK | 1128.4978 | 101.1816 | 0 | 1229.6794
2 |  | Rehab | 3BHK | 1056.379 | 46.931 | 0 | 1103.31
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
13th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Rehab | 3BHK | 1128.4978 | 101.1816 | 0 | 1229.6794
2 |  | Rehab | 3BHK | 1056.379 | 46.931 | 0 | 1103.31
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
14th & 16th Floor | [7 empty] | 2
1 |  | Sale | 3BHK | 1193.5123 | 119.2651 | 0 | 1312.7774
2 |  | Sale | 3BHK | 1121.1782 | 65.2298 | 0 | 1186.4081
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
18th Floor | [7 empty] | 1
1 |  | Rehab | 3BHK | 1193.5123 | 119.2651 | 0 | 1312.7774
2 |  | Sale | 3BHK | 1121.1782 | 65.2298 | 0 | 1186.4081
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
15th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Rehab | 3BHK | 1193.5123 | 119.2651 | 0 | 1312.7774
2 |  | Sale | 3BHK | 1121.1782 | 65.2298 | 0 | 1186.4081
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
17th Floor For Residential (Refuge Area At Midlanding) | [7 empty] | 1
1 |  | Sale | 3BHK | 1193.5123 | 119.2651 | 0 | 1312.7774
2 |  | Sale | 3BHK | 1121.1782 | 65.2298 | 0 | 1186.4081
3 |  | Sale | 4BHK | 1717.9344 | 224.2141 | 0 | 1942.1485
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit (labour found)
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Deck Area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We have referred EC & Fire NOC from the MCGM site on 23/08/2025.
Site & Building/Tower Photographs
Name of the Project |  |  | Aaradhya Onepark
Project Site Address |  |  | Aaradhya Onepark at Ghatkopar, Kurla, Mumbai Suburban, 400077
Site Visit Date & Time |  |  | 2025-08-22
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr.Barkat Hodekar |  | Authorized Signatory Name & Signature
Tower 11
Tower 10
Tower 9
Tower 8
Tower 7
Tower 6
Tower 5
Tower 4
Tower 3
Tower 2
Tower 1
Aradhya Park one
T- 3
Tower 3
T1
T2
T3
T6
T5
T4
T5
T7
T8
T9
T10
T11
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per maps
Note on C17: Maybe same as RERA Registration Validity or different
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G253: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0