## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 23/08/2025
CPC Name: |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  | 2025-08-22
Name of the builder group |  |  |  | T Bhimjyani Realty Pvt.Ltd.
Name of the builder company |  |  |  | T Bhimjyani Realty Pvt.Ltd.
Name of the Project |  |  |  | Infinity Towers
Provided Contact Details ( Name & Contact No.) |  |  |  | 022-66977000/66977001/66977002
Site Person - Contact Details ( Name & Contact No.) |  |  |  | Mr.Naren
Name / No of the Building |  |  |  | A Wing (Building D 119) B Wing (Building E 120) C Wing (Building F 122)
Docouments Provided |  |  |  | Approved Plans, CC
RERA No. |  |  |  | P51700021698
Project location details |  | Infinity Towers, Survey No.312/1A, 312/1B, S.No.313, H.No.1 to 3, S.No.314, H.No.1 to 9, S.No.315, H.No.1 to 3, S.No. 316 (P), S.No.317, H.No.1 to 4, S.No.318/1A, 318/1B, 318/1C, 318/1D/1, 319/1B/2, 321/3/1, 321/3/2, near Neelkanth Woods, Internal Road, Patilpada, Majiwade, Thane West, Thane, Thane - 400610.
Survey No |  | 312/1A, 312/1B, S.No.313, H.No.1 to 3, S.No.314, H.No.1 to 9, S.No.315, H.No.1 to 3, S.No. 316 (P), S.No.317, H.No.1 to 4, S.No.318/1A, 318/1B, 318/1C, 318/1D/1, 319/1B/2, 321/3/1, 321/3/2
Locality |  | Patilpada
Road |  | Internal Road |  | Locality/Village |  | Majiwade
City |  | Thane West |  | District |  | Thane
Taluka |  | Thane |  | Pin Code |  | 400610
Nearby Landmark |  | Neelkanth Woods |  | Distance from city centre: |  | 7.3KM from Thane Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per deed |  |  | At site
East | NA | Other Plot |  |  | Neelkanth Greens
West | NA | Other Plot |  |  | Neelkanth Woods Club House
North | NA | Open Plot |  |  | Open Plot
South | NA | Other Plot |  |  | Neelkanth Woods
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude, Longitude |  | 19.243736,72.969725
Location Link |  | https://goo.gl/maps/HfpPHQxVorvcuXqB8
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 96219.89
Permissible FSI |  |  |  | 1.1
Permissible TDR/Paid FSI |  |  |  | 0.10059
Total FSI availaible for the project |  |  |  | 1.2006
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 115520.33
Total number of Buildings |  |  |  | 03 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Thane Municipal Corporation (TMC)
Layout Approval No |  | S04/0122/18/TMC/TD-DP/TPS/0082(P/C)/2024/AUTODCR |  |  | Dated | 2024-02-02
Approved Floor plan No. A Wing (D 119) |  | S04/0122/18/TMC/TD-DP/TPS/0082(P/C)/2024/AUTODCR |  |  | Dated | 2024-02-02
Approved Floor plan No. B Wing (E 120) |  | S04/0122/18/TMC/TD-DP/TPS/0082(P/C)/2024/AUTODCR |  |  | Dated | 2024-02-02
Approved Floor plan No. C Wing (F 122) |  | S04/0122/18/TMC/TDD/3156/19 |  |  | Dated | 2019-08-14
Commencement-CC No Valid Up to: |  | 2003/40 (S04/0122/18)/TMC/TDD/0082 (P/C)/2024/Auto DCR |  |  | Dated | 2024-02-02
Building D 119, E 120 & F 122 = Gr Podium + 2P + St + 1st to 41st Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 115520.33
Approved no of units |  |  | Flats - 417
Approved no of Floors |  |  | A Wing (D 119) = Gr + 2P + St + 1st to 41st Floor B Wing (E 120) = Gr + 2P + St + 1st to 41st Floor C Wing (F 122) = Gr + 2P + St + 1st to 41st Floor |  |  |  |  | E - 120 means type E BLDG NO.120
Proposed no of Floors |  |  | A Wing (D 119) = Gr + 2P + St + 1st to 41st Floor
B Wing (E 120) = Gr + 2P + St + 1st to 41st Floor
C Wing (F 122) = Gr + 2P + St + 1st to 41st Floor
Expected Completion |  |  | As per RERA - 28/12/2026
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Classic European Café and Organic Juice bar The Grand Ballroom with outdoor cabanas & gazebos Exotic spa zone with fish pond World-class gym and squash court Bose entertainment and music lounge Designer Indoor Kids Play Kingdom Outdoor sports arena with cricket, tennis, golf & basketball Other Indulgences: Designer library and Billiards lounge |  |  |  |  | official site
Violations Observed if any : |  |  | NA | [6 empty] | 0
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | A Wing (D 119) = Gr + 2P + St + 1st to 41st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 29 Slab, Brickwork upto 28 Floor, Internal Plaster upto 21 Floor, External Plaster upto 19.6 Floor Completed | , RCC upto 29 Slab, Brickwork upto 28 Floor, Internal Plaster upto 21 Floor, External Plaster upto 19.6 Floor
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 41 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 29 Slab, Brickwork upto 28 Floor, Internal Plaster upto 21 Floor, External Plaster upto 19.6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.25
Excavation |  | 41 | 100% | 49.52% |  | 72.7% |  | Excavation in process | 20.5
Plinth |  | 41 | 100% |  |  |  |  | Excavation Completed | 41
RCC (Including podiums) |  | 29 | 64.44% |  |  |  |  | Footing in Process | 10.25
Brickwork | Brickwork & Internal Plaster | 28 | 68.29% |  |  |  |  | Footing Completed | 20.5
Internal Plaster | Brickwork & Internal Plaster | 21 | 51.22% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 19.6 | 47.8% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities |  | 0 | 0% |  |  |  |  | Plinth in process | 30.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 41
Construction details: |  | B Wing (E 120) = Gr + 2P + St + 1st to 41st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 28.5 Floor, External Plaster upto 28.5 Floor Completed | , RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 28.5 Floor, External Plaster upto 28.5 Floor
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 41 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 28.5 Floor, External Plaster upto 28.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.25
Excavation |  | 41 | 100% | 63.78% |  | 82.59% |  | Excavation in process | 20.5
Plinth |  | 41 | 100% |  |  |  |  | Excavation Completed | 41
RCC (Including podiums) |  | 39 | 86.67% |  |  |  |  | Footing in Process | 10.25
Brickwork | Brickwork & Internal Plaster | 38 | 92.68% |  |  |  |  | Footing Completed | 20.5
Internal Plaster | Brickwork & Internal Plaster | 28.5 | 69.51% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 28.5 | 69.51% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities |  | 0 | 0% |  |  |  |  | Plinth in process | 30.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 41
Construction details: |  | C Wing (F 122) = Gr + 2P + St + 1st to 41st Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 28.5 Floor, External Plaster upto 28.5 Floor Completed | , RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 28.5 Floor, External Plaster upto 28.5 Floor
Basement | 0 | Ground | 1 | Podium | 3 | Floors | 41 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 39 Slab, Brickwork upto 38 Floor, Internal Plaster upto 28.5 Floor, External Plaster upto 28.5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 10.25
Excavation |  | 41 | 100% | 63.78% |  | 82.59% |  | Excavation in process | 20.5
Plinth |  | 41 | 100% |  |  |  |  | Excavation Completed | 41
RCC (Including podiums) |  | 39 | 86.67% |  |  |  |  | Footing in Process | 10.25
Brickwork | Brickwork & Internal Plaster | 38 | 92.68% |  |  |  |  | Footing Completed | 20.5
Internal Plaster | Brickwork & Internal Plaster | 28.5 | 69.51% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 28.5 | 69.51% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 30.75
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 41
Recommended Rates of the Property : |  |  |  |  | On Saleable Area |  |  | 11000 to 12400 | Sanjay | 2024-08-21 | Cost sheet
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 13200 |  |  | 12400 to 13200 Sanjay on 29/01/2025 Case No. A3604 for LA= 1.45Cr (LTV 75%)
Recommended rate of the Shop Per Sq. Ft. | [8 empty] | 17500 on carpet |  | prop in 9725 | 11900
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate Per Sq. Ft. From 5th Floor |  |  |  |  | 35 |  |  | Sanjay on 28/11/2024 | 11600 |  | 9500
Development Charges |  |  |  |  | 500000 |  |  | Charges & parking |  | 2023-04-29 | gaurav
Club Charges |  |  |  |  | 250000
Legal Charges |  |  |  |  | 20000 |  |  |  | 20104286 | 10665.4037 | 22889403
Gas Connection Charges
Fire Premium Charges |  |  |  |  | 100000
Water, Electricity, Drainages, Sewerage Connection |  |  |  |  | 20000
Society Formation Charges
Security Deposit For Maintenance Charges |  |  |  |  | 120000 |  |  | 775
Advance Maintenance Charges |  |  |  |  | 120000
Corpus Charges |  |  |  |  | 120000
Recommended rate of Parking |  |  |  |  | 700000
Distressed valuation of the Property |  |  |  |  | 10560
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A |  | 160 |  | 124237.6521 |  | 192568.3607
Wing B |  | 145 |  | 106749.7311 |  | 165462.0832
Wing C |  | 112 |  | 106657.8496 |  | 165319.6669
Total |  | 417 |  | 337645.2327 |  | 523350.1107
Building details Floor Wise
Details of Flats in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Saleable area Loading : | Floor
55%
Wing A (D 119)
Stilt Floor For Parking, Society Office, Multipurpose Hall, Library & Massage Room | [8 empty] | 10.764
1st Floor For Residential
1 |  | 2BHK | 753.564 | 0 | 1168.0241 | 1st Floor For Residential
2 |  | 2BHK | 758.0149 | 0 | 1174.9231
3 |  | 2BHK | 758.2947 | 0 | 1175.3568
4 |  | 2BHK | 748.0905 | 0 | 1159.5402
2nd to 3rd, 5th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 33rd, 35th to 38th Floor For Residential | [8 empty] | 19333333.3333
1 |  | 2BHK | 753.564 | 0 | 1168.0241 | 2nd to 3rd, 5th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 33rd, 35th to 38th Floor For Residential |  | 15305930.918
2 |  | 2BHK | 758.0149 | 0 | 1174.9231 |  |  | 18514032.0578 | 18514032.0578 | 19314032.0578 | 4014032.0578
3 |  | 2BHK | 758.2947 | 0 | 1175.3568 |  |  | 1085 | 1258101.1399 | 14300 | 13370
4 |  | 2BHK | 748.0905 | 0 | 1159.5402 |  |  | 18057015.918 | 16570000 | 14284.4828 | 13199.4828 | 15350.9121
4th, 9th, 14th, 19th, 24th, 29th & 34th Floor For Residential (Part Refuge Area)
1 |  | 2BHK | 753.564 | 0 | 1168.0241 | 4th, 9th, 14th, 19th, 24th, 29th & 34th Floor For Residential (Part Refuge Area)
2 |  | 2BHK | 758.0149 | 0 | 1174.9231
3 |  | 2BHK | 758.2947 | 0 | 1175.3568
4 |  | 2BHK | 748.0905 | 0 | 1159.5402
4th, 9th, 14th, 19th, 24th, 29th, 34th & 39th Floor For (Part Refuge Area)
1 |  | 2BHK | 753.564 | 0 | 1168.0241 | 4th, 9th, 14th, 19th, 24th, 29th, 34th & 39th Floor For (Part Refuge Area)
2 |  | 2BHK | 758.0149 | 0 | 1174.9231
- |  | Refuge Area
3 |  | 2BHK | 758.2947 | 0 | 1175.3568 |  |  |  | 10.764
4 |  | 2BHK | 748.0905 | 0 | 1159.5402
40th & 41st Floor | [8 empty] | 58.076 | 8313.4548
1 |  | 3BHK | 1634.2637 | 0 | 2533.1087 | 40th & 41st Floor
2 |  | 3BHK | 1634.2637 | 0 | 2533.1087
Wing B (E 120)
Stilt Floor For Parking, Society Office, Kids Area, Library, Lounge, Fitness Centre & Society Office
1st Floor For Residential
1 |  | 2BHK | 737.2425 | 0 | 1142.7259 | 1st Floor For Residential
2 |  | 2BHK | 737.2425 | 0 | 1142.7259
3 |  | 2BHK | 737.2425 | 0 | 1142.7259
4 |  | 2BHK | 737.2425 | 0 | 1142.7259
2nd, 3rd, 5th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 33rd, 35th to 38th Floor For Residential
1 |  | 2BHK | 737.2425 | 0 | 1142.7259 | 2nd, 3rd, 5th to 8th, 10th to 13th, 15th to 18th, 20th to 23rd, 25th to 28th, 30th to 33rd, 35th to 38th Floor For Residential
2 |  | 2BHK | 737.2425 | 0 | 1142.7259 |  |  |  | 31
3 |  | 2BHK | 737.2425 | 0 | 1142.7259 |  |  | 750
4 |  | 2BHK | 737.2425 | 0 | 1142.7259 |  |  | 17191026.086 | 17891026.086
4th, 9th, 14th, 19th, 24th, 29th & 34th Floor (Part Refuge Area) | [8 empty] | 10039.4546
1 |  | 2BHK | 730.0791 | 0 | 1131.6225 | 4th, 9th, 14th, 19th, 24th, 29th & 34th Floor (Part Refuge Area)
2 |  | 2BHK | 730.0791 | 0 | 1131.6225 | 4th, 9th, 14th, 19th, 24th, 29th & 34th Floor (Part Refuge Area)
3 |  | 2BHK | 730.0791 | 0 | 1131.6225 | 4th, 9th, 14th, 19th, 24th, 29th & 34th Floor (Part Refuge Area)
4 |  | Refuge Area |  |  |  | 4th, 9th, 14th, 19th, 24th, 29th & 34th Floor (Part Refuge Area) |  |  | 20735799.4701 | 11458.4441
41st Floor For Amenity (Fitness Center) & Part Terrace
Fire Check Floor
Wing C (F 122) | [7 empty] | 41ST Also
Stilt Floor For Parking & Society Office | [8 empty] | 11511.4925
1st Floor For Residential | [8 empty] | 10498.8137
1 |  | 3BHK | 1150.3002 | 0 | 1782.9654 | 1st Floor For Residential |  |  | 10856.4925
2 |  | 2BHK | 743.5556 | 0 | 1152.5112 | 1st Floor For Residential
3 |  | 2.5BHK | 885.452 | 0 | 1372.4506 | 1st Floor For Residential
2nd to 3rd, 5th, 6th, 9th to 12th, 15th to 17th, 19th, 20th, 22nd, 24th to 27th, 29th to 32nd, 34th, 36th, 37th, 39th & 40th Floor
1 |  | 3BHK | 1216.1759 | 0 | 1885.0727 | 2nd to 3rd, 5th, 6th, 9th to 12th, 15th to 17th, 19th, 20th, 22nd, 24th to 27th, 29th to 32nd, 34th, 36th, 37th, 39th & 40th Floor
2 |  | 2BHK | 743.5556 | 0 | 1152.5112 | 2nd to 3rd, 5th, 6th, 9th to 12th, 15th to 17th, 19th, 20th, 22nd, 24th to 27th, 29th to 32nd, 34th, 36th, 37th, 39th & 40th Floor
3 |  | 2.5BHK | 885.452 | 0 | 1372.4506 | 2nd to 3rd, 5th, 6th, 9th to 12th, 15th to 17th, 19th, 20th, 22nd, 24th to 27th, 29th to 32nd, 34th, 36th, 37th, 39th & 40th Floor
7th, 14th, 21st & 35th Floor | [8 empty] | problem in 41st floor
1 |  | 3BHK | 1216.1759 | 0 | 1885.0727 | 7th, 14th, 21st & 35th Floor
2 |  | 2BHK | 743.5556 | 0 | 1152.5112 | 7th, 14th, 21st & 35th Floor
3 |  | 2.5BHK | 885.452 | 0 | 1372.4506 | 7th, 14th, 21st & 35th Floor
4th, 8th, 13th, 18th, 23rd, 33rd & 38th Floor (Part Refuge Area)
1 |  | 3BHK | 1216.1759 | 0 | 1885.0727 | 4th, 8th, 13th, 18th, 23rd, 33rd & 38th Floor (Part Refuge Area)
2 |  | 2BHK | 743.5556 | 0 | 1152.5112 | 4th, 8th, 13th, 18th, 23rd, 33rd & 38th Floor (Part Refuge Area)
3 |  | Refuge Area |  |  |  | 4th, 8th, 13th, 18th, 23rd, 33rd & 38th Floor (Part Refuge Area)
28th Floor (Part Refuge Area)
1 |  | 3BHK | 1216.1759 | 0 | 1885.0727 | 28th Floor (Part Refuge Area)
2 |  | 2BHK | 743.5556 | 0 | 1152.5112 | 28th Floor (Part Refuge Area)
3 |  | Refuge Area |  |  |  | 28th Floor (Part Refuge Area)
41st Floor For Amenity (Fitness Center) & Part Terrace
Fire Check Floor
Remarks:
* | Construction work is in process at the time of Visit. Internal photographs not allowed.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony Area + Service Slab
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated approved floor plan (sheet no. 7/28) of 1st to 38th Floor (Except of 4th, 9th, 14th, 19th, 24th, 29th & 34th Floor ) of B Wing (Building E 120).
* | We have updated approved floor plan (sheet no. 3/28) of 1st to 38th Floor (Except of 4th, 9th, 14th, 19th, 24th, 29th & 34th Floor ) of A Wing (Building D 119) (on 14/05/2024).
* | Please provide pending Sheets of revised approved floor plan dtd 02/02/2024 of A Wing (Building D 119), B Wing (Building E 120) & C Wing (Building F 122).
* | Recommended Rates / Other charges of the Property have been revised on 29/04/2023, 21/08/2024, 28/11/2024 & 29/01/2025. | [8 empty] | 2
* | We have updated approved 4th, 9th, 14th, 19th, 24th, 29th, 34th, 39th to 41st Floor Plan for A Wing (Building D 119) dtd. 2/2/2024 on 27/11/2024
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Ajay Songare |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Infinity Towers
Layout :
Google Map :
1st Floor
1st Floor
1st Floor
1st Floor
Wing A
Wing C
Wing B
Wing A
Wing C
Wing B
A
A
B
C

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted