## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com | [8 empty] | approved plan & fire NOC taken from MCGM site
Valuation Report
Date: |  |  |  | 09/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Sammaan Capital | ABFHL
Bank Name: |  |  |  | Axis Bank | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | SCL Kalyan
CPC Name: |  |  |  | Axis Thane | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | SCL Badlapur
Date Of Property Visit |  |  |  | 2025-08-28 |  |  |  | Next time take update fees |  |  | Axis Sanpada |  |  | SCL Vashi
Name of the builder group |  |  |  | Twenty Five Downtown Realty Limited | [6 empty] | Axis Badlapur |  |  | SCL Vashi
Name of the builder company |  |  |  | Twenty Five Downtown Realty Limited | [9 empty] | SCL Thane
Name of the Project |  |  |  | 25 Downtown | [9 empty] | SCL Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Preeti Lamba 7506677587 | [9 empty] | SCL Borivali
Site Person - Contact Details (Name & Contact No.) |  |  |  | Mr. Ashwin | [9 empty] | SCL Virar
Name / No of the Building |  |  |  | Wing 1 (Emerald Palm) Wing 2 (Pearl Cove) Wing 3 (Sapphire Terrace)
Name / No of the Existing Building |  |  |  | Tulsiwadi Navnirman (SRA) Co-operavtive Housing Society Ltd, Rehab Building A-1, 2, 4, 5 & 6 |  |  |  | As per rera title | [8 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | CC, Sale Plans, TOR | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | Wing 1 (Emerald Palm) = P51900076617 Wing 2 ( Pear Cove) = P51900077131 Wing 3 (Sapphire Terrace) =P51900077543 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | 25 Downtown, CTS No.383(Pt), 1/383, 389, 390, 397 & 413(Pt), Redevelopement of " Tulsiwadi Navnirman (SRA) Co-operavtive Housing Society Ltd, Rehab Building A-1, 2, 4, 5 & 6 ", near Essar House, Bhanjibhai Rathod Ln, Arya Nagar, Tardeo, Mumbai Central West, Mumbai, Mumbai - 400034. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
CTS No |  | 383(Pt), 1/383, 389, 390, 397 & 413(Pt), Redevelopement of " Tulsiwadi Navnirman (SRA) Co-operavtive Housing Society Ltd, Rehab Building A-1, 2, 4, 5 & 6 " | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Arya Nagar | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Bhanjibhai Rathod Ln |  | Locality/Village |  | Tardeo | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Mumbai Central West |  | District |  | Mumbai | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Mumbai |  | Pin Code |  | 400034 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Essar House |  | Distance from city centre: |  | 0.70KM from Mumbai Central Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Upper Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | CS No.389 / 24.40M Wide DP Road |  |  | Sant Meghmaya Road
West | NA | CS No.2/383 / 36.60M Wide DP 2034 Road |  |  | Bhanjibhai Rathod Lane
North | NA | CS No.8/838 |  |  | Residential Building
South | NA | Sector II (BMC) |  |  | Slums
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 18.978285,72.819050
Location Link |  | https://maps.app.goo.gl/x4XPMXDEouRkiaiW6
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 48987.14
Permissible FSI |  |  |  | 4
Permissible TDR/Paid FSI |  |  |  | 2.0862
Total FSI availaible for the project |  |  |  | 6.0862
Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 298146.14
Total number of Buildings |  |  |  | 03 Wings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Municipal Corporation of Greater Mumbai (MCGM) | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | P-20082/2023/(Proposed development of Cluster Development Scheme of Municipal property known as Tulsiwadi under D.C.P.Regn. 33 (9) at C.S. No. 383(pt.) And Other)/DWard/TARDEO/ IOD/1/New |  |  | Dated | 2024-04-08 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | P-20082/2023/(Proposed development of Cluster Development Scheme of Municipal property known as Tulsiwadi under D.C.P.Regn. 33 (9) at C.S. No. 383(pt.) And Other)/DWard/TARDEO/ IOD/1/New |  |  | Dated | 2024-04-08 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Muncipal Cooperation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | P-20082/2023/D Ward/TARDEO /CC/1/New |  |  | Dated | 2024-05-24 |  | NO REMARK | [8 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This C.C. is granted up to plinth level for Wing 1 (Marked as A, B,C,D,E,& F) as per the IOD plan dated 08.04.2024. |  |  | Valid Upto Date | 2026-05-23 | [10 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA) | Palghar Muncipal Council
Commencement-CC No Valid Up to: |  | P-20082/2023/D Ward/TARDEO /CC/1/Amend |  |  | Dated | 2024-06-20 |  | #VALUE! | [8 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | This C.C. is granted up to plinth for Wing 2 & 3 (Marked as A, F, G & H) as per the IOD plan dated 08.04.2024. |  |  | Valid Upto Date | 2025-06-19 | [10 empty] | Mumbai Metropolitan Region Development Authority (MMRDA) | Ambernath Municipal Council (AMC) | Navi Mumbai Airport Influence Notified Area (NAINA) | Palghar Muncipal Council
Fire Noc No Valid Up to: |  | P-20082/2023/(383(pt) And Othr)/D Ward/TARDEO/CFO /1/New |  |  | Dated | 2024-01-29 |  |  |  | 2020-05-24 | NO REMARK | [5 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
|  | Wing 1 = 1B + G + 1st to 56th Floor (Height - 198.50Mtr) Wing 2 = 1B + G + 1st to 42nd Floor ( Height - 148.10Mtr) | [14 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 21-180/2006-IA.III |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
|  | CTS No.383(PT), 1/389, 390, 397 & 417(PT) Plot Area - 74537 Sqmt BUA - 298146.48 Sqmt Sale BUA - 172851.41 Sqmt | [15 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up for: |  | JUHU/WEST/B/052616/128302 |  |  | Dated | 2016-06-22 | [11 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
|  | Site Elevation = 4.099M Permissible Top Elevation = 209.95M |  |  | Valid upto Dated | 2028-06-21 | [11 empty] | Bhiwandi Nizampur City Municipal Corporation
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) Wing 1, 2 & 3 |  |  | 68310.39
Approved no of units |  |  | Flats - 139, Shops - 03
Approved no of Floors |  |  | Wing 1 = 1B + Gr/St + 1st Floor + P2 to P7 + 8th to 56th Floor Wing 2 = 1B + Gr/St + 1st Floor + P2 to P7 + 8th to 42nd Floor Wing 3 = 1B + Gr/St + 1st Floor + P2 to P7 + 8th to 11th Floor
Proposed no of Floors |  |  | Wing 1 = 1B + Gr/St + 1st Floor + P2 to P7 + 8th to 56th Floor
Wing 2 = 1B + Gr/St + 1st Floor + P2 to P7 + 8th to 56th Floor
Wing 3 = 1B + Gr/St + 1st Floor + P2 to P7 + 8th to 56th Floor
Expected Completion |  |  | As per RERA - Wing 1 = 31/12/2033 Wing 2 & 3 = 31/12/2034
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Kids Play Area, Jogging Track, Banquet Hall, Multipurpose Court, Indoor Games Room, Fitness Centre, Swimming Pool etc. |  |  |  |  | as per builder site | https://www.25downtowns.com/?utm_source=google&utm_medium=cpc&utm_campaign=Hubtown%2025downtown%20SOBO&utm_term=25%20downtown&utm_Physical_Location=9062280&utm_Targetid=kwd-758549780125&utm_Target=&utm_Pl
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Wing 1 = 1B + Gr/St + 1st Floor + P2 to P7 + 8th to 56th Floor | [5 empty] | Excavation work in process
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 56 |  | Excavation work in process
Stage of construction: |  | Excavation work in process
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 14
Excavation |  | 28 | 50% | 0% |  | 10% |  | Excavation in process | 28
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 56
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 14
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 28
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 42
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 56
Construction details: |  | Wing 2 = 1B + Gr/St + 1st Floor + P2 to P7 + 8th to 56th Floor | [5 empty] | Excavation work in process
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 56 |  | Excavation work in process
Stage of construction: |  | Excavation work in process
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 14
Excavation |  | 28 | 50% | 0% |  | 10% |  | Excavation in process | 28
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 56
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 14
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 28
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 42
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 56
Construction details: |  | Wing 3 = 1B + Gr/St + 1st Floor + P2 to P7 + 8th to 56th Floor | [5 empty] | Excavation work in process
Basement | 1 | Ground | 1 | Podium | 0 | Floors | 56 |  | Excavation work in process
Stage of construction: |  | Excavation work in process
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 14
Excavation |  | 28 | 50% | 0% |  | 10% |  | Excavation in process | 28
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 56
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 14
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 28
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 42
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 56
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 45000 |  |  | 45000 to 60000 | self by market ref 30/08/2025 | [7 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 65000 |  |  |  | rate changes from 60k to 45000 by viraj on 05/09/2025 | [7 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 1500000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 36000 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing 1 + 2 + 3 |  | 3 |  | 63181.4906 |  | 94772.2359
Total |  | 3 |  | 63181.4906 |  | 94772.2359
Residential Area Details : | [8 empty] | 83
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area |  |  | 55
Wing 1 |  | 82 |  | 316775.4029 |  | 475163.1043
Wing 2 |  | 55 |  | 238647.3921 |  | 357971.0882
Wing 3 |  | 2 |  | 6237.0749 |  | 9355.6124
Total |  | 139 |  | 561659.87 |  | 842489.805
Grand Total |  | 142 |  | 624841.3606 |  | 937262.0409
Building details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading : |  |  |  | 10.764
50%
Sector I
Wing( 1 + 2 + 3)
Basement Floor For Pump Room, UG tank & Parking
Ground Floor For Commercial, Entrance Lobby (Double Height)
2 |  | Shop (Duplex with 1st Floor) | 18364.7639 | 0 | 18364.7639 | 0 | 27547.1459
3 |  | Shop (Duplex with 1st Floor) | 18364.7639 | 0 | 18364.7639 | 0 | 27547.1459
4 |  | Shop (Duplex with 1st Floor) | 26451.9627 | 0 | 26451.9627 | 0 | 39677.9441
Ground Floor
1 |  |  | 0 | 0 | 0 | 0 | 0
2 |  |  |  | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area + Utility Area | Deck Area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Sector I
Wing 1 ( Emerald Palm)
Basement Floor For Pump Room, UG tank & Parking
Ground Floor For Commercial, Entrance Lobby (Double Height)
1st Floor For Commercial | [7 empty] | 1
2nd to 7th Floor For Podium Parking | [7 empty] | 6
8th Podium Floor For Fitness Center, Reading Room & Yogalaya (Part Refuge Area) | [7 empty] | 1
9th Floor For Fitness Center, Reading Room & Yogalaya | [7 empty] | 1
10th, 25th & 40th Floor For Service Floor | [7 empty] | 3
11th to 15th, 17th to 22nd, 24th, 26th to 30th, 32nd to 37th, 39th, 41st to 45th, 47th to 52nd, 54th to 56th For Residential | [7 empty] | 38
1 |  | 4BHK | 2769.2898 | 206.6666 | 2975.9564 | 0 | 4463.9347 | 253.1398 | 257.2733 | 61582.4424 | 6500000 |  | 272336080.356
2 |  | 5BHK | 4264.1371 | 285.0609 | 4549.1979 | 0 | 6823.7969 |  |  | 59292.5033 | 43333.3333
16th, 23rd, 31st, 38th, 46th & 53rd Floor (Part Refuge Area) | [7 empty] | 6
1 |  | 5BHK | 4951.849 | 184.7404 | 5136.5894 | 0 | 7704.8841
2 |  | - | Refuge Area |  |  |  | -
Wing 2 ( Pearl Cove) | [9 empty] | 5154 | 273400000 | 53046.1777 | 53337.2138
Basement Floor For Parking
Ground Floor For Commercial, Entrance Lobby (Double Height)
1st Floor For Commercial | [7 empty] | (Duplex with GF)
2nd to 7th Floor For Podium Parking | [7 empty] | 6
8th Podium Floor For Fitness Center, Reading Room & Yogalaya (Refuge Area) | [7 empty] | 1
9th Floor For Fitness Center, Reading Room & Yogalaya | [7 empty] | 1
10th, 25th & 40th Floor For Service Floor | [7 empty] | 3
11th to 15th, 17th to 22nd, 24th, 26th to 30th, 32nd to 37th, 39th & 41st Floor For Residential | [7 empty] | 25 | 46000
1 |  | 5BHK | 3864.8207 | 285.0609 | 4149.8815 | 0 | 6224.8223 |  | 286341824.7144
2 |  | 5BHK | 3864.8207 | 285.0609 | 4149.8815 | 0 | 6224.8223 |  | 286341824.7144
16th, 23th, 31st & 38th Floor (Part Refuge Area) | [7 empty] | 4 | 0
1 |  | 5BHK | 6054.0665 | 499.977 | 6554.0435 | 0 | 9831.0653 |  | 452229003.018
2 |  | - | Refuge Area |  |  |  | - |  | #VALUE!
42nd Floor (Part Terrace Area) | [7 empty] | 1 | 0
1 |  | 5BHK | 4598.6402 | 338.502 | 4937.1422 | 0 | 7405.7133 |  | 340662810.3372
2 |  | - | Terrace Area |  |  |  | - |  | #VALUE!
Wing 3 (Sapphire Terrace) | [9 empty] | 5154 | 273400000 | 53046.1777 | 53337.2138
1st Floor For Commercial
2nd to 7th Floor For Podium Parking
8th Floor For Fitness Center & Yoga Room (Part Refuge Area) | [7 empty] | 1
9th Floor For Fitness Center, Reading Room & Yogalaya | [7 empty] | 1
10th Floor For Service Floor | [7 empty] | 1
11th Floor for Residential
1101 |  | 4.5BHK | 2896.6376 | 221.8999 | 3118.5375 | 0 | 4677.8062
1102 |  | 4.5BHK | 2896.6376 | 221.8999 | 3118.5375 | 0 | 4677.8062
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Construction work is in process at the time of visit. Internal visit was not allowed. | [7 empty] | Work not yet Started.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Deck Area + Utility Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have given Valuation for Sale Flats and Shops only.
* | We have taken the approved plans & fire NOC from MCGM site on 03/10/2024.
* | We have taken the Airport NOC from AAOI site on 30/08/2025.
* | Please check for Environment Clearance Certificate (TOR Received).
* | NO REMARK FOR CC
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Recommended Rates of the Property have been revised on 05/09/2025.
* | We have added Wing 3 on 09/09/2025.
* | Validity of CC is expired on 19/06/2025. Please provide revised CC for Wing 2 & 3.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Karan Misal |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | 25 Downtown
Layout :
83
55
Google Map :
Formulas:
Tardeo = [Tardeo, row above]
Next time take update fees = IF([Tardeo]>EDATE(E3,-48),"NO REMARK","CC REMARK FOR CC")
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C57: SACHIN: Floor with height
Note on C59: SACHIN: Survey Nos.
Note on C61: SACHIN: Height from AMSL
Note on D64: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F124: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H162: SACHIN: Give loading of 50% for A Category
Wing 1
Wing 2
Wing 3
Wing 4
Wing 5

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34 | As per Approved Floor Plan, In C to E wing on Ground floor Shop No. 19 & 20 are merged into single shop.
35 | There are guest houses, villas, resorts, etc. in a range of 200 to 300 meters. There are few residential buildings available in the surrounding areas. (within 500 meters) There are inadequate transportation options to get to the project and the area is not developed
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Wing 3 (Area)
| Floor No | 11th Floor
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 & 2 |  | L | W | A |  | L | W | A | L | W | A
| Foyer | 2.14 | 6.24 | 13.3536 | Deck | 8.6 | 2.14 | 18.404 |  |  | 0
| Hall | 6.11 | 6.56 | 40.0816 |  | 7.37 | 0.3 | 2.211 |  |  | 0
|  | 7.34 | 0.45 | 3.303 |  |  |  | 0 |  |  | 0
| Prayer | 3.37 | 1.95 | 6.5715 | CB |  |  | 0 |  |  | 0
| kitch | 3.61 | 4.57 | 16.4977 | CB |  |  | 0 |  |  | 0
|  | 0.3 | 3.5 | 1.05 | FB |  |  | 0 |  |  | 0
| Dining | 3.61 | 5.34 | 19.2774 |  |  |  | 0 |  |  | 0
| Bed1 | 3.66 | 6.09 | 22.2894 |  |  |  | 0 |  |  | 0
| Bed2 | 3.96 | 4.01 | 15.8796 | CB |  |  | 0 |  |  | 0
|  | 3.31 | 0.15 | 0.4965 | FB |  |  | 0 |  |  | 0
|  | 1.07 | 1.93 | 2.0651 |  |  |  | 0 |  |  | 0
| Bed3 | 3.96 | 5.54 | 21.9384 |  |  |  | 0 |  |  | 0
|  | 1.07 | 2.54 | 2.7178 | CB |  |  | 0 |  |  | 0
| Bed4 | 3.66 | 5.39 | 19.7274 | FB |  |  | 0 |  |  | 0
|  | 1.2 | 0.92 | 1.104 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| toilet1 | 1.83 | 3.2 | 5.856 | FB |  |  | 0 |  |  | 0
|  | 1.28 | 0.15 | 0.192 |  |  |  | 0 |  |  | 0
|  | 1.93 | 2.64 | 5.0952 | DB |  |  | 0 |  |  | 0
| toilet2 | 2.75 | 1.58 | 4.345 | DB |  |  | 0 |  |  | 0
| toilet3 | 2.75 | 2.19 | 6.0225 | DB |  |  | 0 |  |  | 0
|  | 2.36 | 2.75 | 6.49 | DB |  |  | 0 |  |  | 0
| toilet4 | 1.83 | 3.15 | 5.7645 | DB |  |  | 0 |  |  | 0
|  | 1.83 | 3.05 | 5.5815 | DB |  |  | 0 |  |  | 0
| Dry toilet | 1.83 | 1.83 | 3.3489 |  |  |  | 0 |  |  | 0
| Store Room | 3.07 | 2.62 | 8.0434 |  |  |  | 0 |  |  | 0
|  | 3.42 | 1 | 3.42 |  |  |  | 0 |  |  | 0
| passage1 | 10.52 | 1.22 | 12.8344 |  |  |  | 0 |  |  | 0
| passage2 | 1.2 | 1.98 | 2.376 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Utility | 7.14 | 1.37 | 9.7818 |  |  |  | 0 |  |  | 0
|  | 1.8 | 2 | 3.6 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 2896.6376 | 269.1042 |  |  | 221.8999 | 20.615 |  | 0 | 0
|  |  | 3118.5375 | 289.7192
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0