## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 11/09/2025
CPC Name: |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  | 2025-08-29
Name of the builder group |  |  |  | Edenic Enterprises Pvt Ltd
Name of the builder company |  |  |  | Edenic Enterprises Pvt Ltd
Name of the Project |  |  |  | Utopia
Provided Contact Details ( Name & Contact No.) |  |  |  | Mr. Amit Pandey 8976746712
Site Person - Contact Details ( Name & Contact No.) |  |  |  | NA |  |  |  | Mr. Shekhar 8976746712
Name / No of the Building |  |  |  | 01 Building
Docouments Provided |  |  |  | Approved Plans, CC, Cost Sheet
RERA No. |  |  |  | P52000029982
Project location details |  | Utopia, Plot No.73, 74 & 75, Sector No.17, near Alaknanda Apartment, Kalamboli Link Road, Roadpali, Kalamboli, Kalamboli West, Panvel, Raigad - 410206.
Plot No |  | 73, 74 & 75, Sector No.17
Locality |  | Roadpali
Road |  | Kalamboli Link Road |  | Locality/Village |  | Kalamboli
City |  | Kalamboli West |  | District |  | Raigad
Taluka |  | Panvel |  | Pin Code |  | 410206
Nearby Landmark |  | Alaknanda Apartment |  | Distance from city centre: |  | 3.1KM from Kalamboli Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes
Class of locality |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  | Plane
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site
East | NA | Other Plot |  |  | Open Plot
West | NA | 11.00M Wide Road |  |  | Internal Road/ Ricovero
North | NA | Other Plot |  |  | Manisha Paradise
South | NA | 9.00M Wide Road |  |  | Internal Road/ Sai Dham Building
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Latitude,Longitude |  | 19.041318,73.09488
Location Link |  | https://goo.gl/maps/hWisUHNcadfzYu8h7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 1749.13
Permissible FSI |  |  |  | 1.5
Permissible TDR/Paid FSI |  |  |  | 2.6639
Total FSI availaible for the project |  |  |  | 4.1639
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 7283.245 |  |  |  | 2620.501
Total number of Buildings |  |  |  | 01 Building
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Panvel Municipal Corporation
Layout Approval No |  | CARPC/RB/2025/APL/00210 |  |  | Dated | 2025-08-11
Approved Floor plan No. |  | CARPC/RB/2025/APL/00210 |  |  | Dated | 2025-08-11
Commencement-CC No Valid Up to: |  | CARPC/RB/2025/APL/00210 |  |  | Dated | 2025-08-11 |  | PMC/TP/Kalamboli/17/73,74,75/21-21/16009/982/2022 |  |  | 2022-04-07
Gr + 1st to 16th Floor
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA
Building wise Construction details
Approved area of building (Sq.Mt) |  |  | 7283.245
Approved no of units |  |  | Flats - 113
Approved no of Floors |  |  | Gr + 1st to 16th Floor
Proposed no of Floors |  |  | Gr + 1st to 16th Floor
Expected Completion |  |  | As per RERA - 31/12/2025
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Fitness Centre, Kids Play Area, Indoor Games, Gymnasium, Sitting Area etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Gr + 1st to 16th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 12 Floor, Painting upto 10 Floor, Finishing upto 2 Floor Completed | , Flooring upto 12 Floor, Painting upto 10 Floor, Finishing upto 2 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 16 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster Completed, Flooring upto 12 Floor, Painting upto 10 Floor, Finishing upto 2 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 4
Excavation |  | 16 | 100% | 86.25% |  | 93.75% |  | Excavation in process | 8
Plinth |  | 16 | 100% |  |  |  |  | Excavation Completed | 16
RCC (Including podiums) |  | 17 | 100% |  |  |  |  | Footing in Process | 4
Brickwork | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Footing Completed | 8
Internal Plaster | Brickwork & Internal Plaster | 16 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 16 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 12 | 75% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 10 | 62.5% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 2 | 12.5% |  |  |  |  | Plinth in process | 12
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 16
Recommended Rates of the Property : |  |  |  |  | On Saleable Area
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 7700 |  |  | 6100 to 6800 & other charges | 2022-12-26 | smith pal | cost sheet
Recommended rate of the Shop Per Sq. Ft.
Recommended rate of the Office Per Sq. Ft.
Floor Rise Rate
Development Charges |  |  |  |  | 350000 |  |  | 7300 While subsequent report on 04/02/2023
Club Charges |  |  |  |  | 150000
Society Formation Charges |  |  |  |  | 100000
Advance Maintenance Charges |  |  |  |  | 50000 |  |  |  | RATE 7700 SMITH INDEX 2 FLAT 1508 VERBAL on 11/09/2025
Recommended rate of Parking |  |  |  |  | 300000 |  |  | 650000
Distressed valuation of the Property |  |  |  |  | 6160
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Total
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Flat |  | 113 |  | 55361.2972 |  | 86068.1189 |  | 113
Building Details Floor Wise
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Gross Carpet area | Attached Loft area | Saleable area Loading : | Floor
60%
Ground Floor
1 |  |  |  | 0 | 0 | Ground Floor
2 |  |  |  | 0 | 0 | Ground Floor
3 |  |  |  | 0 | 0 | Ground Floor
4 |  |  |  | 0 | 0 | Ground Floor
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Gross Carpet area | Attached Terrace area | Builder Saleable Area | Floor
55%
Ground & 1st Floor For Parking
2nd Floor For Residential & Part Amenities
1 |  | 2 | 584.7866 | 0 | 960 | 2nd Floor For Residential & Part Amenities |  | 1.4286 | 960 | 1.6416
2 |  | 2 | 679.1115 | 0 | 1105 |  |  |  | 1105 | 1.6271
3 |  | 2 | 679.1869 | 0 | 1105 |  |  |  | 1105 | 1.6269
4 |  | 2 | 584.6682 | 0 | 960 |  |  |  | 960 | 1.642
3rd to 7th & 9th, 10th & 12th Floor For Residential | [9 empty] | #DIV/0! |  | 7300 | 650000
1 |  | 1 | 375.3192 | 0 | 585 | 3rd to 7th & 9th, 10th & 12th Floor For Residential |  | 6057.6923 | 585 | 1.5587 | 1.5587 | 4270500 | 4920500
2 |  | 1 | 409.2796 | 0 | 635 |  |  |  | 635 | 1.5515 | 1.5515 | 4635500 | 5285500
3 |  | 2 | 526.9301 | 0 | 815 |  |  | 6191.7791 | 815 | 1.5467 | 1.5467 | 5949500 | 6599500
4 |  | 2 | 615.1518 | 0 | 953.4853 |  |  | 6174.5574 | 1.4286 | 1.55 | 1.55 | 6960443.0243 | 7610443.0243
5 |  | 2 | 615.0765 | 0 | 953.3686 |  |  |  | 1.4286 | 1.55 | 1.55 | 6959590.4617 | 7609590.4617
6 |  | 2 | 526.8547 | 0 | 815 |  |  |  | 815 | 1.5469 | 1.5469 | 5949500 | 6599500
7 |  | 1 | 409.2903 | 0 | 635 |  |  |  | 635 | 1.5515 | 1.5515 | 4635500 | 5285500
8 |  | 1 | 375.2546 | 0 | 585 |  |  |  | 585 | 1.5589 | 1.5589 | 4270500 | 4920500
8th & 11th Floor For Part Refuge Area | [9 empty] | #DIV/0! |  | 0
- |  | Refuge Area |  |  |  | 8th & 11th Floor For Part Refuge Area |  |  |  | #DIV/0!
1 |  | 1 | 409.2796 | 0 | 635 |  |  |  | 635 | 1.5515
2 |  | 2 | 526.9301 | 0 | 815 |  |  | 6191.7791 | 815 | 1.5467
3 |  | 2 | 615.1518 | 0 | 953.4853 |  |  | 6174.5574 | 970 | 1.55
4 |  | 2 | 615.0765 | 0 | 953.3686 |  |  | 5.92 | 970 | 1.55 | Start from Here
5 |  | 2 | 526.8547 | 0 | 815 |  |  |  | 815 | 1.5469
6 |  | 1 | 409.2903 | 0 | 635 |  |  |  | 635 | 1.5515
7 |  | 1 | 375.2546 | 0 | 585 |  |  |  | 585 | 1.5589
13th & 15th Floor | [9 empty] | #DIV/0!
1 |  | 1 | 375.3192 | 0 | 585 | 13th & 15th Floor |  | 6057.6923 | 585 | 1.5587
2 |  | 1 | 409.2796 | 0 | 635 |  |  |  | 635 | 1.5515
3 |  | 2 | 526.9301 | 0 | 815 |  |  | 6191.7791 | 815 | 1.5467
4 |  | 2 | 615.1518 | 0 | 953.4853 |  |  | 6174.5574 | 970 | 1.55
5 |  | 2 | 615.0765 | 0 | 953.3686 |  |  | 1.55 | 970 | 1.55
6 |  | 2 | 526.8547 | 0 | 815 |  |  |  | 815 | 1.5469
7 |  | 1 | 409.2903 | 0 | 635 |  |  |  |  | 1.5515
8 |  | 1 | 375.2546 | 0 | 585 |  |  |  |  | 1.5589
14th Floor For Part Refuge Area | [9 empty] | #DIV/0!
- |  | Refuge Area |  |  |  | 14th Floor For Part Refuge Area |  | 1.5515 |  | #DIV/0!
1 |  | 1 | 409.2796 | 0 | 635 |  |  | 1.5467 |  | 1.5515
2 |  | 2 | 526.9301 | 0 | 815 |  |  | 1.55 |  | 1.5467
3 |  | 2 | 615.1518 | 0 | 953.4853 |  |  | 1.55 |  | 1.55
4 |  | 2 | 615.0765 | 0 | 953.3686 |  |  | 1.5469 |  | 1.55
5 |  | 2 | 526.8547 | 0 | 815 |  |  | 1.5515 |  | 1.5469
6 |  | 1 | 409.2903 | 0 | 635 |  |  | 1.5589 |  | 1.5515
7 |  | 1 | 375.2546 | 0 | 585 |  |  | #DIV/0! |  | 1.5589
16th Floor | [7 empty] | 1.55 |  | #DIV/0!
1 |  | 1 | 382.9939 | 0 | 593.6405 | 16th Floor |  |  | 1.55 | 1.55 |  | builder LOADING TAKEN SAME AS PER
2 |  | 1 | 409.2796 | 0 | 635 |  |  |  | 1.5515 | 1.5515
3 |  | 2 | 526.8978 | 0 | 815 |  |  |  | 1.5468 | 1.5468
4 |  | 2 | 615.1518 | 0 | 953.4853 |  |  |  | 1.55 | 1.55 |  | builder LOADING TAKEN SAME AS PER
5 |  | 2 | 615.0765 | 0 | 953.3686 |  |  |  | 1.55 | 1.55 |  | builder LOADING TAKEN SAME AS PER
6 |  | 2 | 526.8547 | 0 | 815 |  |  |  | 1.5469 | 1.5469
7 |  | 1 | 409.2903 | 0 | 635 |  |  |  | 1.5515 | 1.5515
8 |  | 1 | 382.9185 | 0 | 593.5237 |  |  |  | 1.55 | 1.55 |  | builder LOADING TAKEN SAME AS PER
Remarks:
* | Construction work is in process at the time of Visit. (labour found)
* | We considered Saleable area of Flat as per Builder area Sheet.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Enclose balcony + Balcony Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | We have updated revised approved plans & CC (on 06/12/2022 & 30/08/2025).
* | Recommended Rates of the Property have been revised on 11/09/2025
* | Please check for Fire Noc & Airport Noc.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Sunil Peravi |  | Report By : |  | Gaurav Panchal
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Utopia
Layout :
Google Map :
Formulas:
Kalamboli = [Kalamboli, row above]

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted