## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
APF Valuation Report
Name of Valuation Agency |  | V.S.JADON & CO VALUERS LLP |  |  | Date of Initiation | 2025-08-28
Branch Name/ID |  | Mahindra Rural Housing Finance - Virar |  |  | Date & Time of Site Visit | 30/08/2025 @ 02:11 PM
Name of the person met at site & Contact No |  | Mr. Rushi : 9872668081 |  |  | Date of Report Release | 30/08/2025
Project Details
Name of the project |  | Metro Satyam Queens Necklace
Address |  | Metro Satyam Queens Necklace, Survey No.36/1/A/2/2/2, 36/1/B/3, 36/4 & 36/5, near Khutari Ground Taloja, Mumbra Panvel Highway, Rohinjan, Taloja Panchnand West, Panvel, Raigad - 410208. | [7 empty] | Thane | Palghar | Mumbai | Raigad | Pune
Survey No |  | 36/1/A/2/2/2, 36/1/B/3, 36/4 & 36/5 | [7 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
Village |  | Rohinjan | [7 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Road |  | Mumbra Panvel Highway | [7 empty] | Kalyan | Vasai | Kurla | Uran | Khed
City |  | Taloja Panchnand West | [7 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Taluka |  | Panvel | [7 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
District |  | Raigad | [7 empty] | Ambernath | Dahanu |  | Pen | Shirur
Pincode |  | 410208 | [7 empty] | Murbad | Wada |  | Sudhagad | Indapur
RERA No.- |  | P52000053533 | [5 empty] | https://www.satyammetroqueensnecklace.com/ |  |  |  |  | Mahad | Daund
Landmark |  | Khutari Ground Taloja | [10 empty] | Roha | Mawal
Geo Coordinates |  | Latitude, Longitude |  |  | 19.089464,73.081996 | [7 empty] | Mangaon | Ambegaon
Geo Link |  | https://maps.app.goo.gl/gHq2f2cZ17BkGBNi9 | [10 empty] | Poladpur | Purandhar
Name of the builder / developer |  | Metrosatyam Builders LLP | [10 empty] | Mahasala | Bhor
Office address (agreement) |  | Office No. 1204 to 1206 on 12th Floor, Maithili Signet, Plot No. 39/4, Sector 30A, Near Vashi Railway Station, Vashi, Tal. Thane, Dist. Thane 400705. | [10 empty] | Shriwardhan | Mulshi
Builder Office Verified |  | No | [10 empty] | Murud | Velhe
Builder Bank Details |  | A/c No.- 57500001359731 IFSC Code- HDFC0000540
Contact No. |  | Mr. Sagar Bagade 9372668081
Location of the project Municipal Limit : |  | Panvel Municipal Corporation
Project Type (Apartments/Plot/ Combined) |  | Apartment
No of Wings / Buildings |  | Tower A, B, C & D |  |  | Other HFC's Approval / Funding | None
No. of Tenements / Units in Project |  | 624 |  |  | Exposure Limit (Proposed) | 93
Approved No. of Floor |  | Tower A, B, C & D = Gr + 1st to 5th Podium + 6th to 25th Floor
Proposed No. of Floor |  | Tower A, B, C & D = Gr + 1st to 5th Podium + 6th to 25th Floor
Verification of the schedule of the property |  | Description |  | North | South | East | West
|  | Sale deed |  | NA | NA | NA | NA
|  | Approved Plan |  | Plot No. 37 | Plot No. 35/4 | Plot No. 35/1 | Plot No. 36/1/A/2
|  | Physical on site |  | Other Plot | Other Plot | Other Plot | Other Plot
Verification of survey No. (Title document) |  | Not Provided
Plot area mentioned in the sale deed (As per 7/12) |  | 16910 |  | Plot area mentioned in the approved drg. on which FSI/FAR calculations computed (Net Plot Area) |  | 15696.97
Approach road |  | Yes, Approx 15ft
Connectivity |  | 1. 0.85km from New Prestige School & Junior College 2. 1.8km from R A Patil High School 3. 2.8km from Government ZP Hospital 4. 4.5km from Ashirvad Multi Speciality Hospital 5. 1.5km from Ketlaji Super Market 6. 2.4km from Shiv Shakti Super Market 7. 1.5km from Shree Ram Mandir 8. 1.3km from Swayambhu Vireshwar Mahadev Mandir 9. 2.1km from Taloja RAF Bus stop 10. 1.6km from Taloja Panchanand Railway Station
Approval Detail : Plan approval
Layout approval if applicable |  | Total land area of the project in Sq. Mt. |  |  |  | 15696.97
|  | Permissible FSI |  |  |  | 1.1
|  | Permissible TDR/Paid FSI |  |  |  | 1.5679
|  | Total FSI availaible for the project |  |  |  | 2.6679
|  | Total Permissible Builtup area of the project (Sq.Mt) |  |  |  | 69066.66
|  | Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 41877.422
Building plan approvals - Approval No : |  | PMP/NRV/16621/182/2024 |  |  |  | Date | 2024-01-19
Building height / No. of Floors |  | Tower A, B, C & D = Gr + 1st to 5th Podium + 6th to 25th Floor Total Height = 89.80 Mtrs
Construction/Building Permission Valid Upto: |  | PMC/TP/Rohinjan/36/1/A/2/2/2 & Other/21-24/16621/182/2024 Tower A, B, C & D = Gr + 1st to 5th Podium + 6th to 25th Floor |  |  |  | Date | 2024-01-19
NA / Land conversion |  | Name of the authority : |  | Not Provided
Reference No :
Validity & area : mentioned
Other statutory permissions (Fire NOC/ Environmental Clearance/ Airport NOC) |  | Not Provided |  |  |  | Date
CONSTRUCTION PROGRESS
Baseline start date |  | 2023-11-10 |  | Baseline finish date |  | 2029-12-31
Construction details:
Tower A = Gr + 1st to 5th Podium + 6th to 25th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed
|  |  |  | 0 | 1 | 5 | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 6.25
Excavation |  | 0% |  | 25 | 100% | 17.74% |  | Excavation in process | 12.5
Plinth |  | 10% |  | 25 | 100% |  |  | Excavation Completed | 25
RCC (Including podiums) |  | 40% |  | 6 | 19.35% |  |  | Footing in Process | 6.25
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 12.5
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 18.75
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 25
Tower B = Gr + 1st to 5th Podium + 6th to 25th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed
|  |  |  | 0 | 1 | 5 | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 6 Slab Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 6.25
Excavation |  | 0% |  | 25 | 100% | 17.74% |  | Excavation in process | 12.5
Plinth |  | 10% |  | 25 | 100% |  |  | Excavation Completed | 25
RCC (Including podiums) |  | 40% |  | 6 | 19.35% |  |  | Footing in Process | 6.25
Brickwork |  | 15% |  | 0 | 0% |  |  | Footing Completed | 12.5
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 18.75
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 25
Tower C = Gr + 1st to 5th Podium + 6th to 25th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 11 Slab, Brickwork upto 5 Floor Completed
|  |  |  | 0 | 1 | 5 | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 11 Slab, Brickwork upto 5 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 6.25
Excavation |  | 0% |  | 25 | 100% | 27.19% |  | Excavation in process | 12.5
Plinth |  | 10% |  | 25 | 100% |  |  | Excavation Completed | 25
RCC (Including podiums) |  | 40% |  | 11 | 35.48% |  |  | Footing in Process | 6.25
Brickwork |  | 15% |  | 5 | 20% |  |  | Footing Completed | 12.5
Internal Plaster |  | 5% |  | 0 | 0% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 0 | 0% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 18.75
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 25
Tower D = Gr + 1st to 5th Podium + 6th to 25th Floor |  |  |  | Basement | Ground | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8.25 Floor, External Plaster upto 7.15 Floor Completed
|  |  |  | 0 | 1 | 5 | 25
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8.25 Floor, External Plaster upto 7.15 Floor Completed | [5 empty] | All work Completed. OC Received.
Type of Work |  | Project Progress % |  | Slab/Floor | Complition % | Progress % |  | Piling Work in process | 6.25
Excavation |  | 0% |  | 25 | 100% | 41.62% |  | Excavation in process | 12.5
Plinth |  | 10% |  | 25 | 100% |  |  | Excavation Completed | 25
RCC (Including podiums) |  | 40% |  | 17 | 54.84% |  |  | Footing in Process | 6.25
Brickwork |  | 15% |  | 11 | 44% |  |  | Footing Completed | 12.5
Internal Plaster |  | 5% |  | 8.25 | 33% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing |  | 5% |  | 7.15 | 28.6% |  |  | Basement 2 | 0
Flooring & Fitting |  | 10% |  | 0 | 0% |  |  | Basement 3 | 0
Painting & Wooden |  | 5% |  | 0 | 0% |  |  | Basement 4 | 0
Building Common Amenities |  | 5% |  | 0 | 0% |  |  | Plinth in process | 18.75
Possession |  | 5% |  | 0 | 0% |  |  | Plinth completed | 25
General comment on progress |  | Speed of Construction is Average.
QUALITY/NDMC Parameters
Type of Structure |  | RCC |  | Expansion Joint Available |  | Yes/No | Yes
Mortar Type |  | Cement & Sand |  | Flood Prone Area |  | Yes/No | No
Masonry Type |  | AAC Block/ Brick |  | Projected Parts Available |  | Yes/No | Yes
Footing Type |  | Isolated Footing |  | Fire Exit Available |  | Yes/No | Yes
Soil Type |  | Alluvial Soil |  | Ground Slope >20% |  | Yes/No | No
Concrete Grade |  | M20 |  | Ground Slope Vulnerable to land slide |  | Yes/No | No
Steel Grade |  | FE415 |  | Soil liquefiable |  | Yes/No | No
Cyclone Zone-Wind speed (m/s) |  | 44 meter per sec |  | Coastal regulatory Zone |  | No
Seismic Zone |  | III |  | Environment exposure condition |  | Moderate
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Wing A
Total |  | 0 |  | 0 |  | 0
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Tower A |  | 156 |  | 77527.71 |  | 116291.565
Tower B |  | 156 |  | 80558.508 |  | 120837.7619
Tower C |  | 156 |  | 80558.508 |  | 120837.7619
Tower D |  | 156 |  | 77527.71 |  | 116291.565
Total |  | 624 |  | 316172.4359 |  | 474258.6539
Grand Total |  | 624 |  | 316172.4359 |  | 474258.6539
BUILDING / BLOCK - Configuration Details
Details of Residential in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading:
45%
Building No.1
Ground Floor
1 |  | Shop |  |  | 0 |  | 0
2 |  | Shop |  |  | 0 |  | 0
3 |  | Shop |  |  | 0 |  | 0
4 |  | Shop |  |  | 0 |  | 0
5 |  | Shop |  |  | 0 |  | 0
6 |  | Shop |  |  | 0 |  | 0
7 |  | Shop |  |  | 0 |  | 0
8 |  | Shop |  |  | 0 |  | 0
9 |  | Shop |  |  | 0 |  | 0
10 |  | Shop |  |  | 0 |  | 0
11 |  | Shop |  |  | 0 |  | 0
12 |  | Shop |  |  | 0 |  | 0
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Remark (Flat configuration /Bungalows, etc.) | Carpet area | Balcony Area | Gross Carpet area | Attached Terrace area | Saleable Area Sq.Ft. Loading: | 10.764
50%
Tower A
Ground Floor For Parking | [7 empty] | 5
1st to 5th Floor For Podium Parking
6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 25th Floor For Residential | [7 empty] | 16
1 |  | 1BHK | 431.0982 | 29.0628 | 460.161 | 0 | 690.2415
2 |  | 2BHK | 560.6214 | 29.4288 | 590.0502 | 0 | 885.0753
3 |  | 2BHK | 560.6214 | 29.4288 | 590.0502 | 0 | 885.0753
4 |  | 2BHK | 619.5328 | 29.4288 | 648.9616 | 0 | 973.4423
5 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
6 |  | 1BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
7 |  | 1BHK | 379.6463 | 0 | 379.6463 | 0 | 569.4694
8 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
7th, 12th, 17th & 22nd Floor For Residential (Part Refuge Area) | [7 empty] | 4
1 |  | Refuge Area
2 |  | 2BHK | 560.6214 | 29.4288 | 590.0502 | 0 | 885.0753
3 |  | 2BHK | 560.6214 | 29.4288 | 590.0502 | 0 | 885.0753
4 |  | 2BHK | 619.5328 | 29.4288 | 648.9616 | 0 | 973.4423
5 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
6 |  | 1BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
7 |  | 1BHK | 379.6463 | 0 | 379.6463 | 0 | 569.4694
8 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
Tower B
Ground Floor For Parking
1st to 5th Floor For Podium Parking
6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 25th Floor For Residential
1 |  | 2BHK | 619.8665 | 29.5472 | 649.4136 | 0 | 974.1205
2 |  | 2BHK | 560.6214 | 29.5472 | 590.1686 | 0 | 885.2529
3 |  | 2BHK | 560.6106 | 29.5472 | 590.1578 | 0 | 885.2367
4 |  | 2BHK | 619.5005 | 29.5472 | 649.0477 | 0 | 973.5715
5 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
6 |  | 2BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
7 |  | 2BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
8 |  | 1BHK | 430.4847 | 29.4611 | 459.9457 | 0 | 689.9186
7th, 12th, 17th & 22nd Floor For Residential (Part Refuge Area)
1 |  | 2BHK | 619.8665 | 29.5472 | 649.4136 | 0 | 974.1205
2 |  | 2BHK | 560.6214 | 29.5472 | 590.1686 | 0 | 885.2529
3 |  | 2BHK | 560.6106 | 29.5472 | 590.1578 | 0 | 885.2367
4 |  | Refuge Area
5 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
6 |  | 2BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
7 |  | 2BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
8 |  | 1BHK | 430.4847 | 29.4611 | 459.9457 |  | 689.9186
Tower C
Ground Floor For Parking
1st to 5th Floor For Podium Parking
6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 25th Floor For Residential
1 |  | 2BHK | 619.8665 | 29.5472 | 649.4136 | 0 | 974.1205
2 |  | 2BHK | 560.6214 | 29.5472 | 590.1686 | 0 | 885.2529
3 |  | 2BHK | 560.6106 | 29.5472 | 590.1578 | 0 | 885.2367
4 |  | 2BHK | 619.5005 | 29.5472 | 649.0477 | 0 | 973.5715
5 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
6 |  | 2BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
7 |  | 2BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
8 |  | 1BHK | 430.4847 | 29.4611 | 459.9457 | 0 | 689.9186
7th, 12th, 17th & 22nd Floor For Residential (Part Refuge Area)
1 |  | 2BHK | 619.8665 | 29.5472 | 649.4136 | 0 | 974.1205
2 |  | 2BHK | 560.6214 | 29.5472 | 590.1686 | 0 | 885.2529
3 |  | 2BHK | 560.6106 | 29.5472 | 590.1578 | 0 | 885.2367
4 |  | Refuge Area
5 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
6 |  | 2BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
7 |  | 2BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
8 |  | 1BHK | 430.4847 | 29.4611 | 459.9457 |  | 689.9186
Tower D
Ground Floor For Parking | [7 empty] | 5
1st to 5th Floor For Podium Parking
6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 25th Floor For Residential | [7 empty] | 16
1 |  | 1BHK | 431.0982 | 29.0628 | 460.161 | 0 | 690.2415
2 |  | 2BHK | 560.6214 | 29.4288 | 590.0502 | 0 | 885.0753
3 |  | 2BHK | 560.6214 | 29.4288 | 590.0502 | 0 | 885.0753
4 |  | 2BHK | 619.5328 | 29.4288 | 648.9616 | 0 | 973.4423
5 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
6 |  | 1BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
7 |  | 1BHK | 379.6463 | 0 | 379.6463 | 0 | 569.4694
8 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
7th, 12th, 17th & 22nd Floor For Residential (Part Refuge Area) | [7 empty] | 4
1 |  | Refuge Area
2 |  | 2BHK | 560.6214 | 29.4288 | 590.0502 | 0 | 885.0753
3 |  | 2BHK | 560.6214 | 29.4288 | 590.0502 | 0 | 885.0753
4 |  | 2BHK | 619.5328 | 29.4288 | 648.9616 | 0 | 973.4423
5 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
6 |  | 1BHK | 379.4848 | 0 | 379.4848 | 0 | 569.2272
7 |  | 1BHK | 379.6463 | 0 | 379.6463 | 0 | 569.4694
8 |  | 1BHK | 430.4847 | 29.5472 | 460.0318 | 0 | 690.0477
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) |  |  |  |  | 8000
Recommended of Parking ( If Available) |  |  |  |  | 4,00,000/-
REMARKS ON RECOMMENDATION
1 | Wing A to D = Construction work is in process at the time of Visit. Internal photos was not allowed.
2 | AAC block or Bricks, Cement bags, aggregate, Sand, etc found on site in average quantity.
3 | Labours found on site at the time of visit.
4 | We considered Carpet area as per Approved Plan.
5 | We considered Gross carpet area = Net carpet + Balcony Area.
6 | We considered Saleable area as per our calculation. Loading |  |  |  | 50%
7 | We have considered rate by verifying it from market inquire.
8 | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
9 | Car parking is subjected to authentic documentation.
10 | On Site, we meet Mr. Rushi : 9872668081.
11 | We have referred latest approved CC from RERA on 07/02/2025
12 | Please check for Environment Clearance Certificate, Fire NOC & Airport NOC.
13 | Please check for Environment Clearance Certificate, Fire NOC & Airport NOC.
Photographs Of Property : |  | Metro Satyam Queens Necklace
Layout Of Property : |  | Metro Satyam Queens Necklace
Google Map :
Name of Engineer Visited the property |  | Mr. Sunil Peravi |  | Authorized Signatory Name & Seal of the agency
Note on A9: SACHIN: As per CC
Note on C9: Take address from CC
Note on C21: Builder's office address from RERA
Note on C24: Provided during initiation
Note on C25: Authority
Note on C26: Apartments or Apartments + Shops
Note on G28: 15% of Total No of Flats
Note on E32: If Sale deed is provided
Note on F32: If Sale deed is provided
Note on G32: If Sale deed is provided
Note on H32: If Sale deed is provided
Note on C47: height should also be mentioned
Note on C54: RERA Start date
Note on H114: if multiple buildings are in project and are connected internally
Note on C116: AAC Block or Brick
Note on H118: If present on slopy area
Tower D
Tower C
Tower B
Tower A
Tower A
Tower B
Tower C
Tower D
A Wing
A Wing
A Wing
B Wing
B Wing
C Wing
D Wing
D Wing

## C%
Building No.4 = G + 3rd Floor |  | Basement | Ground | Podium | Floors
|  | 0 | 1 | 0 | 3
Type of Work | Slab/Floor | Complition % | Progress % | Stage of construction |  | Piling Work in process | 0.75
Excavation | 3 | 100% | Excavation, Plinth, RCC Slab, Brickwork Completed | Excavation, Plinth, RCC Slab, Brickwork Completed |  | Excavation in process | 1.5
Plinth | 3 | 100% |  |  |  | Excavation Completed | 3
RCC (Including podiums) | 4 | 100% |  |  |  | Footing in Process | 0.75
Brickwork | 3 | 100% |  |  |  | Footing Completed | 1.5
Internal Plaster | 0 | 0% | 65% |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | 0 | 0% |  |  |  | Basement 2 | 0
Flooring & Fitting | 0 | 0% | Excavation, Plinth, RCC Slab, Brickwork |  |  | Basement 3 | 0
Painting & Wooden | 0 | 0% | Completed |  |  | Basement 4 | 0
Building Common Amenities | 0 | 0% |  |  |  | Plinth in process | 2.25
Possession | 0 | 0% |  |  |  | Plinth completed | 3