## Sheet1
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 Email : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 30/08/2025
CPC Name: |  |  |  |  | Axis Goregaon
Date Of Property Visit |  |  |  |  | 2025-08-30
Name of the builder group |  |  |  |  | M/s.Kanakia Future Realty Private Limited
Name of the builder company |  |  |  |  | M/s.Kanakia Future Realty Private Limited
Name of the Project |  |  |  |  | Kanakia Future City E & F
Old Name of the Project |  |  |  |  | Codename Future City E & F
Name of the Project as per RERA |  |  |  |  | Codename Future City E Kanakia Silicon Valley F
Contact Details ( Name & Contact No.) |  |  |  |  | 2267267777
Site Meet Person Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Shaikh : 9967715516
Name / No of the Building |  |  |  |  | Wing E & F
Docouments Provided |  |  |  |  | Approved Layout, Approved Building Plan, CC
RERA No. |  |  |  |  | Codename Future City E = P51800034748 Kanakia Silicon Valley F = P51800047422
Project location details |  | Codename Future by Kanakia, Building no.2 - Wing C & D, CTS No. 101, S.No.38(Pt.) of village-Tirandaz, Behind Dr L.H. Hiranandani Hospital, Ramabai Ambedkar Nagar, Powai, Mumbai - 400076
CTS No. |  | CTS No. 101, S.No. 38(Pt.) |  |  | Locality |  | Tirandaz
Road |  | Hiranandani hospital Road |  |  | District |  | Mumbai
City |  | Powai |  |  | Pin Code |  | 400076
Near by Landmark |  | Sri Ayyappa Vishnu Temple |  |  | Distance from city centre: |  | About 3.4 Km from kanjur Marg Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Upper Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developed
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Open |  | Open |  | Open |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | 19.1190233,72.9199069
Location Link |  | https://goo.gl/maps/S1wteK37Br2cRYQv8
Approval details:
Approved usage of the Property: Residential (Restrictive Covenants in regard to Land Use, if any)
Total land area of the project in Sq. Mt. |  |  |  |  | 37201.04
Permissible FSI |  |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  |  | 0.56895
Total FSI availaible for the project |  |  |  |  | 1.569
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 58366.62
Total number of Buildings |  |  |  |  | 02 Building
Approval Detail : Plan approval
Layout Approval No |  | CE/1193/BPES/AS |  |  |  |  | Dated | 2022-07-29
Approved Floor plan No. |  | CE/1193/BPES/AS |  |  |  |  | Dated | 2022-07-29
Commencement Certificate No. |  | CE/1193/BPES/AS/FCC/10/Amend |  |  |  |  | Dated | 2024-03-19
Valid Up to: |  | Full C.C. is granted for Wing E up to 24th upper floor, for Wing F up to 24th upper floor including OHT & LMR as per approved amended plans dated 17.10.2023 subject to timely renewal of B.G, SWM NOC, Workmen’s compensation policy, as per height permissible as per Civil Aviation NOC dated 12.03.2018 and taking all sorts of precautions during construction and for air pollution. |  |  |  |  | Valid Upto Date : | 2025-01-31
Part O. Certificate No.: |  | CE/1193/BPES/AS/OCC/2/New Approved upto : Full occupation for wing E & F except occupation for lift no. 2 & 6 in wing ‘E’ and lift no. 6 in wing ‘F’. |  |  | Date of approval: |  | Dated | 2024-12-05
O. Certificate No.: |  | CE/1193/BPES/AS/OCC/3/New Approved upto : Part occupation i.e.occupation permission of lift No.2 & S1E (i.e. lift No .6) in Wing E and lift No.S1F(i.e.lift No.6) in Wing F of building No.2 Alongwith occupation granted for Wing E & F of building No. 2 on 05.12.2024. |  |  | Date of approval: |  | Dated | 2025-01-09
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 26457.5
Approved no of units |  |  | 334
Approved no of Floors |  |  | Wing E = B + 3P + 1st to 24th Floor
Proposed no of Floors |  |  | Wing E = B + 3P + 1st to 24th Floor
Expected Completion |  |  | As per RERA - Codename Future City E = Completed Kanakia Silicon Valley F = Completed
Proposed Amenities : |  |  | 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Quality of construction: |  |  | Good
Projected life of the structure: |  |  | 60 Years
Material laying at Site: : |  |  | Nothing
Violations Observed if any : |  |  | NA
Wheather the construction is as per approved Building plan : |  |  | Yes
Construction details: |  | Wing E & F = B + 3P + 1st to 24th Floor | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 3 | Floors | 24
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% |  | 100% |  | 100% |  | Excavation in process | 12
Plinth |  | 24 | 100% | [5 empty] | Excavation Completed | 24
RCC (Including podiums) |  | 28 | 100% | [5 empty] | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 24 | 100% | [5 empty] | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 24 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 24 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 24 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 24 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 24 | 100% | [5 empty] | Plinth in process | 18
Possession |  | 24 | 100% | [5 empty] | Plinth completed | 24
Construction details: |  | Wing F = B + 3P + 1st to 24th Floor | [6 empty] | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 20 Floor, Painting upto 20 Floor, Finishing upto 3 Floor Completed
Basement | 0 | Ground | 1 | Podium |  | 3 | Floors | 24
Stage of construction: |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring upto 20 Floor, Painting upto 20 Floor, Finishing upto 3 Floor Completed | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 6
Excavation |  | 24 | 100% |  | 88.12% |  | 94.17% |  | Excavation in process | 12
Plinth |  | 24 | 100% | [5 empty] | Excavation Completed | 24
RCC (Including podiums) |  | 28 | 100% | [5 empty] | Footing in Process | 6
Brickwork | Brickwork & Internal Plaster | 24 | 100% | [5 empty] | Footing Completed | 12
Internal Plaster | Brickwork & Internal Plaster | 24 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 24 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 20 | 83.33% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 20 | 83.33% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 12.5% | [5 empty] | Plinth in process | 18
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 24
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 22000 |  |  | 21100 to 22000 | Smith | verbal case E1106 | value 3.98 | 2023-11-29
Electricity & Water Connection | [5 empty] | 50,000/-
Legal Charges incl. Scanning & Documentation | [5 empty] | 50,000/-
Society formation charges | [5 empty] | 5000/-
Recommended rate of Parking | [5 empty] | 1200000/-
Distressed valuation of the Property | [5 empty] | 17600
Residential Area Details :
Building & Wing |  | No. of Flats | Total Carpet Area |  |  | Total Saleable Area
C |  | 71 | #REF! |  |  | #REF!
D |  | 0 | #REF! |  |  | #REF!
Total |  | 71 | #REF! |  |  | #REF!
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  |  | Total Saleable Area
Wing E |  | 167 |  | 161523.5636 |  |  | 258437.7017
Wing F |  | 167 |  | 161535.0165 |  |  | 258456.0264
Total |  | 334 |  | 323058.58 |  |  | 516893.7281
Building details Floor Wise
Details of Flats in Building
Flat No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area (60%) | PLC Y/N | Floor
Building no.2
Wing E
Basement, 1st to 3rd Podium Floor for Parking
Ground Floor for Residential
1 |  | 3BHK | 1048.588 |  | 0 | 1677.7408 | N | Ground Floor |  | 88.9391 |  | 10.764
2 |  | 3BHK | 1048.588 |  | 0 | 1677.7408 | N
3 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N |  |  | 55.5942 | 3.96
4 |  | Entrance Lobby | [7 empty] | 59.5542
5
6
7 |  | 3 BHK | 1248.4087 |  | 0 | 1997.454 | N |  |  | 108.4723 | 5.032
1st Floor | [10 empty] | 113.5043
1 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N | 1st Floor |  |  | Wing F is also drafted.
2 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N
3 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
4 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
5 |  | Entrance Lobby
6
7 |  | 3BHK | 1239.7975 |  | 0 | 1983.676 | N
2nd, 4th to 8th, 12th to 15th, 19th to 22nd Floor
1 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N | 2nd, 4th to 8th, 12th to 15th, 19th to 22nd Floor
2 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N
3 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
4 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
5 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
6 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
7 |  | 3BHK | 1239.7975 |  | 0 | 1983.676 | N
3rd, 10th, 17th Floor (Part Refuge Area)
1 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N | 3rd, 10th, 17th Floor (Part Refuge Area)
2 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N
3 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
4 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
5 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
6 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
7 |  | Refuge Area
9th, 11th, 16th, 18th, 23rd Floor
1 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N | 9th, 11th, 16th, 18th, 23rd Floor
2 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N
3 |  | 2BHK | 715.5907 |  | 0 | 1144.9452 | N
4 |  | 2BHK | 664.7846 |  | 0 | 1063.6554 | N
5 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
6 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N |  | 39822000
7 |  | 3BHK | 1239.7975 |  | 182.8319 | 1983.676 | N
24th Floor (Part Refuge Area)
1 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N | 24th Floor (Part Refuge Area)
2 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N
3 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
4 |  | 2BHK | 664.7846 |  | 0 | 1063.6554 | N
5 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
6 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
7 |  | 3BHK | 946.048 |  | 0 | 1513.6767 | N
Wing F
Basement, 1st to 3rd Podium Floor for Parking
Ground Floor for Residential
1 |  | 3BHK | 1075.6271 |  | 0 | 1721.0034 | N | Ground Floor |  | 93.1153 |  | 10.764
2 |  | 3BHK | 1075.6271 |  | 0 | 1721.0034 | N
3 |  | 2BHK | 629.3711 |  | 0 | 1006.9937 | N
4 |  | Entrance Lobby
5
6
7 |  | 3 BHK | 1248.4087 |  | 0 | 1997.454 | N
1st Floor
1 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N | 1st Floor
2 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N
3 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
4 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
5 |  | Entrance Lobby
6
7 |  | 3BHK | 1239.7975 |  | 0 | 1983.676 | N
2nd, 4th to 8th, 12th to 15th, 19th to 22nd Floor
1 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N | 2nd, 4th to 8th, 12th to 15th, 19th to 22nd Floor
2 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N
3 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
4 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
5 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
6 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
7 |  | 3BHK | 1239.7975 |  | 0 | 1983.676 | N
3rd, 10th, 17th Floor (Part Refuge Area)
1 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N | 3rd, 10th, 17th Floor (Part Refuge Area)
2 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N
3 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
4 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
5 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
6 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
7 |  | Refuge Area
9th, 11th, 16th, 18th, 23rd Floor
1 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N | 9th, 11th, 16th, 18th, 23rd Floor
2 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N
3 |  | 2BHK | 715.5907 |  | 0 | 1144.9452 | N
4 |  | 2BHK | 664.7846 |  | 0 | 1063.6554 | N
5 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
6 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
7 |  | 3BHK | 1239.7975 |  | 182.8319 | 1983.676 | N
24th Floor (Part Refuge Area)
1 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N | 24th Floor (Part Refuge Area)
2 |  | 3BHK | 1050.4179 |  | 0 | 1680.6686 | N
3 |  | 2BHK | 671.9965 |  | 0 | 1075.1944 | N
4 |  | 2BHK | 664.7846 |  | 0 | 1063.6554 | N
5 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
6 |  | 3BHK | 1063.3347 |  | 0 | 1701.3355 | N
7 |  | 3BHK | 946.048 |  | 0 | 1513.6767 | N
Remarks: 1. All work Completed. OC received. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We have considered rate by verifying it from market inquire. 5. Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes) 6. We have considered Other charges from cost sheet. 7. Car parking is subjected to authentic documentation. 8. We update revised Approved plans (on 29/10/2021) 9. We have updated revised CC from MCGM Site (on 30/06/2022). 10. We have Updated CC & Approved Floor plan of Wing E & F (on20/12/2022) 11. We have updated approved CC for Wing E & F from MCGM site (on 12/07/2024). 12. Name of the project Kanakia Future City F name has been changed to Kanakia Silicon Valley F as per the rera. 13. We have updated OC from MCGM site (On 24/01/2025).
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) The saleable area is as per Our Calculation.
5) Legal title of the property is not verified by us.
6) Gross carpet area = Net Carpet area + Fungible area.
7) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Kanakia Future City E & F
Google Map :
Formulas:
North = [North, row above]
E
F

## Note
17/03/2020. | Asmita | OLD APF
In previous report : We considered rate as per Builder cost sheet.
31/08/2020.
2020-09-01
Vishal demand for 18000
Basement Slab + 2nd Podium Floor's Slab Completed. 3rd Podium Floor's Slab work is in process…
05/02/2021. | Pratiksha

## C %
Construction details: Building No. = C | [6 empty] | Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Plaster upto 1.5 Floor completed
Ground | 1 |  | Podium | 3 | Floors | 30 | All work Completed. Wait For OC.
Stage of construction: | Plinth work completed, RCC upto 4 Slab completed, Brickwork upto 3 Floor completed, Plaster upto 1.5 Floor completed | [5 empty] | All work Completed. Provide OC.
Type of Work | Completed Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Plinth | 10 | 100% | 16.71% |  | 35.53%
RCC Slab | 4 | 11.76% |  |  |  |  | Excavation in process | 1% | 2%
Brick | 3 | 9.091% |  |  |  |  | Excavation Completed | 2% | 4%
Plaster | 1.5 | 4.545% |  |  |  |  | Footing in Process | 4% | 8%
Flooring | 0 | 0% |  |  |  |  | Footing Completed | 5% | 15%
Painting & Wooden Work | 0 | 0% |  |  |  |  | Plinth in process | 7% | 20%
Finishing | 0 | 0% |  |  |  |  | Plinth completed | 10% | 30%
|  |  | 16.71% |  | 35.53%

## D %
Construction details: Building No. = D | [6 empty] | Plinth work completed, RCC upto 1 Slab completed
Ground | 1 |  | Podium | 3 | Floors | 30 | All work Completed. Wait For OC.
Stage of construction: | Plinth work completed, RCC upto 1 Slab completed | [5 empty] | All work Completed. Provide OC.
Type of Work | Completed Slab/Floor | Complition % | Progress % |  | Disbursement % |  | All work Completed. OC Received.
Plinth | 10 | 100% | 11.18% |  | 30.88%
RCC Slab | 1 | 2.941% |  |  |  |  | Excavation in process | 1% | 2%
Brick | 0 | 0% |  |  |  |  | Excavation Completed | 2% | 4%
Plaster | 0 | 0% |  |  |  |  | Footing in Process | 4% | 8%
Flooring | 0 | 0% |  |  |  |  | Footing Completed | 5% | 15%
Painting & Wooden Work | 0 | 0% |  |  |  |  | Plinth in process | 7% | 20%
Finishing | 0 | 0% |  |  |  |  | Plinth completed | 10% | 30%
|  |  | 11.18% |  | 30.88%

## Wing A
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.35 | 5.5 | 18.425 | CB |  |  | 0 |  |  | 0
|  | 0.88 | 2.53 | 2.2264 | FB |  |  | 0 |  |  | 0
|  | 2.55 | 1.2 | 3.06 |  |  |  | 0 |  |  | 0
| kitch | 3.05 | 2.35 | 7.1675 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 | 3.15 | 3.8 | 11.97 | CB |  |  | 0 |  |  | 0
|  | 3.26 | 3.8 | 12.388 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 | 2.25 | 1.38 | 3.105 | DB |  |  | 0 |  |  | 0
| toilet2 | 1.58 | 2.53 | 3.9974 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 | 1.5 | 1 | 1.5 |  |  |  | 0 |  |  | 0
| passage2 | 1.9 | 1 | 1.9 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| bal | 0.9 | 2.35 | 2.115 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 730.3837 | 67.8543 |  |  | 0 | 0 |  | 0 | 0

## Wing B
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0

## Wing C
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall | 3.13 | 4.96 | 15.5248 | CB |  |  | 0 |  |  | 0
|  | 1.2 | 2.45 | 2.94 | FB |  |  | 0 |  |  | 0
|  | 2.9 | 2.19 | 6.351 |  |  |  | 0 |  |  | 0
| kitch | 2.38 | 0.9 | 2.142 | CB |  |  | 0 |  |  | 0
|  | 0.9 | 0.9 | 0.81 | FB |  |  | 0 |  |  | 0
|  | 2.3 | 1.38 | 3.174 |  |  |  | 0 |  |  | 0
|  | 3.05 | 4.4 | 13.42 |  |  |  | 0 |  |  | 0
| Bed1 | 3.05 | 3.35 | 10.2175 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 587.4916 | 54.5793 |  |  | 0 | 0 |  | 0 | 0