## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-26
Project Name |  | Maplewoods Phase I & II |  | Date & Time of Site Visit |  | 02/09/2025 @01:32PM |  | Galaxy and Pivaso is Developer Groups (as per site person)
Name of the person met at site & Contact No. |  | Rajnikant Gupta- 8104096387 |  | Date of Report Release |  | 02/09/2025 |  |  | 2025-06-04 | 2025-09-02
Data from APF Request Form | [8 empty] | 90
Branch Name/ID |  | Godrej One, Vikhroli East, Mumbai |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | BKS Galaxy Realtors LLP |  | Developer Name |  | BKS Galaxy Realtors LLP
Developer Office Address |  | Bhumiraj Costarica, Office No. 1201, opp. The Affairs, Sector 18, Sanpada, Navi Mumbai, Maharashtra 400705
Project Address | As per ARF | Maplewoods Phase I & II, Survey No. 51/2, 56 & 57/2, Thane - Belapur Rd, behind Krishna Business Park, Ramu Limaje Nagar, Dighe, Navi Mumbai, Maharashtra 400708
| As per Legal Documents | Maplewoods Phase I & II, Proposed Residential Complex On plot Bearing Gut No. 51(2), 56 & 57(2), Digha Navi Mumbai.
| As per Actual at site | Maplewoods Phase I & II, Gut No.51(2) 56 and 57(2), near Krishna Business Park Airoli, Thane Belapur Road, Digha, Digha, Thane, Thane - 400708.
Documents Provided by GHF |  | Approved Layout & Floor Plans, CC, RERA certificate, EC & Fire NOC
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Navi Mumbai Municipal Corporation
RERA Registration No. | : | Phase I - P51700050973 Phase II - P51700051868 |  | RERA Registration Validity | : | Phase 1 = 31/12/2028 Phase 2 = 31/12/2029
Project Launch Date | : | Phase 1 = 16/05/2023 Phase 2 = 07/07/2023 |  | Construction Start Date | : | Phase 1 = May-23 Phase 2 = July-23
Proposed Date of Completion (As per RERA) | : | Phase 1 = 31/12/2028 Phase 2 = 31/12/2029 |  | Developer Bank Name (As per RERA) | : | Indian Overseas Bank IFSC Code : IOBA0002110
Project Type (Mixed, Residential, Comm.) | : | Residential |  | Plot Area (In Sq.Mt) | : | 20000
FSI/FAR Permissible | : | 1.5 |  | Net Plot Area (In Sq.Mt) | : | 19000
Permissible Built up Area (In Sq.Mt) | : | 108773.11 |  | Proposed Built up Area (In Sq.Mt) | : | 108748.18 |  |  | C | D | E | F
Total Number of Units Approved | : | Flats = 777 |  | Total Number of Units Planned | : | As per RERA Site Flats = 835 |  | 835 | 191 | 191 | 191 | 262
Latitude, Longitude | : | 19.182298,72.996989 |  | Landmark | : | Krishna Business Park Airoli
Location Link | : | https://maps.app.goo.gl/bCMkPV269WA59V2JA
Extra Amenities available | : | Gymmnasium, Yoga Room, Kids Play Area, Terrace Garden, Banquet Hall, Sit Out Area, EV charging Point
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 30M
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 0.29KM from Mukund Company Bus Stop
Distance from the nearest School (Km) | : | About 0.50KM from Swami Vivekanand English Medium School |  | Distance from Hospital (Km) | : | About 1.70KM form Chhatrapati Shivaji Maharaj Hospital, Kalwa
Distance from the Main Market (Km) | : | 1. Approx. 0.40KM from CITI mart. 2. Approx. 5.00KM from Airoli Dmart & Local Market. |  | Distance from Railway Station (Km) | : | 0.25KM from Digha Railway Station 2.90KM from Airoli Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North |  | South | East |  | West
East |  | Other Plot |  |  | Slums
West |  | 9.00 M.Wide Road |  |  | Krishna Business Park Airoli
North |  | Other Plot |  |  | Open Plot
South |  | 30M. Wide Road |  |  | Central Road
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Phase I D Wing |  | Sale | Upper Stilt + 1st to 38th Floor |  |  | Upper Stilt + 1st to 38th Floor
Phase I F Wing |  | Sale | Lower Stilt + Upper Stilt + 1st to 38th Floor |  |  | Lower Stilt + Upper Stilt + 1st to 27th Floor
Phase II C wing |  | Sale | Upper Stilt + 1st to 38th Floor |  |  | Upper Stilt + 1st to 38th Floor
Phase II E Wing |  | Sale | Lower Stilt + Upper Stilt + 1st to 38th Floor |  |  | Lower Stilt + Upper Stilt + 1st to 38th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | NRV/A-17163 |  |  |  | Date: | 2023-04-11
Approved Plan Details | : | NRV/A-17163 |  |  |  | Date: | 2023-04-11
CC Details Valid Up to: |  | NMMC/TPO/BP/17163/2023 |  |  |  | Date: | 2023-04-11
C & D Wing = Upper Stilt + 1st to 38th Floor E Wing = Lower Stilt + Upper Stilt + 1st to 38th Floor F Wing = Lower Stilt + Upper Stilt + 1st to 27th Floor
Environmental Clearance Details Valid Up to: |  | SIA/MH/INFRA2/406628/2022 |  |  |  | Date: | 2023-04-11
Plot Area = 20000 Sqm Built Up Area = 164757.84 Sqm Building C, D & E =Lower stilt + Upper stilt + 38 Floors Building F = Lower stilt + Upper stilt + 33 Floors
Fire NOC Valid Up to: |  | FIRE/HO/VASHI/1816/2023 |  |  |  | Date: | 2023-03-31
Building C, D, E & F = Lower stilt + upper stilt + 1st to 5th Podium + 6th to 38th Floor (Height = 129.65 Mtrs)
Airport Authority Clearance Details | : |  |  |  |  | Date: | [6 empty] | 7 RCC 3Brick 2 plaster
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Phase I D Wing= Upper Stilt + 1st to 38th Floor . |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8.8 Floor, External Plaster upto 8.8 Floor Completed
|  |  | 0 | 1 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 38 | 100% | 38.5% |  | Excavation work Completed. Plinth work completed, RCC upto 17 Slab, Brickwork upto 11 Floor, Internal Plaster upto 8.8 Floor, External Plaster upto 8.8 Floor Completed |  | Excavation in process | 19
Plinth |  | 38 | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 17 | 43.59% |  |  |  |  | Footing in Process | 7.6
Brickwork |  | 11 | 28.95% |  |  |  |  | Footing Completed | 15.2
Internal Plaster |  | 8.8 | 23.16% |  |  |  |  | Basement 1 | 0
External Plaster |  | 8.8 | 23.16% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 26.6
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 38
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Phase I F Wing= Lower Stilt + Upper Stilt + 1st to 38th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 26 Slab, Brickwork upto 19 Floor, Internal Plaster upto 15.2 Floor, External Plaster upto 15.2 Floor Completed
|  |  | 0 | 2 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 38 | 100% | 45.75% |  | Excavation work Completed. Plinth work completed, RCC upto 26 Slab, Brickwork upto 19 Floor, Internal Plaster upto 15.2 Floor, External Plaster upto 15.2 Floor Completed |  | Excavation in process | 19
Plinth |  | 38 | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 26 | 65% |  |  |  |  | Footing in Process | 7.6
Brickwork |  | 19 | 50% |  |  |  |  | Footing Completed | 15.2
Internal Plaster |  | 15.2 | 40% |  |  |  |  | Basement 1 | 0
External Plaster |  | 15.2 | 40% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 26.6
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 38
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Phase II C wing = Upper Stilt + 1st to 38th Floor . |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.6 Floor, External Plaster upto 1.6 Floor Completed
|  |  | 0 | 1 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 38 | 100% | 30.6% |  | Excavation work Completed. Plinth work completed, RCC upto 8 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.6 Floor, External Plaster upto 1.6 Floor Completed |  | Excavation in process | 19
Plinth |  | 38 | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 8 | 20.51% |  |  |  |  | Footing in Process | 7.6
Brickwork |  | 2 | 5.263% |  |  |  |  | Footing Completed | 15.2
Internal Plaster |  | 1.6 | 4.211% |  |  |  |  | Basement 1 | 0
External Plaster |  | 1.6 | 4.211% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 26.6
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 38
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Phase II E Wing = Lower Stilt + Upper Stilt + 1st to 38th Floor. |  |  | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.6 Floor, External Plaster upto 1.6 Floor Completed
|  |  | 0 | 2 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 38 | 100% | 31.1% |  | Excavation work Completed. Plinth work completed, RCC upto 9 Slab, Brickwork upto 2 Floor, Internal Plaster upto 1.6 Floor, External Plaster upto 1.6 Floor Completed |  | Excavation in process | 19
Plinth |  | 38 | 100% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 9 | 22.5% |  |  |  |  | Footing in Process | 7.6
Brickwork |  | 2 | 5.263% |  |  |  |  | Footing Completed | 15.2
Internal Plaster |  | 1.6 | 4.211% |  |  |  |  | Basement 1 | 0
External Plaster |  | 1.6 | 4.211% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 26.6
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 38
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 36.49%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 18000 to 19000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA |  |  |  |  | 19375
Car Parking Charges |  | 600000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 1830.1747
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 6298.7737
Distress Value (Rs. Per sqft) |  |  |  |  | : | 1464.1397
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Total |  | - |  | 0 |  | 0 | 0
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Phase I | Wing D | Sale |  | 191 |  | 137308.1943
| Wing F | Sale |  | 204 |  | 85984.8772
Phase II | Wing C | Sale |  | 191 |  | 137308.1943
| Wing E | Sale |  | 191 |  | 122976.1129
Grand Total |  | - |  | 777 |  | 483577.3786
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Balcony Area | Attached Terrace area | Gross Carpet area
Phase I
Wing D
Upper Stilt Level Floor For Parking & Meter Room
1st Floor For Parking | [7 empty] | 1
2nd, 3rd & 4th Floor For Parking | [7 empty] | 3
5th Floor For Fitness Center, Society Office, Creche & Drivers Room | [7 empty] | 1
6th Floor For Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Sale | 3BHK | 834.1024 | 0 | 301.0153 | 909.3562
2 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414
3 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414
4 |  | - | Refuge Area
5A |  | Sale | 3.5BHK | 987.2741 | 0 | 0 | 987.2741
6 |  | Sale | 3BHK | 834.1024 | 0 | 301.0153 | 909.3562
7th to 9th, 11th to 14th, 16th to 19th, 21st to 24th, 26th to 29th, 31st to 34th & 36th to 38th Floor For Residential | [7 empty] | 26
1 |  | Sale | 3BHK | 834.1024 | 0 | 0 | 834.1024 |  | 18661.3191 | [5 empty] | 791101,..,3801 | 791101 | 3801
2 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [7 empty] | 791102,..,3802 | 791102 | 3802
3 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [7 empty] | 791103,..,3803 | 791103 | 3803
4 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 791104,..,3804 | 791104 | 3804
5 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 791105,..,3805 | 791105 | 3805
6 |  | Sale | 3BHK | 834.1024 | 0 | 0 | 834.1024 | [7 empty] | 791106,..,3806 | 791106 | 3806
10th, 15th, 20th, 25th, 30th & 35th Floor (Part Refuge Area) | [7 empty] | 6
1 |  | Sale | 3BHK | 834.1024 | 0 | 0 | 834.1024 | [7 empty] | 101501,..,301 | 101501 | 301
2 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [7 empty] | 101502,..,302 | 101502 | 302
3 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [7 empty] | 101503,..,303 | 101503 | 303
4 |  | - | Refuge Area | [11 empty] | 101504,..,304 | 101504 | 304
5A |  | Sale | 3.5BHK | 987.2741 | 0 | 0 | 987.2741 | [7 empty] | 101505,..,305 | 101505 | 305
6 |  | Sale | 3BHK | 834.1024 | 0 | 0 | 834.1024 | [7 empty] | 101506,..,306 | 101506 | 306
Wing F
Lower Stilt Level Floor For Parking & Meter Room
Upper Stilt Level Floor For Residential | [7 empty] | 1
1 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | #NUM!
2 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | #NUM!
3 |  | - | Double Height Entrance Lobby | [11 empty] | #REF! | #REF! | #NUM!
4 |  | - | [12 empty] | #REF! | #REF! | #NUM!
5 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | #NUM!
6 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | #NUM!
7 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | #NUM!
8 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | #NUM!
1st, 2nd & 3rd Floor For Part Residential | [7 empty] | 3
1 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 101 & 301 | 101 | 301
2 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 102 & 302 | 102 | 302
3 |  | - | Podium | [11 empty] | 103 & 303 | 103 | 303
4 |  | - | [12 empty] | 104 & 304 | 104 | 304
5 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 105 & 305 | 105 | 305
6 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 106 & 306 | 106 | 306
7 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 107 & 307 | 107 | 307
8 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 108 & 308 | 108 | 308
4th Floor For Part Residential | [7 empty] | 1
1 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 401
2 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 402
3 |  | - | Podium | [11 empty] | #REF! | #REF! | 403
4 |  | - | [12 empty] | #REF! | #REF! | 404
5 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 405
6 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 406
7 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 407
8 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 408
5th Floor For Part Residential & Amenity Area | [7 empty] | 1
1 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 501
2 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 502
3 |  | - | Fitness Center, Society Office, Creche & Drivers Room | [11 empty] | #REF! | #REF! | 503
4 |  | - | [12 empty] | #REF! | #REF! | 504
5 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 505
6 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 506
7 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 507
8 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 508
6th Floor For Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 601
2 |  | - | Refuge Area | [11 empty] | #REF! | #REF! | 602
3 |  | Sale | 1BHK | 420.8724 | 0 | 144.0223 | 492.8836 | [7 empty] | #REF! | #REF! | 603
4 |  | Sale | 1BHK | 420.8724 | 0 | 54.8964 | 475.7688 | [7 empty] | #REF! | #REF! | 604
5 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 605
6 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 606
7 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 607
8 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | #REF! | #REF! | 608
7th to 9th, 11th to 14th, 16th to 19th, 21st to 24th & 26th Floor | [7 empty] | 16
1 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 7901 & 201 | 7901 | 201
2 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 7902 & 202 | 7902 | 202
3 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 7903 & 203 | 7903 | 203
4 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 7904 & 204 | 7904 | 204
5 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 7905 & 205 | 7905 | 205
6 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 7906 & 206 | 7906 | 206
7 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 7907 & 207 | 7907 | 207
8 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 7908 & 208 | 7908 | 208
10th, 15th, 20th & 25th Floor (Part Refuge Area) | [7 empty] | 4
1 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 1001 & 201 | 1001 | 201
2 |  | - | Refuge Area | [11 empty] | 1002 & 202 | 1002 | 202
3 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 1003 & 203 | 1003 | 203
4 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 1004 & 204 | 1004 | 204
5 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 1005 & 205 | 1005 | 205
6 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 1006 & 206 | 1006 | 206
7 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 1007 & 207 | 1007 | 207
8 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 1008 & 208 | 1008 | 208
27th Floor (Part Refuge Area) | [7 empty] | 1
1 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 201 & 2701 | 201 | 2701
2 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 202 & 2702 | 202 | 2702
3 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 203 & 2703 | 203 | 2703
4 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 204 & 2704 | 204 | 2704
5 |  | - | Refuge Area | [11 empty] | 205 & 2705 | 205 | 2705
6 |  | - | [12 empty] | 206 & 2706 | 206 | 2706
7 |  | - | [12 empty] | 207 & 2707 | 207 | 2707
8 |  | Sale | 1BHK | 420.8724 | 0 | 0 | 420.8724 | [7 empty] | 208 & 2708 | 208 | 2708
Phase II
Wing C
Upper Stilt Level Floor For Parking & Meter Room
1st Floor For Parking | [7 empty] | 1
2nd, 3rd & 4th Floor For Parking | [7 empty] | 3
5th Floor For Fitness Center, Society Office, Creche & Drivers Room | [7 empty] | 1
6th Floor For Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Sale | 3BHK | 834.1024 | 0 | 301.0153 | 909.3562
2 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414
3 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414
4 |  | - | Refuge Area
5A |  | Sale | 3.5BHK | 987.2741 | 0 | 0 | 987.2741
6 |  | Sale | 3BHK | 834.1024 | 0 | 301.0153 | 909.3562
7th to 9th, 11th to 14th, 16th to 19th, 22nd to 24th, 26th to 29th, 31st to 34th & 36th to 38th Floor For Residential | [7 empty] | 25
1 |  | Sale | 3BHK | 834.1024 | 0 | 0 | 834.1024 | [7 empty] | 791101,..,3801 | 791101 | 3801
2 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [7 empty] | 791102,..,3802 | 791102 | 3802
3 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [7 empty] | 791103,..,3803 | 791103 | 3803
4 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 791104,..,3804 | 791104 | 3804
5 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 791105,..,3805 | 791105 | 3805
6 |  | Sale | 3BHK | 834.1024 | 0 | 0 | 834.1024 | [7 empty] | 791106,..,3806 | 791106 | 3806
21st Floor | [7 empty] | 1
1 |  | Sale | 3BHK | 834.1024 | 0 | 0 | 834.1024 | [7 empty] | 2101,..,2101 | 2101 | 2101
2 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [7 empty] | 2102,..,2102 | 2102 | 2102
3 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [7 empty] | 2103,..,2103 | 2103 | 2103
4 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 2104,..,2104 | 2104 | 2104
5 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 2105,..,2105 | 2105 | 2105
6 |  | Sale | 3BHK | 834.1024 | 0 | 0 | 834.1024 | [7 empty] | 2106,..,2106 | 2106 | 2106
10th, 15th, 20th, 25th, 30th & 35th Floor (Part Refuge Area) | [7 empty] | 6
1 |  | Sale | 3BHK | 834.1024 | 0 | 0 | 834.1024 | [7 empty] | 101501,..,301 | 101501 | 301
2 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [7 empty] | 101502,..,302 | 101502 | 302
3 |  | Sale | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [7 empty] | 101503,..,303 | 101503 | 303
4 |  | - | Refuge Area | [11 empty] | 101504,..,304 | 101504 | 304
5A |  | Sale | 3.5BHK | 987.2741 | 0 | 0 | 987.2741 | [7 empty] | 101505,..,305 | 101505 | 305
6 |  | Sale | 3BHK | 834.1024 | 0 | 0 | 834.1024 | [7 empty] | 101506,..,306 | 101506 | 306
Wing E | [7 empty] | Wing B Same
Lower Stilt Level Floor For Parking & Meter Room
Upper Stilt Level Floor For Parking & Natural Terrace
1st, 2nd & 3rd Floor For Parking | [7 empty] | 3
4th Floor For Parking | [7 empty] | 1
5th Floor For Fitness Center, Society Office, Creche & Drivers Room | [7 empty] | 1
6th Floor For Residential (Part Refuge Area) | [7 empty] | 1
1 |  | Sale | 2BHK | 629.9093 | 0 | 334.3223 | 713.4899
2 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093
3 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093
4 |  | - | Refuge Area
5A |  | Sale | 3.5BHK | 986.5206 | 0 | 0 | 986.5206
6 |  | Sale | 2BHK | 629.9093 | 0 | 334.3223 | 713.4899
7th to 9th, 11th to 14th, 16th to 19th, 21st to 24th, 26th to 29th, 31st to 34th & 36th to 38th Floor For Residential | [7 empty] | 26
1 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 791101,..,3801 | 791101 | 3801
2 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 791102,..,3802 | 791102 | 3802
3 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 791103,..,3803 | 791103 | 3803
4 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 791104,..,3804 | 791104 | 3804
5 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 791105,..,3805 | 791105 | 3805
6 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 791106,..,3806 | 791106 | 3806
10th, 15th, 20th, 25th, 30th & 35th Floor (Part Refuge Area) | [7 empty] | 6
1 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 101501,..,301 | 101501 | 301
2 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 101502,..,302 | 101502 | 302
3 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 101503,..,303 | 101503 | 303
4 |  | - | Refuge Area | [11 empty] | 101504,..,304 | 101504 | 304
5A |  | Sale | 3.5BHK | 986.5206 | 0 | 0 | 986.5206 | [7 empty] | 101505,..,305 | 101505 | 305
6 |  | Sale | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [7 empty] | 101506,..,306 | 101506 | 306
Project Specific Remarks & Observation
* | Construction work is in process at the time of Visit (labour found).
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | We have received Approved Plan of Wing A to F, but only Wing C to F was registered on RERA, therefore we have drafted report for Wing C to F.
Site & Building/Tower Photographs
Name of the Project |  |  | Maplewoods Phase I & II
Project Site Address |  |  | Maplewoods Phase I & II, Gut No.51(2) 56 and 57(2), near Krishna Business Park Airoli, Thane Belapur Road, Digha, Digha, Thane, Thane - 400708.
Site Visit Date & Time |  |  | 02/09/2025 @01:32PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr. Gangaram Lambore |  | Authorized Signatory Name & Signature
A
B
C
D
E
F
MHADA
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per plans
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G132: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0