## Report
APF Report Format
Name of Valuation Agency |  | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-26
Project Name |  | Maplewood Phase III |  | Date & Time of Site Visit |  | 02/09/2025 @ 01:32PM
Name of the person met at site & Contact No. |  | Mr. Rajnikant Gupta 8104096387 |  | Date of Report Release |  | 02/09/2025
Data from APF Request Form
Branch Name/ID |  | Godrej One, Mumbai-RO Thane |  | Request from GHF Employee |  | Mr. Suraj Khare
Builder Group Name |  | M/s. BKS Galaxy Realtors LLP |  | Developer Name |  | M/s. BKS Galaxy Realtors LLP
Developer Office Address |  | 1002/1202/1302, Bhumiraj Costarica, Sector - 18, Sanpada, Palm Beach Road, Tal. Thane, Dist. Thane 400705.
Project Address | As per ARF | Survey No. 51/2, 56 & 57/2, Thane - Belapur Rd, behind Krishna Business Park, Ramu Limaje Nagar, Dighe, Navi Mumbai, Maharashtra 400708
| As per Legal Documents | Proposed Residential Complex On Plot Bearing Gut Nos. 51(2), 56 & 57(2), Digha, Navi Mumbai.
| As per Actual at site | Maplewoods Phase III, Gut No.51(2), 56 and 57(2), near Krishna Business Park Airoli, Thane Belapur Road, Ramu Limaje Nagar, Digha, Thane East, Thane 400708.
Documents Provided by GHF |  | Approved Layout & Floor Plans, RERA certificate, Fire NOC, Environmental Clearance Certificate
General Details
Status of Holding | : | Freehold |  | Name of Municipal Corporation/Authority | : | Navi Mumbai Municipal Corporation (NMMC)
RERA Registration No. | : | P51700080212 |  | RERA Registration Validity | : | 2030-12-31
Project Launch Date | : | 2025-05-07 |  | Construction Start Date | : | 2025-05-01
Proposed Date of Completion (As per RERA) | : | 2030-12-31 |  | Developer Bank Name (As per RERA) | : | Indian Overseas Bank IFSC Code - IOBA0002110
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  | Plot Area (In Sq.Mt) | : | 20000
FSI/FAR Permissible | : | 1.5 |  | Net Plot Area (In Sq.Mt) | : | 19000
Permissible Built up Area (In Sq.Mt) | : | 108748.18 |  | Proposed Built up Area (In Sq.Mt) | : | 108748.18
Total Number of Units Approved | : | Flats = 507 & Shop = 17 |  | Total Number of Units Planned | : | As per RERA Site Flats = 507 & Shop = 17
Latitude, Longitude | : | 19.182221,72.9961192 |  | Landmark | : | Krishna Business Park
Location Link | : | https://maps.app.goo.gl/GXMpFXYcLRisuUQq9
Extra Amenities available | : | Skating Rink, Rooftop Garden, Squash Court, Badminton Court, Gym, Indoor Games, Café, Banquet Hall, Multipurpose Hall, Library, Yogga Zone, Day Care, Jogging Track, Splash Pad, Party Deck, Kids Play Area, Cricket Net, Gazebo, Swimming Pool, Kids Pool, Jacuzzi, Steam Room, Spa Room, Basketball Court, Tennis Court, etc. | [5 empty] | https://www.99acres.com/galaxy-maplewoods-airoli-navi-mumbai-npxid-r410532
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  | Width of the Road | : | 30M
Electrification/Electric poles observed | : | Yes |  | Distance from Bus stand (Km) | : | 0.20 KM from Mukund Company Bus Stop
Distance from the nearest School (Km) | : | About 0.50 KM from Swami Vivekanand English Medium School |  | Distance from Hospital (Km) | : | About 1.40 KM from Janseva Hospital
Distance from the Main Market (Km) | : | 1. Approx. 0.40KM from CITI mart. 2. Approx. 1.10 KM from Morya Super Market. |  | Distance from Railway Station (Km) | : | 0.450 KM from Digha Railway Station 3.50 KM from Airoli Railway Station
Water Supply | : | Being Provisioned |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  | III |  | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  | No |  | Property Falls in CR Zone | : | No
Degree of Risk Associated |  | Low |  | Any risk of Demolition | : | None
Boundaries
Boundaries |  | As per Layout |  |  | As per Site / Actual |  |  |  | North | South | East | West
East |  | Other Plot |  |  | Slums
West |  | 9M Wide Road |  |  | Road
North |  | Other Plot |  |  | Open Plot/Road
South |  | 30M Wide Road |  |  | Slums/Central Road
Boundaries Matching (If No, then reason thereon) |  | Yes
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Building A |  | Sale | LG +UG + 1st to 38th Floor |  |  | LG +UG + 1st to 38th Floor |  | https://proviso.in/maple-woods/
Building B |  | Sale | LG +UG + 1st to 38th Floor |  |  | LG +UG + 1st to 38th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | NRV/A - 17163 |  |  |  | Date: | 2023-04-11
Approved Plan Details | : | NRV/A - 17163 |  |  |  | Date: | 2023-04-11
CC Details Valid Up to: |  | NMMC/ТРО/ВP/17163/2023 |  |  |  | Date: | 2023-04-11
Total BUA = 108748.18 Sq. M. Residential Unit - 1284 Nos, Commercial Shop - 17 Nos & EWS/LIG Building (MHADA) Residential Unit - 112 Nos.
Environmental Clearance Details | : | SIA/MH/INFRA2/406628/2022 Survey Nos. 51(2), 56 & 57(2) Total Builtup Area = 164757.84 Sq.m. Building A & B = G + 1st to 38th Floor (Height = 129.65Mtrs) |  |  |  | Date: | 2023-04-11
Change of User/Zone Certificate Details | : |  |  |  |  | Date:
Airport Authority Clearance Details | : |  |  |  |  | Date:
Other NOC Details (Fire NOC) Valid Up to: |  | FIRE/HO/VASHI/1816/2023 |  |  |  | Date: | 2023-03-31
Building A = G + 1st to 38th Floor (Total Height = 131.60 Mtrs) Building B = G + 1st to 38th Floor (Total Height = 131.60 Mtrs)
Other NOC Details | : |  |  |  |  | Date:
Construction Status
Building A = LG +UG + 1st to 38th Floor. |  |  | Basement | Ground |  | Podium | Floors | Work not yet Started.
|  |  | 0 | 2 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 0 | 0% | 0% |  | Work not yet Started. |  | Excavation in process | 19
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 7.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 15.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 26.6
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 38
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Construction Status
Building B = LG +UG + 1st to 38th Floor. |  |  | Basement | Ground |  | Podium | Floors | Work not yet Started.
|  |  | 0 | 2 |  | 0 | 38 | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 9.5
Excavation |  | 0 | 0% | 0% |  | Work not yet Started. |  | Excavation in process | 19
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 38
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 7.6
Brickwork |  | 0 | 0% |  |  |  |  | Footing Completed | 15.2
Internal Plaster |  | 0 | 0% |  |  |  |  | Basement 1 | 0
External Plaster |  | 0 | 0% |  |  |  |  | Basement 2 | 0
External Plumbing, Elevation and Waterproofing |  | 0 | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 | 0% |  |  |  |  | Plinth in process | 26.6
Electrical & Sanitary fittings |  | 0 | 0% |  |  |  |  | Plinth completed | 38
Building Common Amenities |  | 0 | 0%
Possession |  | 0 | 0%
Project Completion % | [5 empty] | 0%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  | Sq. Ft |  | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  | 18000 to 19000 |  | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  | 600000 |  | Other Charges | : | As applicable and documented.
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | 1830.1747
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) |  |  |  |  | : | 6298.7737
Distress Value (Rs. Per sqft) |  |  |  |  | : | 1464.1397
Unit Details, Nomenclature and Area Details (Commercial)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Wing A1 + A2 |  | - |  | 17 |  | 9030.5654 |  | OK
Total |  | - |  | 17 |  | 9030.5654
Unit Details, Nomenclature and Area Details (Flats)
Building & Wing |  | Sale / Rehab |  | No. of Unit |  | Total Gross Carpet Area
Building A | Wing A1 | - |  | 158 |  | 122903.1852 |  | OK
| Wing A2 | - |  | 158 |  | 122903.1852 |  | OK
Building B |  | - |  | 191 |  | 122919.6541 |  | OK
Total |  | - |  | 507 |  | 368726.0244
Grand Total |  | - |  | 524 |  | 377756.5898
Details of Flats in Building
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Sale / Rehab / PAP | Description | Carpet area | Fungible area | Attached Terrace area | Gross Carpet area | 10.764
Building A
Wing A1 + A2
Lower Ground Floor For Commercial, Parking, Entrance Lobby, Meter Room & OWC Room
1 |  | - | Shop | 748.8515 | 0 | 0 | 748.8515
2 |  | - | Shop | 451.9804 | 0 | 0 | 451.9804 | 40.864
3 |  | - | Shop | 558.9745 | 0 | 0 | 558.9745 | 50.63
4 |  | - | Shop | 548.1029 | 0 | 0 | 548.1029
5 |  | - | Shop | 548.2105 | 0 | 0 | 548.2105
6 |  | - | Shop | 558.7592 | 0 | 0 | 558.7592
7 |  | - | Shop | 386.6429 | 0 | 0 | 386.6429
8 |  | - | Shop | 386.6429 | 0 | 0 | 386.6429
9 |  | - | Shop | 548.1029 | 0 | 0 | 548.1029
10 |  | - | Shop | 386.6429 | 0 | 0 | 386.6429
11 |  | - | Shop | 386.6429 | 0 | 0 | 386.6429 | 34.953
12 |  | - | Shop | 558.7592 | 0 | 0 | 558.7592
13 |  | - | Shop | 548.2105 | 0 | 0 | 548.2105
14 |  | - | Shop | 548.2105 | 0 | 0 | 548.2105
15 |  | - | Shop | 558.7592 | 0 | 0 | 558.7592
16 |  | - | Shop | 558.544 | 0 | 0 | 558.544
17 |  | - | Shop | 748.5286 | 0 | 0 | 748.5286
Upper Ground Floor For Parking & Natural Terrace
1st to 4th Floor as Podium Parking | [7 empty] | 4
5th Floor For Natural Terrace, Parking, Fitness Center, Society Office & Drivers Room | [7 empty] | 1
Wing A1
6th Floor For Residential (Part Refuge Area) | [7 empty] | 1
1 |  | - | 3BHK | 826.137 | 0 | 0 | 826.137 | 73.2262 |  | 102.7693 |  |  | 101,..,401 | 101 | 401
2 |  | - | 3BHK | 843.8976 | 0 | 0 | 843.8976 | a |  | 102.7693 |  |  | 102,..,402 | 102 | 402
3 |  | - | 3BHK | 829.4738 | 0 | 0 | 829.4738 | a |  | 118.108 |  |  | 103,..,403 | 103 | 403
- |  | - | Refuge Area | [9 empty] | 104,..,404 | 104 | 404
5A |  | - | 3.5BHK | 987.1664 | 0 | 142.1817 | 1058.2573 | 86.132 |  | 108.3397 |  |  | 105,..,405 | 105 | 405
7th to 9th, 11th to 14th, 16th to 19th, 21st to 24th, 26th to 29th, 31st to 34th & 36th to 38th Floor | [7 empty] | 26
1 |  | - | 3BHK | 826.137 | 0 | 0 | 826.137 |  |  | 102.7693 |  |  | 791101 to 3801 | 791101 | 3801
2 |  | - | 3BHK | 843.8976 | 0 | 0 | 843.8976 |  |  | 102.7693 |  |  | 791102 to 3802 | 791102 | 3802
3 |  | - | 3BHK | 829.4738 | 0 | 0 | 829.4738 |  |  | 118.108 |  |  | 791103 to 3803 | 791103 | 3803
4 |  | - | 2BHK | 643.0414 | 0 | 0 | 643.0414 |  |  | 91.3056 |  |  | 791104 to 3804 | 791104 | 3804
5 |  | - | 2BHK | 643.0414 | 0 | 0 | 643.0414 | 56.5506 |  | 91.3056 |  |  | 791105 to 3805 | 791105 | 3805
10th, 15th, 20th, 25th, 30th & 35th Floor For Residential (Part Refuge Area) | [7 empty] | 6
1 |  | - | 3BHK | 826.137 | 0 | 0 | 826.137 |  |  | 102.7693 |  |  | 301,..,301 | 301 | 301
2 |  | - | 3BHK | 843.8976 | 0 | 0 | 843.8976 |  |  | 102.7693 |  |  | 302,..,302 | 302 | 302
3 |  | - | 3BHK | 829.4738 | 0 | 0 | 829.4738 |  |  | 118.108 |  |  | 303,..,303 | 303 | 303
- |  | - | Refuge Area | [9 empty] | 304,..,304 | 304 | 304
5A |  | - | 3.5BHK | 987.1664 | 0 | 0 | 987.1664 |  |  | 108.3397 |  |  | 305,..,305 | 305 | 305
Wing A2
6th Floor For Residential (Part Refuge Area) | [7 empty] | 1
1 |  | - | 3BHK | 826.137 | 0 | 0 | 826.137 | [5 empty] | #REF! | #REF! | #NUM!
2 |  | - | 3BHK | 843.8976 | 0 | 0 | 843.8976 | [5 empty] | #REF! | #REF! | #NUM!
3 |  | - | 3BHK | 829.4738 | 0 | 0 | 829.4738 | [5 empty] | #REF! | #REF! | #NUM!
- |  | - | Refuge Area | [9 empty] | #REF! | #REF! | #NUM!
5A |  | - | 4BHK | 987.1664 | 0 | 142.1817 | 1058.2573 | [5 empty] | #REF! | #REF! | #NUM!
7th to 9th, 11th to 14th, 16th to 19th, 21st to 24th, 26th to 29th, 31st to 34th & 36th to 38th Floor | [7 empty] | 26
1 |  | - | 3BHK | 826.137 | 0 | 0 | 826.137 | [5 empty] | 791101 to 3801 | 791101 | 3801
2 |  | - | 3BHK | 843.8976 | 0 | 0 | 843.8976 | [5 empty] | 791102 to 3802 | 791102 | 3802
3 |  | - | 3BHK | 829.4738 | 0 | 0 | 829.4738 | [5 empty] | 791103 to 3803 | 791103 | 3803
4 |  | - | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [5 empty] | 791104 to 3804 | 791104 | 3804
5 |  | - | 2BHK | 643.0414 | 0 | 0 | 643.0414 | [5 empty] | 791105 to 3805 | 791105 | 3805
10th, 15th, 20th, 25th, 30th & 35th Floor For Residential (Part Refuge Area) | [7 empty] | 6
1 |  | - | 3BHK | 826.137 | 0 | 0 | 826.137 | [5 empty] | 301,..,301 | 301 | 301
2 |  | - | 3BHK | 843.8976 | 0 | 0 | 843.8976 | [5 empty] | 302,..,302 | 302 | 302
3 |  | - | 3BHK | 829.4738 | 0 | 0 | 829.4738 | [5 empty] | 303,..,303 | 303 | 303
- |  | - | Refuge Area | [9 empty] | 304,..,304 | 304 | 304
5A |  | - | 4BHK | 987.1664 | 0 | 0 | 987.1664 | [5 empty] | 305,..,305 | 305 | 305
Building B
Lower Ground Floor For Parking, Entrance Lobby, Meter Room & OWC Room
Upper Ground Floor For Parking & Natural Terrace
1st to 4th Floor For Parking
5th Floor as Podium Parking, Fitness Center & Drivers Room
6th Floor For Residential (Part Refuge Area) | [7 empty] | 1
1 |  | - | 2BHK | 629.9093 | 0 | 110.7024 | 685.2605 | 54.9396 | 66.5215 |  |  |  | #REF! | #REF! | 501
2 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 |  | 91.3056 |  |  |  | #REF! | #REF! | 502
3 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 |  | 91.3056 |  |  |  | #REF! | #REF! | 503
- |  | - | Refuge Area | [9 empty] | #REF! | #REF! | 504
5A |  | - | 3.5BHK | 986.5206 | 0 | 0 | 986.5206 |  | 159.1188 |  |  |  | #REF! | #REF! | 505
6 |  | - | 2BHK | 629.9093 | 0 | 110.7024 | 685.2605 |  | 66.5215 |  |  |  | #REF! | #REF! | 506
7th to 9th, 11th to 14th, 16th to 19th, 21st to 24th, 26th to 29th, 31st to 34th & 36th to 38th Floor | [7 empty] | 26
1 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 |  | 91.3056 |  |  |  | #REF! | #REF! | 601
2 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 |  | 91.3056 |  |  |  | #REF! | #REF! | 602
3 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 |  | 91.3056 |  |  |  | #REF! | #REF! | 603
4 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 |  | 91.3056 |  |  |  | #REF! | #REF! | 604
5 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 |  | 91.3056 |  |  |  | #REF! | #REF! | 605
6 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 |  | 91.3056 |  |  |  | #REF! | #REF! | 606
10th, 15th, 20th, 25th, 30th & 35th Floor For Residential (Part Refuge Area) | [7 empty] | 6
1 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [5 empty] | #REF! | #REF! | 601
2 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [5 empty] | #REF! | #REF! | 602
3 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [5 empty] | #REF! | #REF! | 603
- |  | - | Refuge Area | [9 empty] | #REF! | #REF! | 604
5A |  | - | 3.5BHK | 986.5206 | 0 | 0 | 986.5206 | [5 empty] | #REF! | #REF! | 605
6 |  | - | 2BHK | 629.9093 | 0 | 0 | 629.9093 | [5 empty] | #REF! | #REF! | 606
Project Specific Remarks & Observation
* | Building A & B = Work not yet Started.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + Terrace area.
* | We have considered rate by verifying it from market inquire.
* | Car parking is subjected to authentic documentation.
* | The layout plan consists of Wings A to F & Mhada Building. Phase I consists of Wing D & F, Phase II consists of Wing C & E & Phase III consists of Wing A & B. But we have received the RERA certificate for Phase III (Wing A & B), so we have drafted the APF report for Phase III (Wing A & B).
* | We have refered CC from RERA site on 17/06/2025.
* | Since the project has received CC on 11/04/2023, But construction work is not yet Started.
* | Remark for NOCs
Site & Building/Tower Photographs
Name of the Project |  |  | Maplewood Phase III
Project Site Address |  |  | Survey No. 51/2, 56 & 57/2, Thane - Belapur Rd, behind Krishna Business Park, Ramu Limaje Nagar, Dighe, Navi Mumbai, Maharashtra 400708
Site Visit Date & Time |  |  | 02/09/2025 @ 01:32PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  | Mr. Gangaram Lambore |  | Authorized Signatory Name & Signature
Maplewoods Phase III
Building A
Building B
Building F
Building E
Building D
Building C
MHADA Bldg
Note on C9: SACHIN: As per initiation Mail
Note on C10: SACHIN: As per plans
Note on C11: SACHIN: As per maps
Note on G17: From Rera
Note on G20: From RERA
Note on G21: From RERA
Note on G27: SACHIN: Road size should be in metre
Note on G98: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 25% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0