## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-26
Project Name |  |  | : | Rustomjee LA VIE (Wing A, B & C) |  | Date & Time of Site Visit |  | 15/09/2025 @05:35PM |  | 2025-04-23 | 2025-06-23 | 2025-09-15
Name of the person met at site & Contact No. |  |  | : | NA |  | Date of Report Release |  | 15/09/2025 | Mr. Santosh Shetty (sales) - 9820995007. |  | 61 | 84
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Kapstone Constructions Private Limited | Developer Name | : | Kapstone Constructions Private Limited
Developer Office Address |  |  | :
Project Address | : | As per ARF | : | Rustomjee LA VIE (Wing B & C), Survey No.12, 13, 14pt, 15, 16pt, 17pt, 18pt, 19pt, 20, 21pt, 30pt, 35 to 38, 41, 42, 43, 44, 45pt, 46pt, 47pt, 47pt, 48, 49, 50, 51, 53pt, 54, 55, 84pt, 327, 328, 329, 345, 383, 386pt, 423, 424 & Others, near Lodha Crown, RG Road, Majiwade, Balkum Pada, Thane West, Thane, Thane - 400607.
| : | As per Legal Documents | : | (Building name, CTS No., Plot No., Survey No., Road., Locality/Village., District., Taluka., Pin Code - )
| : | As per Actual at site | :
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC, RERA certificate, NOC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation (TMC)
RERA Registration No. | : | Wing A = P51700050803 Wing B = P51700053110 Wing C = P51700053109 |  |  | RERA Registration Validity | : | Wing A = 31/12/2028 Wing B, Wing C = 28/02/2029
Project Launch Date | : |  |  |  | Construction Start Date | :
Proposed Date of Completion (As per RERA) | : |  |  |  | Developer Bank Name (As per RERA) | :
Project Type (Mixed, Residential, Comm.) | : | Residential + Commercial |  |  | Plot Area (In Sq.Mt) | :
FSI/FAR Permissible | : |  |  |  | Proposed Built up Area (In Sq.Mt) | :
Permissible Built up Area (In Sq.Mt) | : |  |  |  | Total Number of Units Planned | : | As per RERA Site Flats = & Shop =
Total Number of Units Approved | : | Flats = |  |  | If Mixed, No. of Commercial Units | : | Shop =
Latitude, Longitude | : | 19.210904,72.990706 |  |  | Landmark | : | Lodha Crown
Location Link | : | https://maps.app.goo.gl/aVUwZZpd5W4LfYTT6
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from the Main Market (Km) | : | 1. Approx. 2KM from Village Market. 2. Approx. 10KM from Panvel Main Market.
Distance from the nearest School (Km) | : | About 4KM from School |  |  | Distance from Hospital (Km) | : | About 4K form Hospital
Distance from Bus stand (Km) | : | 1.2 KM from Saket Complex Bus Stop |  |  | Distance from Railway Station (Km) | : | 4.4 KM from Thane Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Other Plot | 20.00 M. Wide Service Road | 45.00 M. Wide D.P. Road |  | Other Plot
As per Site / Actual |  |  | : | Other Plot | RG Road | RG Road/Pipeline Road |  | Loadha Crown
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing A |  | Sale |  | 4B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 55th Floor |  |  | 4B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 55th Floor
Wing B |  | Sale |  | 4B + Gr/stilt + 1st to 22nd Floor + Service Floor + Recreational Floor +23rd to 53rd Floor |  |  | 4B + Gr/stilt + 1st to 22nd Floor + Service Floor + Recreational Floor +23rd to 53rd Floor
Wing C |  | Sale |  | 4B + Gr/stilt + 1st to 23rd Floor + Service Floor + Recreational Floor +24th to 54th Floor |  |  | 4B + Gr/stilt + 1st to 23rd Floor + Service Floor + Recreational Floor +24th to 54th Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes |  |  | LOI/IOD Details | : | Date:
Approved Plan Details | : | NA
Environmental Clearance Details | : | Date: |  |  | Airport Authority Clearance Details | : | Date:
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | :
CC Details | : | S05/0022/10 TMCB/TDD/0006/(P/T)/ 2023/AutoDCR Date: 15/09/2023 Valid Up to: Wing A = 4 Level Basement + Stilt/Ground/ Retial Shops + 1st to 22nd Floor + Service Floor + Recreational Floor + 23rd to 53rd Floor Wing B = 4 Level Basement + Stilt/Ground/ Retial Shops + 1st to 22nd Floor + Service Floor + Recreational Floor + 23rd to 53rd Floor Wing C = 4 Level Basement + Stilt/Ground + 1st to 23rd Floor + Service Floor + Recreational Floor + 24th to 54th Floor
Construction Status
Wing A= 4B + G + 1st to 22nd + Service Floor + Recreational Floor + 23rd to 55th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 10 Slab Completed
|  |  |  | 4 | 1 |  | 0 | 55 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.75
Excavation |  | 55 |  | 100% | 29.46% |  | Excavation work Completed. Plinth work completed, RCC upto 10 Slab Completed |  | Excavation in process | 27.5
Plinth |  | 55 |  | 100% |  |  |  |  | Excavation Completed | 55
RCC (Including podiums) |  | 10 |  | 17.86% |  |  |  |  | Footing in Process | 9.1667
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 18.3333
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 27.5
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 36.6667
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 45.8333
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 55 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing B= 4B + Gr/stilt + 1st to 22nd Floor + Service Floor + Recreational Floor +23rd to 53rd Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
|  |  |  | 4 | 1 |  | 0 | 53 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.25
Excavation |  | 53 |  | 100% | 25.46% |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed |  | Excavation in process | 26.5
Plinth |  | 53 |  | 100% |  |  |  |  | Excavation Completed | 53
RCC (Including podiums) |  | 1 |  | 1.852% |  |  |  |  | Footing in Process | 8.8333
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 17.6667
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 26.5
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 35.3333
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 44.1667
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 53 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing C= 4B + Gr/stilt + 1st to 23rd Floor + Service Floor + Recreational Floor +24th to 54th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed
|  |  |  | 4 | 1 |  | 0 | 54 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 13.5
Excavation |  | 54 |  | 100% | 25.45% |  | Excavation work Completed. Plinth work completed, RCC upto 1 Slab Completed |  | Excavation in process | 27
Plinth |  | 54 |  | 100% |  |  |  |  | Excavation Completed | 54
RCC (Including podiums) |  | 1 |  | 1.818% |  |  |  |  | Footing in Process | 9
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 18
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 27
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 36
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 45
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 54 |  | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 26.79%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 18000 to 19000 | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA |  |  | 18000
Car Parking Charges |  |  | : | 600000 | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | :
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | :
Distress Value (Rs. Per sqft) | [5 empty] | : | 0
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Gross Carpet Area
Total |  | 0 |  | 0 | 0 |  | 0 | 0
Details of Flats in Building
Flat/Shop No. |  | Description |  | Carpet area | Fungible area |  | Attached Terrace area | Gross Carpet area
1st Floor
101 |  |  |  | 0 | 0 |  | 0 | 0
102 | [7 empty] | 0
103 | [7 empty] | 0
104 | [7 empty] | 0
105 | [7 empty] | 0
106 | [7 empty] | 0
107 | [7 empty] | 0
108 | [7 empty] | 0
2nd, 3rd, 4th, 6th, 8th, 7th, 9th Floor
201,..,901 | [7 empty] | 0 |  |  |  |  | 201,..,901 | 201 | 901
202,..,902 | [7 empty] | 0 |  |  |  |  | 202,..,902 | 202 | 902
203,..,903 | [7 empty] | 0 |  |  |  |  | 203,..,903 | 203 | 903
204,..,904 | [7 empty] | 0 |  |  |  |  | 204,..,904 | 204 | 904
205,..,905 | [7 empty] | 0 |  |  |  |  | 205,..,905 | 205 | 905
206,..,906 | [7 empty] | 0 |  |  |  |  | 206,..,906 | 206 | 906
207,..,907 | [7 empty] | 0 |  |  |  |  | 207,..,907 | 207 | 907
208,..,908 | [7 empty] | 0 |  |  |  |  | 208,..,908 | 208 | 908
209,..,909 | [7 empty] | 0 |  |  |  |  | 209,..,909 | 209 | 909
210,..,910 | [7 empty] | 0 |  |  |  |  | 210,..,910 | 210 | 910
2nd to 5th Floor
201 to 501 | [7 empty] | 0 |  |  |  |  | 201 to 501 | 201 | 501
202 to 502 | [7 empty] | 0 |  |  |  |  | 202 to 502 | 202 | 502
203 to 503 | [7 empty] | 0 |  |  |  |  | 203 to 503 | 203 | 503
204 to 504 | [7 empty] | 0 |  |  |  |  | 204 to 504 | 204 | 504
205 to 505 | [7 empty] | 0 |  |  |  |  | 205 to 505 | 205 | 505
206 to 506 | [7 empty] | 0 |  |  |  |  | 206 to 506 | 206 | 506
207 to 507 | [7 empty] | 0 |  |  |  |  | 207 to 507 | 207 | 507
208 to 508 | [7 empty] | 0 |  |  |  |  | 208 to 508 | 208 | 508
209 to 509 | [7 empty] | 0 |  |  |  |  | 209 to 509 | 209 | 509
210 to 510 | [7 empty] | 0 |  |  |  |  | 210 to 510 | 210 | 510
2nd & 5th Floor
201 & 501 | [7 empty] | 0 |  |  |  |  | 201 & 501 | 201 | 501
202 & 502 | [7 empty] | 0 |  |  |  |  | 202 & 502 | 202 | 502
203 & 503 | [7 empty] | 0 |  |  |  |  | 203 & 503 | 203 | 503
204 & 504 | [7 empty] | 0 |  |  |  |  | 204 & 504 | 204 | 504
205 & 505 | [7 empty] | 0 |  |  |  |  | 205 & 505 | 205 | 505
206 & 506 | [7 empty] | 0 |  |  |  |  | 206 & 506 | 206 | 506
207 & 507 | [7 empty] | 0 |  |  |  |  | 207 & 507 | 207 | 507
208 & 508 | [7 empty] | 0 |  |  |  |  | 208 & 508 | 208 | 508
209 & 509 | [7 empty] | 0 |  |  |  |  | 209 & 509 | 209 | 509
210 & 510 | [7 empty] | 0 |  |  |  |  | 210 & 510 | 210 | 510
Project Specific Remarks & Observation | [9 empty] | 19062.5 | 2188208.6168
Remarks / Observations | : | 1. Construction work is in process at the time of Visit. Internal visit not allowed. 2. We have considered rate by verifying it from market inquire. 3. Car parking is subjected to authentic documentation. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Enclose balcony + D.B Area + F.B Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. On Site, we meet Mr........(........). 8. As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Rustomjee LA VIE (Wing A, B & C)
Project Site Address |  |  | : | Rustomjee LA VIE (Wing B & C), Survey No.12, 13, 14pt, 15, 16pt, 17pt, 18pt, 19pt, 20, 21pt, 30pt, 35 to 38, 41, 42, 43, 44, 45pt, 46pt, 47pt, 47pt, 48, 49, 50, 51, 53pt, 54, 55, 84pt, 327, 328, 329, 345, 383, 386pt, 423, 424 & Others, near Lodha Crown, RG Road, Majiwade, Balkum Pada, Thane West, Thane, Thane - 400607.
Site Visit Date & Time |  |  | : | 15/09/2025 @05:35PM
Layout
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Ajay | Authorized Signatory Name & Signature | :
Wing C
Wing B
Wing B
Wing A
Note on E9: Initiation Address
Note on E10: Plan Address
Note on E11: Map Address
Note on C17: Maybe same as RERA Registration Validity or different
Note on H17: From Rera
Note on H20: From RERA
Note on A39: As per Layout
Note on H113: Ready Recknor

## Construction table
Construction Status
1 |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed
|  |  |  | 3 | 1 |  | 0 | 1 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 0.25
Excavation |  | 1 |  | 100% | 35% |  | Excavation work Completed. Plinth work completed |  | Excavation in process | 0.5
Plinth |  | 1 |  | 100% |  |  |  |  | Excavation Completed | 1
RCC (Including podiums) |  | 0 |  | 0% |  |  |  |  | Footing in Process | 0.2
Brickwork |  | 0 |  | 0% |  |  |  |  | Footing Completed | 0.4
Internal Plaster |  | 0 |  | 0% |  |  |  |  | Basement 1 | 0.6
External Plaster |  | 0 |  | 0% |  |  |  |  | Basement 2 | 0.8
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 1
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Linked Plan
| Milestones | Weightage | No. of Floors | Floors Completed | Completion % | Recommendation %
| Completion of excavation | 10 | 1 |  | 0 | 0
| Completion of footing | 10 | 1 |  | 0 | 0
| Completion of plinth | 15 | 1 |  | 0 | 0
| Completion of RCC | 25 | 40 |  | 0 | 0
| Completion of Brickwork | 5 | 39 |  | 0 | 0
| Completion of Internal Plaster | 2.5 | 39 |  | 0 | 0
| Completion of External plaster | 2.5 | 39 |  | 0 | 0
| Completion of external plumbing, elevation and waterproofing | 5 | 39 |  | 0 | 0
| Completion of Flooring, tiling, doors and windows | 5 | 39 |  | 0 | 0
| Completion of Electrical and sanitary fittings | 5 | 39 |  | 0 | 0
| Completion of lifts, entrance lobbies, plinth protection and paving of area | 10 | 39 |  | 0 | 0
| On possesssion OR receipt of Occupancy/Completion certificate | 5 | 39 |  | 0 | 0
| Total % | 100 |  |  | 0 | 0
Approval Matrix For Accelerated Disbursement (If Builder Demand is more than GHFL Recommendation)
| Accelerated Disbursement % |  |  | Approving Authority
| Up to 10% |  |  | ATM
| >10% - 15% |  |  | Head-Technical
| >15% |  |  | CCO
Sr. no. | Milestones | GHF Stage % | GHF Reco % | RERA Threshold
1 | On or before execution of the agreement | 0% | 10% | 10%
2 | On execution of Agreement | 1-10% | 11-20% | 30%
3 | On completion of the Plinth of the building or wing inwhich the said Apartment is located | 11-25% | 21-35% | 45%
4 | On completion of the slabs including podiums and stilts of the building or wing in which the said Apartment is located | 26-50% | 36-60% | 70%
5 | On completion of the walls, internal plaster, floorings, doors and windows of the said Apartment | 51-65% | 61-75% | 75%
6 | On completion of the Sanitary fittings, staircases, lift wells, lobbies upto the floor level of the said Apartment | 66-70% | 76-80% | 80%
7 | On completion of the external plumbing and external plaster, elevation, terraces with waterproofing, of the building or wing in whichthe said Apartment is located | 71-80% | 81-85% | 85%
8 | On completion of the lifts, water pumps, electrical fittings, electro, mechanical and environment requirements, entrance lobby/s, plinth protection, paving of areas appertain and all other requirements as maybe prescribed in the Agreement of sale of the building or wing in which the said Apartment is located. | 81-90% | 85-95% | 95%
9 | At the time of handing over of the possession of the Apartment to the Allottee on or after receipt of Occupancy Certificate or Completion Certificate | 91-100% | 96-100% | 100%