## Report
APF Report Format
Name of Valuation Agency |  |  | : | V.S Jadon & Co.Valuers LLP |  | Date of Technical Initiation |  | 2025-08-26 | 2025-03-25 | 2025-06-23
Project Name |  |  | : | Rustomjee La Familia A & B Wing (Rustomjee Urbania) |  | Date & Time of Site Visit |  | 15/09/2025 @ 02:00PM | 90
Name of the person met at site & Contact No. |  |  | : | NA |  | Date of Report Release |  | 2025-09-15 |  | Mr.Santosh Shetty - 9820995007. |  | 15/09/2025
Data from APF Request Form
Branch Name/ID |  |  | : | Godrej One, Vikhroli East, Mumbai | Request from GHF Employee | : | Mr. Suraj Khare
Builder Group Name |  |  | : | Kapstone Constructions Private Limited | Developer Name | : | Runwal Group
Developer Office Address |  |  | : | Runwal & Omkar Esquare, 5th Floor, Eastern Express Highway, Sion (East), Mumbai – 400022
Project Address | : | As per ARF | : | Rustomjee Urbania, Eastern Express Hwy, Majiwada, Junction, Thane West, Mumbai, Maharashtra 400601
| : | As per Legal Documents | : | Rustomjee Urbania, Prop.Bldg. No Property Bearing S.No. 12, 13, 14pt, 15, 16pt, 17pt, 18pt, 19pt, 20, 21pt, 30pt, 35 to 38, 41, 42, 43, 44, 45pt, 46pt, 48, 50, 51, 53pt 54, 55, 84pt, 327, 328, 329, 345, 383, 386pt, 423, 424 & Others At Village Majiwada, Thane (West).
| : | As per Actual at site | : | Rustomjee Urbania, Road - Saket - Kalwa Road, Near - Lodha Codename Crown Jewel, Village - Majiwada, Thane West, Mumbai, Maharashtra 400601
Documents Provided by GHF |  |  | : | Approved Layout & Floor Plans, CC
General Details
Status of Holding | : | Freehold |  |  | Name of Municipal Corporation/Authority | : | Thane Municipal Corporation (TMC)
RERA Registration No. | : | Rustomjee La Familia A Wing - P51700032262 B Wing - P51700032205 |  |  | RERA Registration Validity | : | 2026-12-31
Project Launch Date | : | 2021-11-30 |  |  | Construction Start Date | : | 2021-12-20
Proposed Date of Completion (As per RERA) | : | 2026-12-31 |  |  | Developer Bank Name (As per RERA) | : | Standard Chartered Bank Ltd IFSC Code - SCBL0036085
Project Type (Mixed, Residential, Comm.) | : | Residential |  |  | Plot Area (In Sq.Mt) | : | 463538.45
FSI/FAR Permissible | : | 1 |  |  | Proposed Built up Area (In Sq.Mt) | : | 346925.68
Permissible Built up Area (In Sq.Mt) | : | 414407.43 |  |  | Total Number of Units Planned | : | As per Rera Flats = 782
Total Number of Units Approved | : | Flats = 704 |  |  | If Mixed, No. of Commercial Units | : | Shop = NA
Latitude | : | 19.2115 |  |  | Longitude | : | 72.9903
Extra Amenities available | : | Entrance, Drop-off points, Central Breezeway, Open Party, Lawn, Zen Garden, Jogging Track, Pet Zone, Amphitheatre, Senior Citizen's Area, Reflexology pathway, Outdoor Activity Lawn, Chlorine-free infinity Pool, Chlorine-free Kid's Pool, Kids Play Area, Barbeque corner, Seating Promenade, Clubhouse, Cafe, Gym, Basketball Court, Futsal Court, Cricket pitch, Sunken Seating with Planters, Canopy covered Walkway, Spa, Reading Room, Yoga/Aerobics Room, Indoor games, Billiards Room.
Zone/Locality/Surrounding/Civic Amenities
Infrastructure in the area | : | Developing |  |  | Class of Locality | : | Middle
Type of Road | : | Bitumen |  |  | Width of the Road | : | 9ft
Electrification/Electric poles observed | : | Yes |  |  | Distance from Bus stand (Km) | : | 2.9 KM from Thane Central Bus Stand(CBS).
Distance from the nearest School (Km) | : | About 1.4 KM from Lodha World School |  |  | Distance from Hospital (Km) | : | About 3.2K form Sapphire Hospital.
Distance from the Main Market (Km) | : | 1. Approx. 3.4 KM from DMart Kolshet. 2. Approx. 1.5KM fromKuldeep super Market. |  |  | Distance from Railway Station (Km) | : | 4.8KM from Thane Railway Station 3.7KM from Kalwa Railway Station
Water Supply | : | Being Provisioned |  |  | Electricity Supply | : | Being Provisioned
Drainage Connection | : | Being Provisioned
NDMA Guidelines
Property falls under Seismic Zone |  |  | : | III | Property Falls under Flood Zone | : | No
Property Falls in Cyclone Zone |  |  | : | No | Property Falls in CR Zone | : | No
Degree of Risk Associated |  |  | : | Low | Any risk of Demolition | : | None
Boundaries | [8 empty] | Proposed structure changed on 01/07/2025
Boundaries |  |  | : | North | South | East |  | West
As per Documents |  |  | : | Open Plot | Road | Open Plot |  | Open Plot | https://www.youtube.com/watch?v=2yEJGhaD0Eo
As per Site / Actual |  |  | : | Lodha Codename Crown Jewel | Road | Open Plot |  | Lodha Quality Homes
Boundaries Matching |  |  | : | Yes | If No, then reason thereon | : | -
Project Structure
Building/Tower Name/No. |  | Type (Sale/Rehab) |  | No. of Floors Planned/Proposed |  |  | No. of Floors Approved
Wing A & B |  | Sale |  | 3B + G/St + 1st to 22nd Floor + Service Floor + 23rd to 47th Floor. |  |  | 3B + G/St + 1st to 22nd Floor + Service Floor + 23rd to 45th Floor + Recreational Floor
Building Permission & Other Approvals
Construction as per Approved/ Sanctioned Plans | : | Yes
LOI/IOD Details | : | S05/0022/10/TMC/TD-DP/TPS/3784/21 |  |  |  |  | Date: | 2021-11-30
Approved Plan Details | : | S05/0022/10/TMC/TD-DP/TPS/3784/21 |  |  |  |  | Date: | 2021-11-30
CC Details | : | S05/0022/10/TMC/TDD3784/21 Valid Up to: Bldg. no. Wing A & B = 3B + G/St + 1st to 22nd Floor + Service Floor + 23rd to 45th Floor + Recreational Floor. |  |  |  |  | Date: | 2021-11-30
Environmental Clearance Details | : | - |  |  | Airport Authority Clearance Details | : | -
Change of User/Zone Certificate Details | : | - |  |  | Other NOC Details | : | -
Construction Status
A Wing = 3B + G/St + 1st to 22nd Floor + Service Floor + 23rd to 47th Floor |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 44 Floor, External Plaster upto 44 Floor, External Plumbing, Elevation and Waterproofing upto 36 Floor, Flooring & Fitting upto 36 Floor, Wooden Work upto 24 Floor, Electrical & Sanitary fittings upto 24 Floor Completed
|  |  |  | 3 | 1 |  | 0 | 47 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11.75
Excavation |  | 47 |  | 100% | 73.72% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 44 Floor, External Plaster upto 44 Floor, External Plumbing, Elevation and Waterproofing upto 36 Floor, Flooring & Fitting upto 36 Floor, Wooden Work upto 24 Floor, Electrical & Sanitary fittings upto 24 Floor Completed |  | Excavation in process | 23.5
Plinth |  | 47 |  | 100% |  |  |  |  | Excavation Completed | 47
RCC (Including podiums) |  | 48 |  | 100% |  |  |  |  | Footing in Process | 9.4
Brickwork |  | 47 |  | 100% |  |  |  |  | Footing Completed | 18.8
Internal Plaster |  | 44 |  | 93.62% |  |  |  |  | Basement 1 | 28.2
External Plaster |  | 44 |  | 93.62% |  |  |  |  | Basement 2 | 37.6
External Plumbing, Elevation and Waterproofing |  | 36 |  | 76.6% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 36 |  | 76.6% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 24 |  | 51.06% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 24 |  | 51.06% |  |  |  |  | Plinth completed | 47 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing B = 3B + G/St + 1st to 22nd Floor + Service Floor + 23rd to 47th Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 42 Floor, External Plaster upto 42 Floor, External Plumbing, Elevation and Waterproofing upto 38 Floor, Flooring & Fitting upto 38 Floor, Wooden Work upto 28 Floor, Electrical & Sanitary fittings upto 28 Floor Completed
|  |  |  | 3 | 1 |  | 0 | 47 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 11.75
Excavation |  | 47 |  | 100% | 74.57% |  | Excavation work Completed. Plinth work completed, RCC Slab, Brickwork, Internal Plaster upto 42 Floor, External Plaster upto 42 Floor, External Plumbing, Elevation and Waterproofing upto 38 Floor, Flooring & Fitting upto 38 Floor, Wooden Work upto 28 Floor, Electrical & Sanitary fittings upto 28 Floor Completed |  | Excavation in process | 23.5
Plinth |  | 47 |  | 100% |  |  |  |  | Excavation Completed | 47
RCC (Including podiums) |  | 48 |  | 100% |  |  |  |  | Footing in Process | 9.4
Brickwork |  | 47 |  | 100% |  |  |  |  | Footing Completed | 18.8
Internal Plaster |  | 42 |  | 89.36% |  |  |  |  | Basement 1 | 28.2
External Plaster |  | 42 |  | 89.36% |  |  |  |  | Basement 2 | 37.6
External Plumbing, Elevation and Waterproofing |  | 38 |  | 80.85% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 38 |  | 80.85% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 28 |  | 59.57% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 28 |  | 59.57% |  |  |  |  | Plinth completed | 47 | #VALUE!
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing A = 3B + G/St + 1st to 22nd Floor + Service Floor + 23rd to 50th Floor + Recreational Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 32 Slab, Brickwork upto 31 Floor, Internal Plaster upto 24.8 Floor, External Plaster upto 24.8 Floor Completed
|  |  |  | 3 | 1 |  | 0 | 50 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12.5
Excavation |  | 50 |  | 100% | 56.27% |  | Excavation work Completed. Plinth work completed, RCC upto 32 Slab, Brickwork upto 31 Floor, Internal Plaster upto 24.8 Floor, External Plaster upto 24.8 Floor Completed |  | Excavation in process | 25
Plinth |  | 50 |  | 100% |  |  |  |  | Excavation Completed | 50
RCC (Including podiums) |  | 32 |  | 62.75% |  |  |  |  | Footing in Process | 10
Brickwork |  | 31 |  | 62% |  |  |  |  | Footing Completed | 20
Internal Plaster |  | 24.8 |  | 49.6% |  |  |  |  | Basement 1 | 30
External Plaster |  | 24.8 |  | 49.6% |  |  |  |  | Basement 2 | 40
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 50
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Construction Status
Wing B = 3B + G/St + 1st to 22nd Floor + Service Floor + 23rd to 50th Floor + Recreational Floor. |  |  | : | Basement | Ground |  | Podium | Floors | Excavation work Completed. Plinth work completed, RCC upto 30 Slab, Brickwork upto 29 Floor, Internal Plaster upto 23.2 Floor, External Plaster upto 23.2 Floor Completed
|  |  |  | 3 | 1 |  | 0 | 50 | All work Completed. OC Received.
Type of Work |  | Slab/Floor |  | Complition % | Progress % |  | Stage of construction: |  | Piling Work in process | 12.5
Excavation |  | 50 |  | 100% | 54.93% |  | Excavation work Completed. Plinth work completed, RCC upto 30 Slab, Brickwork upto 29 Floor, Internal Plaster upto 23.2 Floor, External Plaster upto 23.2 Floor Completed |  | Excavation in process | 25
Plinth |  | 50 |  | 100% |  |  |  |  | Excavation Completed | 50
RCC (Including podiums) |  | 30 |  | 58.82% |  |  |  |  | Footing in Process | 10
Brickwork |  | 29 |  | 58% |  |  |  |  | Footing Completed | 20
Internal Plaster |  | 23.2 |  | 46.4% |  |  |  |  | Basement 1 | 30
External Plaster |  | 23.2 |  | 46.4% |  |  |  |  | Basement 2 | 40
External Plumbing, Elevation and Waterproofing |  | 0 |  | 0% |  |  |  |  | Basement 3 | 0
Flooring & Fitting |  | 0 |  | 0% |  |  |  |  | Basement 4 | 0
Wooden Work |  | 0 |  | 0% |  |  |  |  | Plinth in process | 0
Electrical & Sanitary fittings |  | 0 |  | 0% |  |  |  |  | Plinth completed | 50
Building Common Amenities |  | 0 |  | 0%
Possession |  | 0 |  | 0%
Project Completion % | [6 empty] | 74.15%
PSF Rates & Other Charges
Measurement Unit of Area (Sq. Ft./Sq. Mt.) |  |  | : | Sq. Ft | Type of Saleable Area (CA/BUA/SBA) | : | On Carpet area
Rate of Flat Per Sq. Ft. (on Carpet area) |  |  | : : | 17000/- | Floor Rise Per Sq. Ft. (on Carpet area) | : | NA
Car Parking Charges |  |  | : | 6,00,000/- | Other Charges | : | As applicable and documented.
PLC Charges |  |  | : | 215100/- | Club House Charges | : | 150000/-
Maintenance charges for 12 months Per Sq. Ft. (on Carpet area) |  |  | : | 75.07/- | Township for 3 Year Per Sq. Ft. (on Carpet area) | : | 25.02/-
Legal Charges |  |  | : | 25000/- | Corpus Amount | : | 25000/-
Water & Electricity Charges |  |  | : | 75000/- | Car Parking Charges | : | 5,00,000/-
Gas Connection Charges |  |  | : | - | GST | : | -
Other Charges |  |  | : |  | Other Charges | : | -
Guideline Values
Government Guideline/ Circle rate for Land (Rs per sqft) | [5 empty] | : | 3632.4786
Government Guideline/ Circle rate for Flat/Unit/ Built up (Rs per sqft) | [5 empty] | : | 10832.4043
Distress Value (Rs. Per sqft) | [5 empty] | : | 2905.9829
Unit Details, Nomenclature and Area Details
Building & Wing |  | Sale / Rehab |  | Flats/ Shops/ Offices | No. of Unit |  | Total Carpet Area | Total Saleable Area
A Wing |  | Sale |  | Flats | 352 |  | 224291.1902 | 358865.9044
B Wing |  | Sale |  | Flats | 352 |  | 217431.5083 | 347890.4133
Total |  | Sale |  | Flats | 704 |  | 441722.6986 | 706756.3177
Details of Flats in Building
Floor |  | Flat/Shop No. |  | Description | Gross Carpet area |  | Attached Terrace area | Saleable area Loading :
60%
A Wing
1st to 3rd Basement Floor For Parking
Ground Floor For Parking
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 25th, 27th to 30th, 32nd to 35th, 37th to 40th & 42nd to 45th Floor
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 25th, 27th to 30th, 32nd to 35th, 37th to 40th & 42nd to 45th Floor |  | 1 |  | 2BHK | 650.1456 |  | 0 | 1040.233 | 55.6137
|  | 2 |  | 1BHK | 457.3624 |  | 0 | 731.7798 | 16530.6525
|  | 3 |  | 1BHK | 447.5671 |  | 0 | 716.1074
|  | 4 |  | 2BHK | 663.7082 |  | 0 | 1061.9332
|  | 5 |  | 2BHK | 667.7986 |  | 0 | 1068.4777
|  | 6 |  | 3BHK | 861.6582 |  | 0 | 1378.6531 | 20773.8985
|  | 7 |  | 2BHK | 665.4305 |  | 0 | 1064.6888
|  | 8 |  | 2BHK | 650.1456 |  | 0 | 1040.233
7th, 12th, 17th, 22nd, 26th, 31st, 36th & 41th Floor (Part Refuge Area)
7th, 12th, 17th, 22nd, 26th, 31st, 36th & 41th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 650.1456 |  | 0 | 1040.233 | 58.6637
|  | 2 |  | 1BHK | 457.3624 |  | 0 | 731.7798
|  | 3 |  | Refuge Area
|  | 4 |  | 2BHK | 663.7082 |  | 0 | 1061.9332
|  | 5 |  | 2BHK | 667.7986 |  | 0 | 1068.4777
|  | 6 |  | 3BHK | 861.6582 |  | 0 | 1378.6531
|  | 7 |  | 2BHK | 665.4305 |  | 0 | 1064.6888
|  | 8 |  | 2BHK | 650.1456 |  | 0 | 1040.233
Service Floor (Above 22nd Floor)
Recreational Floor
B Wing
1st to 3rd Basement Floor For Parking
Ground Floor For Parking | [9 empty] | 48.8442
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 25th, 27th to 30th, 32nd to 35th, 37th to 40th & 42nd to 45th Floor
1st to 6th, 8th to 11th, 13th to 16th, 18th to 21st, 23rd to 25th, 27th to 30th, 32nd to 35th, 37th to 40th & 42nd to 45th Floor |  | 1 |  | 2BHK | 626.0342 |  | 0 | 1001.6548 | 55.1142
|  | 2 |  | 1BHK | 447.5671 |  | 0 | 716.1074 | 16530.6525
|  | 3 |  | 1BHK | 457.3624 |  | 0 | 731.7798
|  | 4 |  | 2BHK | 612.4716 |  | 0 | 979.9546
|  | 5 |  | 2BHK | 612.4716 |  | 0 | 979.9546
|  | 6 |  | 2BHK | 665.4305 |  | 0 | 1064.6888
|  | 7 |  | 3BHK | 861.6582 |  | 0 | 1378.6531
|  | 8 |  | 2BHK | 630.1246 |  | 0 | 1008.1993
7th, 12th, 17th, 22nd, 26th, 31st, 36th & 41th Floor (Part Refuge Area)
7th, 12th, 17th, 22nd, 26th, 31st, 36th & 41th Floor (Part Refuge Area) |  | 1 |  | 2BHK | 626.0342 |  | 0 | 1001.6548 | 58.6637
|  | 2 |  | 1BHK | 447.5671 |  | 0 | 716.1074
|  | 3 |  | Refuge Area
|  | 4 |  | 2BHK | 612.4716 |  | 0 | 979.9546
|  | 5 |  | 2BHK | 612.4716 |  | 0 | 979.9546
|  | 6 |  | 2BHK | 665.4305 |  | 0 | 1064.6888
|  | 7 |  | 3BHK | 861.6582 |  | 0 | 1378.6531
|  | 8 |  | 2BHK | 630.1246 |  | 0 | 1008.1993
Service Floor (Above 22nd Floor)
Recreational Floor
Project Specific Remarks & Observation
Remarks / Observations | : | 1. Construction work is in process at the time of Visit. Internal Visit was not allowed. 2. We considered Saleable area as per our calculation. 3. We considered Carpet area as per Approved Plan. 4. We considered Gross carpet area = Net carpet + Balcony + Utility Area + C.B Area. 5. We have considered rate by verifying it from market inquire. 6. Car parking is subjected to authentic documentation. 7. Please check for Fire Noc & EC. 8. Please provide revised approved plans & CC.
Site & Building/Tower Photographs
Name of the Project |  |  | : | Rustomjee La Familia A & B Wing (Rustomjee Urbania)
Project Site Address |  |  | : | Rustomjee Urbania, Eastern Express Hwy, Majiwada, Junction, Thane West, Mumbai, Maharashtra 400601
Site Visit Date & Time |  |  | : | 15/09/2025 @ 02:00PM
Location Cum Root Map (Satelite View)
Valuer Certification/Disclaimer
I certify that to the best of my knowledge and belief:
The statements of fact contained in this report are true and correct.
The reported analyses, opinion and conclusions are limited only by the reported assumptions and limiting conditions, and are my personal, impartial, and unbiased professional analyses, opinions and conclusions.
I have no present or prospective interest in the property that is the subject of this report, and I have no personal interest with respect to the parties involved.
I have no bias with respect to the property that is the subject of this report or to the parties involved with this assignment.
My engagement in this assignment was not contingent upon developing or reporting predetermined results.
My compensation for completing this assignment is not contingent upon the reporting of predetermined value or direction in value that favours the cause of the client, the amount of the value opinion, the attainment of a stipulated result, or the occurrence of a subsequent event directly related to the intended use of this appraisal.
I have not made a personal inspection of the property that is the subject of this report. My valuation executive (valuer code above) has undertaken the inspection of the property that is the subject of this report.
No one has provided significant mass appraisal assistance to the person signing this certification.
Name of Engineer Visited the property |  |  | : | Mr.Ajay Songare | Authorized Signatory Name & Signature | :
C
B
A
Wing A
Wing B
Wing C
Rustomjee La Familia
Wing C
Wing C
Wing B
Wing A
Wing A