## Report
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  | 02/09/2025 | [5 empty] | Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Sammaan Capital Limited | ABFHL
Bank Name: |  |  |  | Sammaan Capital Limited | [5 empty] | Branch | Axis Goregaon | PNB Thane | Cent Kalyan | SCL Kalyan
CPC Name: |  |  |  | SCL Thane | [6 empty] | Axis Thane | PNB Borivali | Cent Belapur | SCL Badlapur
Date Of Property Visit |  |  |  | 2025-09-01 | [6 empty] | Axis Sanpada | PNB Panvel |  | SCL Vashi
Name of the builder group |  |  |  | Aditya Realtors | [6 empty] | Axis Badlapur |  |  | SCL Vashi
Name of the builder company |  |  |  | Aditya Realtors | [9 empty] | SCL Thane
Name of the Project |  |  |  | AV Smart City Phase 1 | [9 empty] | SCL Andheri
Provided Contact Details (Name & Contact No.) |  |  |  | Jayram Sahu : 9960850977 | [9 empty] | SCL Borivali
Site Person - Contact Details (Name & Contact No.) |  |  |  | NA | [9 empty] | SCL Virar
Name / No of the Building |  |  |  | Building No.1 (Type A & B) Building No.2 (Type C) Building No.3 (Type D) Building No.4 (Type C1) Building No.5 (Type D1)
Name / No of the Existing Building | [16 empty] | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | #VALUE!
Documents Provided |  |  |  | Approved Plans, CC | [12 empty] | Thane | Mokhada | Andheri | Alibag | Pune City
RERA No. |  |  |  | P99000050740 |  |  |  | #N/A | [8 empty] | Shahpur | Talasari | Borivali | Panvel | Haveli
Project location details |  | AV Smart City Phase 1, Survey No.1023/8 (Old S.No.1023/1 + 2/4), near Gayatri Park, Haranwadi Road, Haranwadi, Mahim, Palghar (West), Palghar, Palghar - 401404. | [14 empty] | Kalyan | Vasai | Kurla | Uran | Khed
Survey No |  | 1023/8 (Old S.No.1023/1 + 2/4) | [14 empty] | Bhiwandi | Vikramgad | Mumbai | Karjat | Baramati
Locality |  | Haranwadi | [14 empty] | Ulhasnagar | Palghar |  | Khalapur | Junnar
Road |  | Haranwadi Road |  | Locality/Village |  | Mahim | [10 empty] | Ambernath | Dahanu |  | Pen | Shirur
City |  | Palghar (West) |  | District |  | Palghar | [10 empty] | Murbad | Wada |  | Sudhagad | Indapur
Taluka |  | Palghar |  | Pin Code |  | 401404 | [13 empty] | Mahad | Daund
Nearby Landmark |  | Gayatri Park |  | Distance from city centre: |  | 5.0 KM from Palghar Railway Station | [13 empty] | Roha | Mawal
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market, etc.) |  |  |  | all available at 1 to 2 km. | [15 empty] | Mangaon | Ambegaon
[20 empty] | Poladpur | Purandhar
Does property have Electricity / Water / Drainage Connection |  |  |  | Yes | [15 empty] | Mahasala | Bhor
Class of locality |  |  |  | Middle Class | [15 empty] | Shriwardhan | Mulshi
Nature of land with topographical condtion |  |  |  | Plane | [15 empty] | Murud | Velhe
Nature of the locality |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  | Good
Type of Structure |  |  |  | RCC Frame Structure
Approved usage of the Property: |  |  |  | Residential + Commercial
Restrictive Covenants in regard to Land Use |  |  |  | No
Boundries |  | As per Layout |  |  | At site | [11 empty] | #VALUE!
East | NA | Adj. H. No. 1+2/5 |  |  | Other Plot
West | NA | Adj. H. No. 1+2/3 |  |  | Other Plot
North | NA | Other Plot |  |  | Other Plot
South | NA | 18 M.W. Road |  |  | Haranwadi Road
Does the boundaries at site match, as mentioned in the Documentation: NA
Latitude, Longitude |  | 19.6755884,72.7400386
Location Link |  | https://maps.app.goo.gl/47nTgTmECZUvydkP7
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  | 11340.81
Permissible FSI |  |  |  | 1
Permissible TDR/Paid FSI |  |  |  | 0.59838
Total FSI availaible for the project |  |  |  | 1.5984
Total Approved Builtup area of the project (Sq.Mt) |  |  |  | 18126.96
Total number of Buildings |  |  |  | 06 Buildings
Approval Detail : Plan approval
Name of Municipal Corporation/Authority |  | Palghar Muncipal Council | [13 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Layout Approval No |  | MHSL/K-1/MJ1/BSP/SR/CR/121/2022 |  |  | Dated | 2023-01-03 | [10 empty] | Slum Rehabilitation Authority (SRA) | Navi Mumbai Municipal Corporation (NMMC) | Panvel Municipal Corporation | Vasai-Virar City Municipal Corporation. (VVCMC)
Approved Floor plan No. |  | MHSL/K-1/MJ1/BSP/SR/CR/121/2022 |  |  | Dated | 2023-01-03 | [10 empty] | Municipal Corporation of Greater Mumbai (MCGM) | Thane Municipal Corporation (TMC) | City and Industrial Development Corporation (CIDCO) | Collector Of Palghar
Commencement-CC No Valid Up to: |  | MHSL/KS-1/T1/NAP/SR-121/2021 |  |  | Dated | 2023-01-03 |  | NO REMARK | [8 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
Building No.1 (Type A & B) = Gr + 1st to 7th Floor Building No.2 (Type C) = Gr + 1st to 7th Floor Building No.3 (Type D) = Gr + 1st to 7th Floor Building No.4 (Type C1) = Gr + 1st to 7th Floor Building No.5 (Type D1) = Gr + 1st to 7th Floor Building No.6 (Type E) = Gr + 1st Floor Building No.7, 8 & 9 (Type E & E1) = Gr + 1st Floor (Total BUA = 18126.96 Sq.M)
Fire Noc No Valid Up to: |  | #REF! |  |  | Dated |  |  |  |  | 2019-01-03 | NO REMARK | [5 empty] | Maharashtra Housing and Area Development Authority(MHADA) | Kalyan Dombivli Municipal Corporation (KMDC) | Maharashtra State Road Development Corporation Limited (MSRDC) | Town Planner, Palghar
[17 empty] | Maharashtra State Road Development Corporation Limited (MSRDC) | Kulgoan Badlapur Municipal Council | Pen Municipal Council
Environmental Clearance Certificate (EC) No Valid Up for: |  | 0 |  |  | Dated | 0 | [11 empty] | Town Planning Thane | Raigad Zilha Parishad
[18 empty] | Ulhasnagar Municipal Corporation | Roha Municipal Council
Airport Noc No Valid Up for: |  |  |  |  | Dated | [12 empty] | Nagar Rachana Ani Mulya Nirdharan Vibhag Thane | Collector Of Raigad
[5 empty] | Valid upto Dated | [12 empty] | Bhiwandi Nizampur City Municipal Corporation
Site Elevation (AMSL) = Permissible Top Elevation (AMSL) =
O. Certificate No.: |  | NA Approved upto : NA |  |  | Dated | NA | [11 empty] | Maharashtra Industrial Development Corporation (MIDC)
Building wise Construction details | [17 empty] | Mira-Bhayandar Municipal Corporation
Approved area of building (Sq.Mt) (Building No.1 to 5) |  |  | 17265.82
Approved no of units |  |  | Flats - 348, Shops - 55
Approved no of Floors |  |  | Building No.1 (Type A & B) = Gr + 1st to 7th Floor Building No.2 (Type C) = Gr + 1st to 7th Floor Building No.3 (Type D) = Gr + 1st to 7th Floor Building No.4 (Type C1) = Gr + 1st to 7th Floor Building No.5 (Type D1) = Gr + 1st to 7th Floor
Proposed no of Floors |  |  | Building No.1 (Type A) = Gr + 1st to 7th Floor
Building No.1 (Type B) = Gr + 1st to 7th Floor
Building No.2 (Type C) = Gr + 1st to 7th Floor
Building No.3 (Type D) = Gr + 1st to 7th Floor
Building No.4 (Type C1) = Gr + 1st to 7th Floor
Building No.5 (Type D1) = Gr + 1st to 7th Floor
Expected Completion |  |  | As per RERA - 31/12/2027
Projected life of the structure |  |  | 60 Years After Completion
Quality of construction: |  |  | Good
Proposed Amenities : |  |  | Gymnasium, Club House, Swimming Pool, Indoor Game, Banquet Hall, Kids Play Area, Automated Vehicle Entry, EV Charging Station, 24 Power Backup, etc.
Violations Observed if any : |  |  | NA
Material laying at Site: |  |  | Cement, Aggregate, Steel, etc
Wheather the construction is as per approved Building plan : |  |  | Under Construction |  | Under Construction
Construction details: |  | Building No.1 (Type A) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 4 Floor, External Plaster upto 3 Floor Completed | , Internal Plaster upto 4 Floor, External Plaster upto 3 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork Completed, Internal Plaster upto 4 Floor, External Plaster upto 3 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 66.07% |  | 85% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 4 | 57.14% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 3 | 42.86% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.1 (Type B) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed, RCC upto 5 Slab, Brickwork upto 4 Floor Completed | , RCC upto 5 Slab, Brickwork upto 4 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed, RCC upto 5 Slab, Brickwork upto 4 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 39.29% |  | 66.61% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 5 | 62.5% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 4 | 57.14% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.2 (Type C) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth Completed
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth
Stage of construction: |  | Excavation, Plinth Completed | [5 empty] | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 10% |  | 45% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.3 (Type D) = Gr + 1st to 7th Floor | [5 empty] | Work not yet Started.
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 |  | Work not yet Started.
Stage of construction: |  | Work not yet Started.
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 0 | 0% | 0% |  | 0% |  | Excavation in process | 3.5
Plinth |  | 0 | 0% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 0 | 0% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 0 | 0% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 0 | 0% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.4 (Type C1) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 6 Floor Completed | , Painting upto 6 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster, External Plaster, Flooring Completed, Painting upto 6 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 89.29% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 6 | 85.71% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Construction details: |  | Building No.5 (Type D1) = Gr + 1st to 7th Floor | [5 empty] | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5 Floor Completed | , External Plaster upto 5 Floor
Basement | 0 | Ground | 1 | Podium | 0 | Floors | 7 | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster
Stage of construction: |  | Excavation, Plinth, RCC Slab, Brickwork, Internal Plaster Completed, External Plaster upto 5 Floor Completed | [5 empty] | Completed | Completed
Type of Work |  | Slab/Floor | Complition % | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% | 72.14% |  | 88.57% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% |  |  |  |  | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% |  |  |  |  | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% |  |  |  |  | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 5 | 71.43% |  |  |  |  | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 0 | 0% |  |  |  |  | Basement 3 | 0
Painting & Wooden |  | 0 | 0% |  |  |  |  | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 0 | 0% |  |  |  |  | Plinth in process | 5.25
Possession |  | 0 | 0% |  |  |  |  | Plinth completed | 7
Recommended Rates of the Property : |  |  |  |  | On Saleable Area | [10 empty] | Authorites | Mumbai | Thane | Raigad | Palghar
Recommended rate of the Flat Per Sq. Ft. |  |  |  |  | 4000 | [11 empty] | 800000 | 150000 | 100000 | 100000
Recommended rate of the Shop Per Sq. Ft. |  |  |  |  | 6000 | [11 empty] | 900000 | 200000 | 150000 | 150000
Recommended rate of the Office Per Sq. Ft. | [16 empty] | 1000000 | 250000 | 200000 | 200000
Floor Rise Rate from Floor | [16 empty] | 1100000 | 300000 | 250000 | 250000
Development Charges | [16 empty] | 1200000 | 350000 | 300000 | 300000
Club Charges | [16 empty] | 1300000 | 400000 | 350000 | 400000
Gas Connection Charges | [16 empty] | 1400000 | 500000 | 400000
Water, Electricity, Drainages, Sewerage Connection | [16 empty] | 1500000 | 600000 | 500000
Society Formation Charges | [16 empty] | 1600000 | 700000 | 600000
Advance Maintenance Charges | [16 empty] | 1700000 | 800000
Recommended rate of Parking |  |  |  |  | 100000 | [11 empty] | 1800000 | 900000
Distressed valuation of the Property |  |  |  |  | 3200 | [12 empty] | 1000000
Commercial Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 (Type A) |  | 20 |  | 3102.1848 |  | 4653.2772
Building No.1 (Type B) |  | 9 |  | 1378.4378 |  | 2067.6568
Building No.2 (Type C) |  | 13 |  | 2007.2707 |  | 3010.9061
Building No.4 (Type C1) |  | 13 |  | 2007.3784 |  | 3011.0675
Total |  | 55 |  | 8495.2717 |  | 12742.9076
Residential Area Details :
Building & Wing |  | No. of Units |  | Total Carpet Area |  | Total Saleable Area
Building No.1 (Type A) |  | 58 |  | 21135.3293 |  | 31390.3899
Building No.1 (Type B) |  | 58 |  | 21135.3293 |  | 31197.4793
Building No.2 (Type C) |  | 58 |  | 21135.3293 |  | 31238.8825
Building No.3 (Type D) |  | 58 |  | 21135.3293 |  | 30980.6757
Building No.4 (Type C1) |  | 58 |  | 21135.3293 |  | 31217.4595
Building No.5 (Type D1) |  | 58 |  | 21135.3293 |  | 30961.949
Total |  | 348 |  | 126811.9757 |  | 186986.836
Grand Total |  | 403 |  | 135307.2474 |  | 199729.7435
Building Details Floor Wise
Details of Residential & Commercials in Building
Shop No. (Approved Plan) | Shop No. (Sale Plan) | Description | Carpet area | Attached Loft area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
50%
Building No.1 (Type A)
Ground Floor For Commercial, Meter Room & Parking
10 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
11 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
12 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
13 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
14 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
15 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
16 |  | Shop | 131.9666 | 0 | 131.9666 | 0 | 197.95
17 |  | Shop | 113.1296 | 0 | 113.1296 | 0 | 169.6945
18 |  | Shop | 205.0542 | 0 | 205.0542 | 0 | 307.5813
19 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
20 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
21 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
22 |  | Shop | 131.9666 | 0 | 131.9666 | 0 | 197.95
23 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
24 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
25 |  | Shop | 114.8519 | 0 | 114.8519 | 0 | 172.2778
26 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
27 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
28 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
29 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
Building No.1 (Type B)
Ground Floor For Commercial, Society Office, Driver Room, Meter Room & Parking
1 |  | Shop | 171.2552 | 0 | 171.2552 | 0 | 256.8829
2 |  | Shop | 113.1296 | 0 | 113.1296 | 0 | 169.6945
3 |  | Shop | 131.9666 | 0 | 131.9666 | 0 | 197.95
4 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
5 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
6 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
7 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
8 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
9 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
Building No.2 (Type C)
Ground Floor For Commercial, Meter Room & Parking
1 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
2 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
3 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
4 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
5 |  | Shop | 114.8519 | 0 | 114.8519 | 0 | 172.2778
6 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
7 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
8 |  | Shop | 131.9666 | 0 | 131.9666 | 0 | 197.95
9 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
10 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
11 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
12 |  | Shop | 144.3452 | 0 | 144.3452 | 0 | 216.5179
13 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
Building No.4 (Type C1)
Ground Floor For Commercial, Meter Room & Parking
1 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
2 |  | Shop | 144.3452 | 0 | 144.3452 | 0 | 216.5179
3 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
4 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
5 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
6 |  | Shop | 132.0743 | 0 | 132.0743 | 0 | 198.1114
7 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
8 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
9 |  | Shop | 114.8519 | 0 | 114.8519 | 0 | 172.2778
10 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
11 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
12 |  | Shop | 135.0882 | 0 | 135.0882 | 0 | 202.6323
13 |  | Shop | 172.9775 | 0 | 172.9775 | 0 | 259.4662
Flat No. (Approved Plan) | Flat No. (Sale Plan) | Description | Carpet area | Fungible area | Gross Carpet area | Attached Terrace area | Saleable area Loading :
45%
Building No.1 (Type A)
1st Floor for Residential
1 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
2 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
3 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 133.1238 | 548.3747
4 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 44.8859 | 749.1098
5 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 73.7334 | 539.7823
6 |  | 1BHK | 311.5102 | 21.3127 | 332.8229 | 132.6986 | 548.9425
7 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 79.9388 | 545.9878
8 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 312.9794 | 543.6695
9 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
2nd to 6th Floor
1 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
2 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
3 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
4 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
5 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
6 |  | 1BHK | 311.5102 | 21.3127 | 332.8229 | 0 | 482.5932
7 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
8 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
9 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
7th Floor (Part Terrace Area)
1 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 346.9237 | 790.9549
2 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 346.9237 | 790.9549
3 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 334.4752 | 549.6677
4 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 309.4704 | 543.4165
Building No.1 (Type B)
1st Floor for Residential
1 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
2 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 323.8909 | 546.3973
3 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 84.196 | 550.2449
4 |  | 1BHK | 311.5102 | 21.3127 | 332.8229 | 51.6349 | 534.2281
5 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
6 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
7 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
8 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
9 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
2nd to 6th Floor
1 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
2 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
3 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
4 |  | 1BHK | 311.5102 | 21.3127 | 332.8229 | 0 | 482.5932
5 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
6 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
7 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
8 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
9 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
7th Floor (Part Terrace Area)
1 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 309.4704 | 543.4165
2 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 334.4752 | 549.6677
3 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 346.9237 | 790.9549
4 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 346.9237 | 790.9549
Building No.2 (Type C)
1st Floor for Residential
101 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
102 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
103 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
104 |  | 1BHK | 311.5102 | 21.3127 | 332.8229 | 134.8299 | 550.0081
105 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 81.5804 | 547.6293
106 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 41.2907 | 745.5146
107 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 130.9118 | 547.2687
108 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
109 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
2nd to 6th Floor
1 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
2 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
3 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
4 |  | 1BHK | 311.5102 | 21.3127 | 332.8229 | 0 | 482.5932
5 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
6 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
7 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
8 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
9 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
7th Floor (Part Terrace Area)
1 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 320.9825 | 546.2945
2 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 332.8229 | 549.2546
3 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 346.9237 | 790.9549
4 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 346.9237 | 790.9549
Building No.3 (Type D)
Ground Floor For Driver Room, Meter Room, Society Office & Parking
1st to 6th Floor for Residential
1 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
2 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
3 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
4 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
5 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
6 |  | 1BHK | 311.5102 | 21.3127 | 332.8229 | 0 | 482.5932
7 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
8 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
9 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
7th Floor (Part Terrace Area)
1 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 346.9237 | 790.9549
2 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 346.9237 | 790.9549
3 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 334.4752 | 549.6677
4 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 309.4704 | 543.4165
Building No.4 (Type C1)
1st Floor for Residential
1 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
2 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
3 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 125.519 | 544.5723
4 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 41.2907 | 745.5146
5 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 81.5804 | 547.6293
6 |  | 1BHK | 311.5102 | 21.3127 | 332.8229 | 134.8299 | 550.0081
7 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
8 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
9 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
2nd to 6th Floor
1 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
2 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
3 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
4 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
5 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
6 |  | 1BHK | 311.5102 | 21.3127 | 332.8229 | 0 | 482.5932
7 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
8 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
9 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
7th Floor (Part Terrace Area)
1 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 309.4704 | 781.5915
2 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 309.4704 | 781.5915
3 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 332.8229 | 549.2546
4 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 320.9825 | 546.2945
Building No.5 (Type D1)
Ground Floor For Driver Room, Meter Room, Society Office & Parking
1st to 6th Floor for Residential
1 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
2 |  | 1BHK | 298.0552 | 22.9273 | 320.9825 | 0 | 465.4246
3 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
4 |  | 1BHK | 311.5102 | 21.3127 | 332.8229 | 0 | 482.5932
5 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 0 | 466.0489
6 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
7 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
8 |  | 1BHK | 309.3574 | 22.9273 | 332.2847 | 0 | 481.8128
9 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 0 | 704.2239
7th Floor (Part Terrace Area)
1 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 309.4704 | 543.4165
2 |  | 1BHK | 298.4857 | 22.9273 | 321.413 | 334.4752 | 549.6677
3 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 309.4704 | 781.5915
4 |  | 1.5BHK | 462.7444 | 22.9273 | 485.6717 | 309.4704 | 781.5915
2nd Floor
201 |  |  |  | 0 | 0 | 0 | 0
202 |  |  |  | 0 | 0 | 0 | 0
203 |  |  |  | 0 | 0 | 0 | 0
204 |  |  |  | 0 | 0 | 0 | 0
205 |  |  |  | 0 | 0 | 0 | 0
3rd, 5th, 7th, 9th, 11th, 13th, 15th Floor
301 ,.., 1501 |  |  |  | 0 | 0 | 0 | 0
302 ,.., 1502 |  |  |  | 0 | 0 | 0 | 0
303 ,.., 1503 |  |  |  | 0 | 0 | 0 | 0
304 ,.., 1504 |  |  |  | 0 | 0 | 0 | 0
305 ,.., 1505 |  |  |  | 0 | 0 | 0 | 0
2nd to 5th Floor
201 to 501 |  |  |  | 0 | 0 | 0 | 0
202 to 502 |  |  |  | 0 | 0 | 0 | 0
203 to 503 |  |  |  | 0 | 0 | 0 | 0
204 to 504 |  |  |  | 0 | 0 | 0 | 0
205 to 505 |  |  |  | 0 | 0 | 0 | 0
2nd & 5th Floor
201 & 501 |  |  |  | 0 | 0 | 0 | 0
202 & 502 |  |  |  | 0 | 0 | 0 | 0
203 & 503 |  |  |  | 0 | 0 | 0 | 0
204 & 504 |  |  |  | 0 | 0 | 0 | 0
205 & 505 |  |  |  | 0 | 0 | 0 | 0
Remarks:
* | Building No.1 (Type A & B) Building No.2 (Type C) Building No.4 (Type C1) Building No.5 (Type D1) |  |  | Construction work is in process at the time of visit.
| Building No.3 (Type D) |  |  | Work not yet started.
* | We have considered Saleable area of Flats as per our Calculation.
* | We have considered Saleable area of Commercial as per our Calculation.
* | We considered Carpet area as per Approved Plan.
* | We considered Gross carpet area = Net carpet + D.B Area.
* | We have considered proposed No. of Floor for Stage Calculation.
* | We have considered rate by verifying it from market inquire.
* | Recommended rate should be considered as all inclusive rate if other charges are not mentioned. (Excluding GST & other government Taxes)
* | Car parking is subjected to authentic documentation.
* | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
* | Please check for Environment Clearance Certificate, Fire NOC, Airport NOC, CRZ NOC, Railway Noc.
* | We have given Valuation for Sale Flats and Shops only.
* | NO REMARK FOR CC
* | There are guest houses, villas, resorts, etc. in a range of 200 to 300 meters. There are few residential buildings available in the surrounding areas. (within 500 meters) There are inadequate transportation options to get to the project and the area is not developed
* | As per bank request we have done APF for only Building No.1 to 5.
Undertaking :
1) We have personally visited the property & identified the same based on the documents provided.
2) I/We have no direct or Indirect Interest in the property being valued
3) The information furnished above is true and correct to my/our knowledge.
4) Legal title of the property is not verified by us.
5) Gross carpet area = Net Carpet area + Fungible area.
6) Fungible Area= Enclosed Balcony + Flower Bed + Covered Balcony + Service Slab + Duct + Chajja + Wheather Shed area.
Inspected By : |  | Harshad Pawade |  | Report By : |  | Pooja Kawale
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | AV Smart City Phase 1
Layout :
Google Map :
Formulas:
Mahim = [Mahim, row above]
Building No.9
Building No.8
Building No.7
Building No.6
E
E1
E
E
E1
E
E1
Building No.5 (Type D1)
Building No.4 (Type C1)
Building No.3 (Type D)
Building No.2 (Type C)
Building No.1 (Type B)
Building No.1 (Type A)
Type A
Note on E12: Sachin: Building No. Tower No. Wing Bunglow No., etc
Note on E13: Sachin: If exisiting Building is provided write it or else NA
Note on C55: SACHIN: Floor with height
Note on C57: SACHIN: Survey Nos.
Note on D63: Sachin: If multiple building in project or complex just mention builtup of required building
Note on F168: SACHIN: Other charges should be given on basis of location amenties builder type n should not exceed above 12 lakhs or 8% of flat value
Note on H262: SACHIN: Give loading of 50% for A Category

## valuation
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
Magic Brick |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
99 Acres |  |  |  | 0 | #DIV/0!
Average |  |  |  |  | #DIV/0!
Valuation Adopted

## Research
[6 empty] | 1 | 2
District | Thane | Palghar | Mumbai | Raigad | Pune | Raigad | Borivali
| Thane | Mokhada | Andheri | Alibag | Pune City
| Shahpur | Talasari | Borivali | Panvel | Haveli
| Kalyan | Vasai | Kurla | Uran | Khed
| Bhiwandi | Vikramgad |  | Karjat | Baramati
| Ulhasnagar | Palghar |  | Khalapur | Junnar
| Ambernath | Dahanu |  | Pen | Shirur
| Murbad | Wada |  | Sudhagad | Indapur
|  |  |  | Mahad | Daund
|  |  |  | Roha | Mawal
|  |  |  | Mangaon | Ambegaon
|  |  |  | Poladpur | Purandhar
|  |  |  | Mahasala | Bhor
|  |  |  | Shriwardhan | Mulshi
|  |  |  | Murud | Velhe
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
Approved Plans, CC
Approved Plans, CC, Sale Plans
Approved Plans, CC, Sale Plans, Builder Saleable Area
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet,
Approved Plans, CC, Builder Saleable Area,
Approved Plans, CC, Sale Plans, Builder Saleable Area, Cost Sheet, Airport Noc, Railway Noc, OC
[6 empty] | 1 | 2
Bank | Axis Bank | PNB Housing Finance Limited | Cent Bank | Indiabulls Housing Finance Ltd | ABFHL | Raigad | Borivali
Branch | Axis Goregaon | PNB Thane | Cent Kalyan | IBHF Kalyan
| Axis Thane | PNB Borivali | Cent Belapur | IBHF Badlapur
| Axis Sanpada |  |  | IBHF Vashi
| Axis Badlapur |  |  | IBHF Vashi
IBHF Thane
IBHF Andheri
Authorites
Mumbai | Slum Rehabilitation Authority (SRA)
Municipal Corporation of Greater Mumbai (MCGM)
Maharashtra Housing and Area Development Authority(MHADA)
Mumbai Metropolitan Region Development Authority (MMRDA)
Maharashtra State Road Development Corporation Limited (MSRDC)
Thane | Navi Mumbai Municipal Corporation (NMMC)
Thane Muncipal Cooperation (TMC)
Kalyan Dombivli Municipal Corporation (KMDC)
Ambernath Municipal Council (AMC)
Kulgoan Badlapur Municipal Council
Town Planning Thane
Ulhasnagar Municipal Corporation
Nagar Rachana Ani Mulya Nirdharan Vibhag Thane
Bhiwandi Nizampur City Municipal Corporation
Maharashtra Industrial Development Corporation (MIDC)
Mira-Bhayandar Municipal Corporation
Raigad | Panvel Municipal Corporation
City and Industrial Development Corporation (CIDCO)
Maharashtra State Road Development Corporation Limited (MSRDC)
Navi Mumbai Airport Influence Notified Area (NAINA)
Pen Municipal Council
Raigad Zilha Parishad
Roha Municipal Council
Palghar | Vasai-Virar City Municipal Corporation. (VVCMC)
Collector Of Palghar
Town Planner, Palghar

## Remarks
1 | As per RERA, completion period of project Yashwant Height is expired on 30/06/2021 but still project is under construction.
2 | Validity of CC is expired on 31/01/2021. Please provide latest CC.
3 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
4 | As per CRZ Norms, The said plot is coming under list of plots affected by CRZ. Ref Letter No. CIDCO/PLNG/ACP(BP)/2021/895/E-19416 Date : 09/03/2021.
5 | Construction work has increased from last visit but no active work was found during site visit
6 | As per Approved Floor plan, Wing A consist of 62 units ( Rehab = 40 units & Sale = 22 Units), but which unit no should be considered as rehab or sale is not mentioned in Approved plan.
7 | If stage is not identifibale due to external Visit, 1. Confirm with visitor that internal visit was possible or not, if internal visit possible ask visitor to to revisit 2. If internal visit not possible in category A Builders, if stage is not possible to increase mention below remark Since internal visit were not permitted, we were unable to determine building progress from an external visit; so, we are maintaining the same progress as in the previous report (dtd. ) 3. If Stage is identifiable increase the stage. Mention internal visit is not allowed in Remark
8 | Recommended Rates / Other charges of the Property have been revised on 23/10/2023.
9 | Other charges/ Rate has been revised as per market inquiry (on 12/10/2023)
10 | Cementry of Hindu, Muslim, & Christian Religion is located in 150 to 200m from project
11 | There is a road on the west side of the project, and a creek is next to the other side of the road.
12 | We have updated revised approved plans & CC (on 15/12/2022).
13 | High Tension lines are passing through project (name)
14 | Construction work is same as last visit but work is in process at the time of visit. (Slow Speed)
15 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan.
16 | Construction work was stopped since visit 04/12/2017, but during 07/10/2021 site visit some construction activity was seen on site (Single room flooring work was seen)
17 | Builder is selling Bare Shell Office units
18 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
19 | As building have received First CC on 08/05/2015 still building is still under construction.
20 | Since the project has received first CC on 17/01/2020, But construction work of Wing A is not yet started. Please provide revised approved CC for Wing A.
21 | We did not consider the terrace area attached to the 1st floor flats because it was not shown in the approved plans. However, it was shown in the sale plan.
22 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp A wing is a rehab wing, and B wing is a sale wing. The same letter is attached below.
23 | A sale or rehab statement is not provided along with approved floor plans. But as per a letter provided by the Bank Official on whatsapp, 5 shops & 6 Flats are Rehab Flats. The same letter is attached below.
24 | High tension lines are passing nearby project Project Name. Please provide Power Noc.
25 | As Flat No. 201, 202, 203 & 204 consists of large terrace area but dimension of that area is not mentioned. Therefore we have not considered terrace area for that flat.
26 | Electric Lines are passing above the project
27 | We have release report on the basis of other vendor report.
28 | As per the last site visit dtd. 06/03/2024, internal visit was not allowed. Hence, the construction percentage given in the report was as per site met person i.e. 1st slab completed. As per the visit dtd 10/06/2024, we have observed that only plinth work is completed. But higher construction stage is already given in last report i.e. 1st slab completed Hence, we are maintaining the same construction percentage as of previous report.
29 | Recommended Rates / Other charges of the Property (Commercial) have been revised on 23/10/2023 on basis of Cost sheet provided to us on mail by bank official, which is attached below
30 | Provided plans doesnot consist of Owner & Architect Signature, We are releasing report after verbel discussion with Bank Officials about above Query.
31 | We have not drafted Unit No. 4, Office No. 107, 207, 307 & 407 due to improper dimentions n shape of that unit.
32 | We are releasing report on MIDC Approved plans & Combined Approval Letter.
33 | As the project is redevelopement project but rehab statement or rehab flats is not mentioned approved layout plan & floor plan. But builder rehab tenant list is provided on mail by bank officials which is attached below
34 | As per Approved Floor Plan, In C to E wing on Ground floor Shop No. 19 & 20 are merged into single shop.
35 | There are guest houses, villas, resorts, etc. in a range of 200 to 300 meters. There are few residential buildings available in the surrounding areas. (within 500 meters) There are inadequate transportation options to get to the project and the area is not developed
36 | The project is not registered on RERA site, Beacause land area of project is less than 500 Sq.Mt
37 | Construction stage is reduced due to revision in proposed structure of project.
38 | Construction percentage has been reduced due to the construction work being processed in two parts.
39 | The project has received CC on 07/06/2019, But construction work is not yet Completed.
40 | Some flats are occupied by tenants but finishing work is in process at the time of visit.
41 | As per site visit dtd.23/01/2025 we have observed that the construction work is not done as per approved floor plan. (Extra Terrace Area are Constructed for flats) According to the approved 1st floor plan, terrace area is not attached to Flat No.3, 4 & 5, But on site terrace area is already constructed.
42 | As per approved plan & CC, project consists of Survey No.40, H.No.2A, Plot No.3 & 4. But as per RERA, project consists of Survey No.40/B, Plot No.3 & 4. | Vishw apartment
43 | Remark No. 42 is resolved by corrigendum (i.e. correction letter) provided by authority regarding survey nos. letter attached below.
44 | As per approved Floor plans does not consist of Unit Numbering, We have considered unit numbering from sale plan provided by site meet person during site visit.
45 | As per New version of RERA portal project consist of single building - Hasha Heights As per Old version of RERA portal project consist of Two buildings- Hasha Heights & Kunti Heights
46 | Remark No.11 is solved. we were asked to follow the old version of RERA by the bank official builder letter provided on the mail is attached below.
47 | The approved large land parcel layout plan does not consist of survey number, therefore we have referred Survey No. from Title Certificate.
48 | As per the discussion with the bank official, Builder provided approved EC on whatsapp for a large land parcel.
49 | As per the approved floor plan, out of 1199 flats, there are 132 flats that are "I to R" flats. Please check from your end. | Mahindra Vista Phase 1 & 2
50 | As per the approved plans & RERA in the project Shikara Heights Phase I consist of " Wing A, B, C " for Sale & " Wing D " for Rehab Therefore we have not considered Rehab Wing D in APF Report.
Note on C9: SACHIN: If banker changes the rate
Note on C10: SACHIN: If we change the rate

## Area Calculation
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
|  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 | Balcony |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 | CB |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed3 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed4 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Servant room |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0