## Report (2)
Office No. 1031, Wing J, Akshar Business Park, Plot No. 03 Sector 25, Near APMC Market, Vashi, Navi Mumbai, Maharashtra 400703 TEL: 022-46090378/79/80 E mail : vsjcapf@gmail.com. Web site : www.vsjadon.com
Valuation Report
Date: |  |  |  |  | 30/08/2025
CPC Name: |  |  |  |  | Axis Sanpada
Date Of Property Visit |  |  |  |  | 2025-08-30
Name of the builder group |  |  |  |  | M/s.Trilok Properties
Name of the builder company |  |  |  |  | M/s.Trilok Properties
Name of the Project |  |  |  |  | Tulsi Kalash City (F & G Wing)
Contact Details ( Name & Contact No.) |  |  |  |  | Ketan Patil -8149591441
Site Person - Contact Details ( Name & Contact No.) |  |  |  |  | Mr. Mahesh : 9967500538
Name / No of the Building |  |  |  |  | F & G Wings
Docouments Provided |  |  |  |  | Refer Data
RERA No. |  |  |  |  | P52000014259
Project location details |  | Tulsi Kalash City (F & G Wing), Sr.No.142/7, 142/8/1, 142/9, 142/11/A,142/12/1/A, 142/12/2, 142/12/3/A, 142/12/4/A, 142/13, 142/14, Savroli - Kharpada Road, Karade Khurd, Panvel, Raigad.
Sr.No |  | 142/7, 142/8/1, 142/9, 142/11/A,142/12/1/A, 142/12/2, 142/12/3/A, 142/12/4/A, 142/13, 142/14 |  |  |  |  | Locality | Karade Khurd
Road | Savroli - Kharpada Road |  |  |  | District | Raigad
City | Panvel |  |  |  | Pin Code | 410220
Near by Landmark |  | Rasayani Police Station |  |  | Distance from city centre: |  | About 3.3 Km from Rasayani Railway Station
Accessibility to the Project from the City: (Proximity to civic amenities like school, hospital, market) |  |  |  |  | all available at 1 to 2 km.
Does property have Electricity / Water / Drainage Connection |  |  |  |  | Yes
Class of locality |  |  |  |  | Middle Class
Nature of land with topographical condtion |  |  |  |  | Plane
Nature of the locality |  |  |  |  | Developing
Quality of infrastructure in vicinity |  |  |  |  | Good
Boundaries |  | East |  | West |  | South |  | North
As per deed |  | NA |  | NA |  | NA |  | NA
At site |  | Road |  | Open |  | Open |  | Road
Does the boundaries at site match, as mentioned in the Docoumentation: NA
Type of Structure : RCC Frame Structure
Latitude & Longitude |  | Latitude |  | 18.8855 |  | Longitude |  | 73.17
Location Link |  | https://goo.gl/maps/5eFcBUhFpCFv5waY7?coh=178572&entry=tt
Approval details:
Approved usage of the Property: |  |  |  |  | Residential
(Restrictive Covenants in regard to Land Use, if any) |  |  |  |  | No
Area Statement Details :
Total land area of the project in Sq. Mt. |  |  |  |  | 30860
Permissible FSI |  |  |  |  | 1.2
Permissible TDR/Paid FSI |  |  |  |  | 0
Total FSI availaible for the project |  |  |  |  | 1.2
Total Approved Builtup area of the project in Sq. Mt. |  |  |  |  | 35208.174
Total number of Buildings |  |  |  |  | 02 Wings
Approval Detail : Plan approval
Layout Approval No |  | MASHA/LNA-1/Case No.112/2016 |  |  |  | Dated | 04/08/2017.
Approved Floor plan No. |  | MASHA/LNA-1/Case No.112/2016 |  |  |  | Dated | 04/08/2017.
Commencement Certificate No. |  | MASHA/LNA-1/Case No.112/2016 Valid Up to: F, G Wings - Stilt+ 1st to 7th Floor. |  |  |  | Dated | 04/08/2017.
O. Certificate No.: |  | J.K.MS/LNA.1(B)/OC/OC.16/2024 Approved Upto : Wing F & G = Gr/St + 1st to 7th Floor Total Flats = 112 Nos. |  |  | Date of approval: | Dated | 2024-06-06 | NA
Commencement date of construction |  |  | 04/08/2017. |  | Expected Completion |  | Completed
Building wise Construction details
Approved area of the building in Sq.Mt |  |  | 35208.174 |  | Approved no of units |  |  | NA
Approved no of Floors |  | F, G Wings - Stilt + 1st to 7th Floor. |  |  |  | No of floors at site : See Construction details
Quality of construction: Good |  |  | Projected life of the structure: 59 Years
Material laying at Site: :Nothing.
Construction details: |  | F & G Wing - Stilt+ 1st to 7th Floor. | [6 empty] | All work completed. Please provide OC.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | All work Completed. OC Received. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 100% |  | 100% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 7 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 7 | 100% | [5 empty] | Plinth in process | 5.25
Possession |  | 7 | 100% | [5 empty] | Plinth completed | 7
Construction details: |  | G Wing - Stilt+ 1st to 7th Floor. | [6 empty] | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process.
Basement | 0 | Ground | 1 | Podium |  | 0 | Floors | 7
Stage of construction: |  | Plinth, RCC, Brick, Plaster, Flooring, Painting work Completed. Finishing work is in process. | [6 empty] | All work Completed. OC Received.
Type of Work |  | Slab/Floor | Complition % |  | Progress % |  | Disbursement % |  | Piling Work in process | 1.75
Excavation |  | 7 | 100% |  | 92.14% |  | 95% |  | Excavation in process | 3.5
Plinth |  | 7 | 100% | [5 empty] | Excavation Completed | 7
RCC (Including podiums) |  | 8 | 100% | [5 empty] | Footing in Process | 1.75
Brickwork | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Footing Completed | 3.5
Internal Plaster | Brickwork & Internal Plaster | 7 | 100% | [5 empty] | Basement 1 | 0
Ext. Plaster & Plumbing | External Plaster & Plumbing | 7 | 100% | [5 empty] | Basement 2 | 0
Flooring & Fitting | Flooring & Fitting | 7 | 100% | [5 empty] | Basement 3 | 0
Painting & Wooden |  | 7 | 100% | [5 empty] | Basement 4 | 0
Building Common Amenities | Building Common Amenities | 3 | 42.86% | [5 empty] | Plinth in process | 5.25
Possession |  | 0 | 0% | [5 empty] | Plinth completed | 7
Wheather the construction is as per approved Building plan : Yes
Violations Observed if any : NA
Proposed Amenities : |  | : 1.Vitrified tiles flooring 2. Granite Kitchen Platform 3. Decorative Enternace etc.
Recommended Rates of the Property :
Recommended rate of the flat Per Sq. Ft. ( on Saleable area) | [5 empty] | 3700
Other Charges (Car Parking) | [5 empty] | 200000/-
Club Charges | [5 empty] | 75000/-
Development charges | [5 empty] | 2,50,000/-
Distressed valuation of the Property | [5 empty] | 2960
Remark : 1. All work Completed. OC Received. 2. We have considered rate by verifying it from market inquire. 3. Car parking is subjected to authentic documentation. 4. We have updated OC from Rera (On 22/02/2025). 4. On site, we meet Mr.Vinayak - 8108978930.
Authorized Signatory Name & Seal of the agency
PHOTOGRAPHS OF PROPERTY : |  |  | Tulsi Kalash City (F & G Wing)
Google Map :
Wing G
Wing G
Wing F & G
Wing F & G

## VALUATION
Market Research Data
Source | Distance from proposed property | Flat | Net Carpet | Saleable Area | Rate on Saleable | Market Value
Magic Brick | Tulsi Kalash City (F & G Wing) | 2BHK | 540 | 810 | 3703.7037 | 3000000
Average |  |  |  |  | 3703.7037
Valuation Adopted |  |  |  |  | 3700

## Note
2020-03-11 | Asmita | OLD APF
2021-02-26 | Pratiksha

## F
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 0 | 0 | Progress |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 10 | 30

## G
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 62.5 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 5 | 0 | Progress |  |  | 10 | 25 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 18.75 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 25 | 18.75
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 35 | 48.75

## D
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 100 | Progress |  |  | 10 | 40 | 15 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 15 | 0 | 0 | 0 | 0
| 7 | 7 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 15 | 15
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 65 | 75

## E
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 10 | 100
slab | total slab | completed slab | 100 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 8 | 42.8571 | Progress |  |  | 10 | 40 | 6.4286 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 30 | 30 | 6.4286 | 0 | 0 | 0 | 0
| 7 | 3 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 10 | 30
| 7 | 0 |  | RCC | 40 | 30
Finishing | Total Floor | completed Floor |  | Bricks | 6.4286 | 6.4286
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 56.4286 | 66.4286

## X
Particulars | totaL floor | 7
| total | completed
plinth | 10 | 0 | 0
slab | total slab | completed slab | 0 |  |  |  | p | rcc | Bricks | Plaster | Flooring | Wood & painting | Finishing
| 8 | 0 | 0 | Progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bricks | Total Floor | completed Floor | 0 | Recommended |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | 0
plaster | Total Floor | completed Floor | 0
| 7 | 0 | 0
Flooring | Total Floor | completed Floor
| 7 | 0 |  |  | Progress | Recommended
Wood & painting | Total Floor | completed Floor |  | Plinth | 0 | 20
| 7 | 0 |  | RCC | 0 | 0
Finishing | Total Floor | completed Floor |  | Bricks | 0 | 0
| 7 | 0 |  | Plaster | 0 | 0
|  |  |  | Flooring | 0 | 0
|  |  |  | Wood & painting | 0 | 0
|  |  |  | Finishing | 0 | 0
|  |  |  | total | 0 | 20

## Flat detail
Floor No
Flat | Discription | Carpet |  |  |  | Fungible |  |  | Terrace
1 |  | L | W | A |  | L | W | A | L | W | A
| Hall |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| kitch |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed1 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Bed2 |  |  | 0 | CB |  |  | 0 |  |  | 0
|  |  |  | 0 | FB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| toilet1 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet2 |  |  | 0 | DB |  |  | 0 |  |  | 0
| toilet3 |  |  | 0 | DB |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| passage1 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage2 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage3 |  |  | 0 |  |  |  | 0 |  |  | 0
| passage4 |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
|  |  |  | 0 |  |  |  | 0 |  |  | 0
| Total |  | 0 | 0 |  |  | 0 | 0 |  | 0 | 0
|  |  | 0 | 0